DRAFT

CONTRACT FOR WORK

for

Supplies of gas turbines from 40 to 60 MWe

2024

Elektrárny Opatovice, a.s.

Registered office: no. 478, Opatovice nad Labem, Postal Code: 533 45

Company ID No.: 288 00 621 (authorised contracting entity)

Contracting entity

United Energy, a.s.

Registered office: Teplárenská 2, Most - Komořany,  Postal  Code:  434 03

Company ID: 273 09 959

Plzenska teplárenská a.s.

Registered office: Doubravecká 2760/1, Pilsen,  Postal Code:  301 00

Company ID: 497 90 480

Content

Article 1.	PREAMBLE TO THE AGREEMENT	4

Article 2.	GOVERNING LAW	4

Article 3.	CONTRACTUAL PARTIES	4

Article 4.	DEFINITION AND INTERPRETATION OF TERMS	6

Article 5.	PURPOSE OF AGREEMENT	12

Article 6.	SUBJECT MATTER OF THE AGREEMENT	12

Article 7.	QUALITY AND TECHNICAL CONDITIONS	17

Article 8.	DELIVERY DEADLINES, TIME SCHEDULE	21

Article 9.	PRICE	22

Article 10.	PAYMENT TERMS	28

Article 11.	CHANGEs to the delivery	31

Article 12.	TAXES, DUTIES AND CHARGES	31

Article 13.	spare PARTS	32

Article 14.	ORGANISATION OF WORKS	33

Article 15.	COOPERATION OF THE CUSTOMER	35

Article 16.	SUB-SUPPLIERS and suppliers of major components	37

Article 17.	GOODS, CONSTRUCTION MACHINERY AND SURPLUS GOODS	37

Article 18.	SITE	38

Article 19.	CONTROLS, individual test and completion of assembly	38

Article 20.	COMMISSIONING	40

Article 21.	takeover of the DELIVERY	44

Article 22.	contractual PENALTIES AND late payment INTEREST	47

Article 23.	damages	54

Article 24.	SUPPLIER'S LIABILITY	55

Article 25.	ownership	55

Article 26.	LAWS, SAFETY, ENVIRONMENT	55

Article 27.	WARRANTIES	56

Article 28.	DEFECTS AND THEIR REMOVAL	59

Article 29.	confidentiality	61

Article 30.	WITHDRAWAL FROM THE AGREEMENT	62

Article 31.	suspension OF DELIVERY	63

Article 32.	UNPREDICTABLE AND INSURMOUNTABLE OBSTACLES	64

Article 33.	ASSIGNMENT OF RIGHTS AND OBLIGATIONS	64

Article 34.	DISPUTE RESOLUTION	65

Article 35.	CONFLICT OF INTEREST	65

Article 36.	CONTACTS AND CORRESPONDENCE	65

Article 37.	miscellaneous	66

Article 38.	insurance	68

Article 39.	SIGNATURES	70

# PREAMBLE TO THE AGREEMENT

|  | - CUSTOMER'S AGREEMENT number : [TO BE ADDED] - SUPPLIER'S AGREEMENT number : [TO BE ADDED] |
| --- | --- |
|  | In consideration of the fact that the CUSTOMER desires to receive delivery of the GAS TURBINES, including related services, on the terms and conditions set forth in this AGREEMENT, and that the SUPPLIER is willing to deliver the DELIVERY on the terms and conditions set forth in this AGREEMENT, the CUSTOMER and the SUPPLIER agree as follows. |

# GOVERNING LAW

|  | The AGREEMENT is concluded pursuant to Section 1746(2) of CIVIL CODE with the appropriate application of Section 2586 et seq. of CIVIL CODE. CUSTOMER hereby draws SUPPLIER’s attention to the fact, that all terms (whether capitalized or not) mentioned in the AGREEMENT, if not precisely defined by the AGREEMENT, are further defined in the TENDER DOCUMENTATION. |
| --- | --- |

# CONTRACTUAL PARTIES

## CUSTOMER

|  | Trade Name: Elektrárny Opatovice, a.s. |
| --- | --- |
|  | Registered seat at: No. 478, 533 45 Opatovice nad Labem |
|  | Entry in the Commercial Register: Commercial Register maintained by the Regional Court in Hradec Králové, file no. B 3807 |
|  | Represented by: [TO BE ADDED] [TO BE ADDED] |
|  | ID No.: 275 67 320 TIN: CZ27567320 |
|  | Contact persons for contractual negotiations: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Contact persons for negotiations on technical matters: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Bank connection: [TO BE ADDED] Account number: [TO BE ADDED] |
|  | Hereinafter in this AGREEMENT referred to as CUSTOMER 1. |
|  | Trade Name: United Energy, a.s. |
|  | Registered seat at: Most-Komořany, Teplárenská 2, Postal code: 434 03 |
|  | Entry in the Commercial Register: Commercial Register maintained by the Regional Court in Ústí nad Labem, file no. B 1722 |
|  | Represented by: Ing. Milan Boháček, Vice-Chairman of the Board of Directors Ing. Petr Mareš, member of the Board of Directors |
|  | ID No.: 273 09 959 TIN: CZ27309959 |
|  | Contact persons for contractual negotiations: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Contact persons for negotiations on technical matters: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Bank connection: [TO BE ADDED] Account number: [TO BE ADDED] |
|  | Hereinafter in this AGREEMENT referred to as CUSTOMER 2. |
|  | Trade Name: Plzeňská teplárenská a.s. |
|  | Registered seat at: Doubravecká 2760/1, Plzeň, ZIP code: 301 00 |
|  | Entry in the Commercial Register: Commercial Register maintained by the Regional Court in Pilsen, file no. B 392 |
|  | Represented by: [TO BE ADDED] [TO BE ADDED] |
|  | ID No.: 497 90 480 TIN: CZ49790480 |
|  | Contact persons for contractual negotiations: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Contact persons for negotiations on technical matters: - Name: [TO BE ADDED] - Contact address: [TO BE ADDED] - Phone: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | Bank connection: [TO BE ADDED] Account number: [TO BE ADDED] |
|  | Hereinafter in this AGREEMENT referred to as CUSTOMER 3. |
|  | CUSTOMER 1, CUSTOMER 2 and CUSTOMER 3 hereinafter in this AGREEMENT collectively referred to as CUSTOMER |

## SUPPLIER

|  | Trade Name: [TO BE ADDED BY THE PARTICIPANT] |
| --- | --- |
|  | Registered seat at: [TO BE ADDED BY THE PARTICIPANT] |
|  | Entry in the Commercial Register: [TO BE ADDED BY THE PARTICIPANT] |
|  | Represented by: [TO BE ADDED BY THE PARTICIPANT] |
|  | ID No.: [TO BE ADDED BY THE PARTICIPANT] TIN: [TO BE ADDED BY THE PARTICIPANT] |
|  | Contact persons for contractual negotiations: - Name: [TO BE ADDED BY THE PARTICIPANT] - Contact address: [TO BE ADDED BY THE PARTICIPANT] - Phone: [TO BE ADDED BY THE PARTICIPANT] - E-mail: [TO BE ADDED BY THE PARTICIPANT] |
|  | Contact persons for negotiations on technical matters: - Name: [TO BE ADDED BY THE PARTICIPANT] - Contact address: [TO BE ADDED BY THE PARTICIPANT] - Phone: [TO BE ADDED BY THE PARTICIPANT] - E-mail: TO BE ADDED BY THE PARTICIPANT] |
|  | Bank connection: [TO BE ADDED BY THE PARTICIPANT] Account number: [TO BE ADDED BY THE PARTICIPANT] |
|  | Hereinafter referred to in this AGREEMENT as the SUPPLIER. |

# DEFINITION AND INTERPRETATION OF TERMS

|  | In this AGREEMENT concluded by and between CUSTOMER and SUPPLIER, the terms defined below, when capitalized, shall be construed only as set forth below. |
| --- | --- |

## DEFINITIONS

|  | ACCEPTABLE VALUES ACCEPTABLE VALUES means the permissible limit values of deviations from the GUARANTEED PARAMETERS of DELIVERY set out in Annex 5 to the AGREEMENT which are acceptable to the CUSTOMER. |
| --- | --- |
|  | AZ For the purposes of this AGREEMENT, the term “AZ” or "Copyright Act" shall always mean Act No. 121/2000 Coll., on Copyright, on Rights Related to Copyright and on Amendments to Certain Acts (Copyright Act), as amended. |
|  | PERFORMANCE BOND PERFORMANCE BOND means a bank guarantee for good performance of the DELIVERY. |
|  | ADVANCE PAYMENT GUARANTEE ADVANCE PAYMENT GUARANTEE means a bank guarantee provided by the SUPPLIER before issuance of the advance payment after the signing of the AGREEMENT and advance payment after the fulfilment of Milestone No. 2. |
|  | PRICE PRICE means the total agreed price for the DELIVERY according to Article 9 of the AGREEMENT. |
|  | FINAL ACCEPTANCE CERTIFICATE FINAL ACCEPTANCE CERTIFICATE (or FAC) means the document to be issued by the CUSTOMER upon successful FINAL ACCEPTANCE of the DELIVERY in accordance with the rules set forth in the AGREEMENT. |
|  | PRELIMINARY ACCEPTANCE CERTIFICATE PRELIMINARY ACCEPTANCE CERTIFICATE shall mean the document to be issued by the CUSTOMER after the successful PRELIMINARY ACCEPTANCE of the DELIVERY certifying that the SUPPLIER has fulfilled all its obligations to be fulfilled under the AGREEMENT up to the time of completion of the TESTING OPERATION. |
|  | TIME SCHEDULE TIME SCHEDULE is a document prepared by the SUPPLIER according to the terms and conditions specified in the AGREEMENT and allowing detailed monitoring of the deadlines for the implementation of the DELIVERY in relation to Annex 2 to the AGREEMENT. |
|  | DETAILED TERMS OF DELIVERY DETAILED TERMS OF DELIVERY means detailed specification of term of Delivery pursuant to paragraph 6.1.1.2 of the AGREEMENT. |
|  | DELIVERY DELIVERY means all performance to be performed in relation to 1 (one) GAS TURBINE including delivery GOODS and EQUIPMENT to be provided, under the terms and conditions set out below, including related engineering, procurement of supplies, licenses necessary for the supply of DELIVERY and including the removal of any DEFECTS as necessary for its performance. DELIVERY shall also mean all other related work and services described or referred to in the AGREEMENT or required for its performance under the terms of the AGREEMENT. The DELIVERY must altogether comprise complete, functional, safe and continuously operable reliable facility, that complies with the parameters defined in the AGREEMENT. |
|  | AS-BUILT DOCUMENTATION AS-BUILT DOCUMENTATION includes documentation according to Annex 7 to the AGREEMENT prepared in accordance with REGULATIONS, which is necessary for the safe installation, operation and maintenance of the DELIVERY. |
|  | CONFIDENTIAL INFORMATION CONFIDENTIAL INFORMATION shall be deemed by the parties hereto to be the terms and conditions of this AGREEMENT, information exchanged between the parties hereto in connection with the DELIVERY, and any information obtained by the SUPPLIER or the CUSTOMER from the other party hereto in connection with the execution or performance of this AGREEMENT, as well as the design, technical details or configurations, know how, methods, practices, procedures, processes and formulas relating to the manufacture, assembly, installation, design or processing of the products and any components thereof. |
|  | EPC CONTRACTOR EPC CONTRACTOR means the person who provides the supply, installation and commissioning of the COMBINED CYCLE UNIT and the installation of the GAS TURBINE. |
|  | FUNCTIONAL TESTS A FUNCTIONAL TESTS are the tests that demonstrates the ability of the DELIVERY as a whole to its operation within the parameters of the AGREEMENT and generally precedes the PERFORMANCE TEST under the AGREEMENT. |
|  | PERFORMANCE TESTS PERFORMANCE TESTS are tests to prove that the DELIVERY meets the GUARANTEED PARAMETERS as per the AGREEMENT. |
|  | GUARANTEED PARAMETERS GUARANTEED PARAMETERS mean the parameters to be met by the DELIVERY, as defined in Annex 5 to the AGREEMENT. |
|  | INDIVIDUAL TESTS The INDIVIDUAL TESTS are tests by which the SUPPLIER is obliged to demonstrate the quality of the supplied GOODS and the CHIEF ASSEMBLY, the assembly work within the scope of the SUPPLIER's obligation under the AGREEMENT, the mechanical functions and tightness of the assembled equipment and the readiness of the DELIVERY to commence the COMPREHENSIVE TESTS within the scope of the AGREEMENT. |
|  | ENGINEERING ORGANISATION OF THE CUSTOMER The SUPPLIER's ENGINEERING ORGANISATION is/are the entity(ies) responsible for coordination, control and other activities in connection with the performance of the AGREEMENT. The CUSTOMER's ENGINEERING ORGANISATION shall be provided by the CUSTOMER. |
|  | COMPREHENSIVE TESTS The COMPREHENSIVE TESTS are tests during which the SUPPLIER shall demonstrate the readiness of the DELIVERY to commence the TESTING OPERATION. The detailed execution of the COMPREHENSIVE TESTS shall be as set out in the COMPREHENSIVE TESTS plan prepared by the SUPPLIER and APPROVED by the CUSTOMER. Detailed information on the conduct of these tests and the obligations during their performance are set out in paragraph 20.2 of the AGREEMENT. |
|  | FINAL ACCEPTANCE OF the DELIVERY FINAL ACCEPTANCE of the DELIVERY shall mean the successful ACCEPTANCE of the DELIVERY by the CUSTOMER after the expiration of the WARRANTY PERIOD and the successful fulfilment of all other obligations of the SUPPLIER in accordance with all requirements set forth in the AGREEMENT. |
|  | COORDINATION The term COORDINATION shall mean taking into account all the time, material, spatial, functional and other links of the DELIVERY with respect to the existing operations and facilities of the CUSTOMER, as well as with respect to other activities of the CUSTOMER, or to activities carried out by third parties for the CUSTOMER. The SUPPLIER is obliged to provide COORDINATION. |
|  | CUSTOMER'S SAFETY COORDINATOR CUSTOMER'S SAFETY COORDINATOR has the meaning assigned to the term "coordinator" in Act No. 309/2006 Coll., regulating other occupational safety and health requirements in labour relations and on ensuring safety and health in activities or provision of services outside labour relations (Act on Ensuring Other Conditions of Occupational Safety and Health), as amended, and is designated by the CUSTOMER prior to commencement of work on the SITE. |
|  | MONTHLY REPORT MONTHLY REPORT means a detailed monthly report on the progress of the SUPPLIER's performance prepared by the SUPPLIER in accordance with the requirements set forth in the AGREEMENT. |
|  | MILESTONE MILESTONE means a binding deadline that serves the CUSTOMER to control and manage the progress of the DELIVERY. MILESTONES are specified in Annex 2 to the AGREEMENT. MILESTONES may be subject to liquidated damages as provided for in the AGREEMENT and may also be subject to the payment of the PRICE in accordance with Annex 3 to the AGREEMENT. |
|  | APPROVED APPROVED means approved in writing by the CUSTOMER. The following shall apply with respect to the SUPLLIER's written output, if not stipulated otherwise in the AGREEMENT: - The CUSTOMER is obliged to send the SUPPLIER its justified comments on the written output within 10 working days from its delivery by the SUPPLIER or to to issue the approval of the written output; if the CUSTOMER does not send the SUPPLIER its justified comments on the written output within 10 working days from the date of delivery, the written output shall be deemed to have been APPROVED by the CUSTOMER; - The SUPPLIER is obliged to settle the justified comments of the CUSTOMER, to modify its the written output and to forward it again to the CUSTOMER for APPROVAL without undue delay, but no later than within 10 working days of submission of the CUSTOMER's justified comments; - The CUSTOMER is obliged to send the SUPPLIER its justified comments on the updated written output within 10 working days from its delivery by the SUPPLIER or to to issue the approval of the written output; if the CUSTOMER does not send the SUPPLIER its justified comments on the written output within 10 working days from the date of delivery, the written output shall be deemed to have been APPROVED by the CUSTOMER; this procedure shall be repeated until all the CUSTOMER's justified comments have been settled. The SUPPLIER is obliged to submit the documents for APPROVAL in time so that the subsequent deadlines can be met. The conflict of the written output with the AGREEMENT shall be considered the justified comment of the CUSTOMER. In the case of written outputs relating to the PERFORMANCE TEST Plan – Part "A" and the PERFORMANCE TEST Plan – Part "B", the principles according to this paragraph of the AGREEMENT shall be applied, however the party submitting written outputs for approval shall be the CUSTOMER and the party granting the approval shall be the SUPPLIER. |
|  | COMBINED CYCLE UNIT COMBINED CYCLE UNIT means the equipment connected and adjacent to the GAS TURBINE, which forms one functional technological unit with the GAS TURBINE. |
|  | QUALITY ASSURANCE PLAN The QUALITY ASSURANCE PLAN is a document by which the SUPPLIER defines the quality of individual parts of the DELIVERY in relation to the requirements set by the CUSTOMER in the AGREEMENT. |
|  | GAS TURBINE GAS TURBINE means a gas turbine as defined in Annex 8 to the AGREEMENT. |
|  | SUB-SUPPLIER SUB-SUPPLIER shall have the meaning assigned to such term in paragraph 16.1 of the AGREEMENT. |
|  | PRELIMINARY ACCEPTANCE OF DELIVERY PRELIMINARY ACCEPTANCE OF DELIVERY means the successful ACCEPTANCE of DELIVERY by the CUSTOMER upon successful completion of the INDIVIDUAL TESTS, COMPREHENSIVE TESTS, FUNCTIONAL TESTS, TRIAL RUN and PERFORMANCE TESTS and possibility to place the DELIVERY in CONTINUOUS OPERATION in accordance with all requirements specified or referred to in the AGREEMENT. |
|  | REGULATIONS REGULATIONS shall mean all applicable binding legal regulations of the Czech Republic, directly applicable legal regulations of the European Union and internal by-laws and regulations of the CUSTOMER which are part of the AGREEMENT. The REGULATIONS are binding on the DELIVERY, its implementation and all activities of the SUPPLIER. |
|  | TAKEOVER TAKEOVER includes all takeovers during the execution of the DELIVERY. A takeover report shall be drawn up for each TAKEOVER. |
|  | AGREEMENT AGREEMENT shall mean this DELIVERY AGREEMENT entered into between the CUSTOMER and the SUPPLIER. The following annexes form an integral part of the AGREEMENT: - Annex 1 - Binding LTSA draft, - Annex 2 - List of MILESTONES, - Annex 3 - Payment Schedule , - Annex 4 - Price tables, - Annex 5 - GUARANTEED PARAMETERS of DELIVERY, - Annex 6A - List of SUB-SUPPLIERS, - Annex 6B - List of suppliers of major components, - Annex 7 - BOOK "B", TENDER DOCUMENTATION - Annex 8 - Part of the SUPPLIER's offer, - Annex 9 - Rules for suppliers, - Annex 10 - Welding inspection management rules and other CUSTOMER's by-laws, - Annex 11 - GDPR Information , - Annex 12 - Form of Parent Company Guarantee - Annex 13 - Table for Assessment of the Risks In the event of a conflict between the AGREEMENT and any attachment thereto, the AGREEMENT shall prevail. In the event of a conflict between Annexes, the text of the Annex with the lower serial number shall prevail. This AGREEMENT is drawn up in the Czech language. |
|  | SITE SITE means the location as more fully described in Annex 7 to the AGREEMENT. Annex 7 to the AGREEMENT also describes the land and other locations where the DELIVERY will be carried out. |
|  | Chief Assembly Provision of advice and technical guidance within the installation of the equipment according to the documentation prepared by the SUPPLIER in accordance with the AGREEMENT at the place of its installation by a qualified person of the SUPPLIER, for the purpose of safe installation, COMMISSIONING and training of the CUSTOMER's operators. |
|  | CONTINUOUS OPERATION CONTINUOUS OPERATION is the period after the completion of the TESTING OPERATION when the DELIVERY is operated and used for its intended purpose throughout the whole lifetime of the DELIVERY. Within the CONTINUOUS OPERATION, the WARRANTY PERIOD runs. |
|  | COMPLETION OF ASSEMBLY COMPLETION OF ASSEMBLY means the point at which the DELIVERY is completed in accordance with the detail design and its assembly is completed. Furthermore, the necessary INDIVIDUAL TESTS have been successfully carried out and the documentation as per paragraph 19.5.2 of the AGREEMENT has been provided in accordance with the AGREEMENT and other conditions of the AGREEMENT precedent to the COMPLETION OF ASSEMBLY have been fulfilled. With the COMPLETION OF ASSEMBLY, the DELIVERY is ready to start the COMPREHENSIVE TESTS. The parties to the AGREEMENT shall execute a report on the COMPLETION of the ASSEMBLY. |
|  | COMMISSIONING COMMISSIONING includes activities leading to the enabling of the CONTINUOUS OPERATION of the DELIVERY and is further defined in Article 20 of the AGREEMENT. |
|  | INITIAL DOCUMENTATION OF DELIVERY The INITIAL DOCUMENTATION of DELIVERY is defined in Annex 7 to the AGREEMENT. |
|  | RIGHTS OF USE RIGHTS of USE represent all rights of use to the intangible and tangible components of the DELIVERY that are by their nature necessary for the CUSTOMER to operate and maintain the DELIVERY without interference, including the right to use the DELIVERY (license). Since the DELIVERY include a performance that may constitute a work of authorship within the meaning of the AZ, the following rights are granted to these parts of the DELIVERY: - for software products (proprietary/platform software) considered to be works of authorship under the AZ supplied as part of the DELIVERY (hereinafter referred to as "Software"), a user license to use the Software for the purpose of operation and routine maintenance of the WORK and to the extent deemed necessary, appropriate or reasonable by the SUPPLIER. For the avoidance of doubt, this means that the CUSTOMER is entitled to use the Software in the necessary quantity and within the territory of the Czech Republic, and in a manner consistent with the license terms and conditions provided by the software supplier to the SUPPLIER. These user licenses are granted on a non-exclusive basis and are granted for at least the term of the AGREEMENT and thereafter until the end of the next calendar year following the year in which the AGREEMENT expired. The licenses granted under this provision of the AGREEMENT shall extend to all updates and upgrades to the Software. - In the event that the SUPPLIER's activities under the AGREEMENT result in a performance (in particular, software necessary for the operation (control) of the DELIVERY, except for the software described in the preceding bullet point, and all documentation) that is subject to protection under the AZ (hereinafter referred to as the "Performance"), the paragraph above shall not apply to such performance, but the SUPPLIER grants to the CUSTOMER and the CUSTOMER obtains from the SUPPLIER the right to exercise the right to use the Performance, to the extent necessary for the proper use of the Performance by the SUPPLIER for the entire period during which the Performance is operated by the SUPPLIER. In particular, the CUSTOMER acquires from the SUPPLIER the right to use such Work in the form of the license agreement set forth below (the "License"): - The license is granted as a non-exclusive license to all reasonable uses of the Performance related to the purpose for which such Performance was created by the SUPPLIER in accordance with the AGREEMENT, to the extent necessary for the proper use of the DELIVERY by the CUSTOMER; - The License is granted as irrevocable, unlimited in quantity and as limited to the territory of the Czech Republic and for the purpose of operation and maintenance of the DELIVERY. If the Performance is a computer program, the SUPPLIER is also obliged to hand over to the CUSTOMER after the expiry of the WARRANTY PERIOD source codes of the application software of the control system, except for the parts dealing with the control of the gas turbine itself, for which the SUPPLIER shall only provide the input and output data. Application software of the control system shall be provided by the SUPPLIER including the related documentation, by being stored on the data means reserved for this purpose by the CUSTOMER or by handing over the performance of which such Performance forms a part, on a data carrier, at the latest on the date of hand over of such performance; - Further, the License is granted for a definite term (for the period during which the DELIVERY will be operated), is non-transferable and non-assignable, i.e., it is granted without the right to sublicense or assign the License to any third party; the CUSTOMER is not obliged to use the License, even in part. - The obligation regarding the License shall also apply to the SUPPLIER in the case of performance of part of the Performance by the SUB-SUPPLIER. The License is granted to the maximum extent permitted by applicable law; the SUPPLIER hereby declares that, in the event of creation of the Performance, it shall secure all rights to the Performance, in particular, but not exclusively, that it shall obtain all author or third party rights to such Performance and shall be entitled to grant them to the CUSTOMER. - The SUPPLIER further grants to the CUSTOMER by this AGREEMENT with respect to the Performance (all the documentation) the right to modify, alter, interfere with, combine it with another work, incorporate it into a complete work, all to the extent that the DELIVERY may be operated for the purpose of the AGREEMENT after the expiration of the WARRANTY PERIOD. He is authorized to perform the aforementioned activities independently or through a third party (contractor), provided that the Work shall be subject to Confidentiality in accordance with this AGREEMENT. The SUPPLIER, by signing this AGREEMENT, confirms that it is authorized to grant the said rights to the CUSTOMER and that no unlawful interference with the rights of third parties (authors) will occur. By signing the AGREEMENT, the CUSTOMER expressly declares that the remuneration for all RIGHTS of USE granted to the CUSTOMER under the AGREEMENT is already included in the price for the provision of the DELIVERY. The granting of all RIGHTS of USE shall not be terminable by the SUPPLIER and shall not be affected by the termination of the AGREEMENT. |
|  | DEFECT DEFECT shall mean that due to a fault on the part of the SUPPLIER the DELIVERY or a part thereof has a defect in material or workmanship and/or the DELIVERY does not meet the requirements imposed on it by the AGREEMENT. DEFECT shall include arrears of work as well. |
|  | TENDER DOCUMENTATION All written documents containing the tender terms and conditions communicated or made available to the PARTICIPANTS at the commencement of the PUBLIC PROCUREMENT PROCEDURE for the execution of the DELIVERY, including any subsequent revisions and clarifications, including the forms pursuant to Section 212 of the PPA and the invitations listed in Annex 6 to the PPA. |
|  | CODE/CIVIL CODE For the purposes of this AGREEMENT, the term CODE, or CIVIL CODE, shall always mean Act No. 89/2012 Coll., the Civil Code, as amended. |
|  | WARRANTY PERIOD WARRANTY PERIOD is the period of time during which the SUPPLIER warrants that the DELIVERY is free from DEFECTS. The length of the WARRANTY PERIOD for the DELIVERY is set out in Article 27 of the AGREEMENT below. |
|  | PARENT COMPANY GUARANTEE PARENT COMPANY GUARANTEE constitutes parent company guarantee provided by the parent company of the SUPPLIER in the form introduced in Annex 12 hereto. |
|  | GOODS GOODS means all supplies, products, equipment, parts, materials, spare parts, under the AGREEMENT. GOODS supplied for DELIVERY under the AGREEMENT shall be new at the time of the first delivery of the first GAS TURBINE (not more than 2 years at the time of this AGREEMENT coming into effect) and delivery of used GOODS shall be deemed a failure to comply with this condition and shall result in non-acceptance of the GOODS unless otherwise agreed by the contractual parties. For the avoidance of doubt, delivery of repaired or reconditioned parts of the GOODS within and for the purpose of the removal of DEFECTS is permitted. Furthermore, this provision shall not apply to SUPPLIER's use of SUPPLIER's original equipment with the prior consent of the CUSTOMER. |
|  | TESTS TEST means any INDIVIDUAL TEST, COMPREHENSIVE TEST, FUNCTIONAL TESTS, TRIAL RUN and PERFORMANCE TESTS. |
|  | TRIAL RUN TRIAL RUN shall confirm the reliability of the DELIVERY according to the terms and conditions set forth in the AGREEMENT and will be performed in accordance with the TRIAL RUN schedule (72 hours). |
|  | TESTING OPERATION TESTING OPERATION means the operation of the DELIVERY by the CUSTOMER and SUPPLIER after completion of the necessary INDIVIDUAL and COMPREHENSIVE TESTS which shall demonstrate and confirm that the DELIVERY can be operated in a safe manner on a permanent basis. In exceptional cases and with the CUSTOMER's consent, the INDIVIDUAL and COMPREHENSIVE TESTS may also be performed during the TESTING OPERATION. The TESTING OPERATION includes FUNCTIONAL TESTS, TRIAL RUN and PERFORMANCE TEST - Part "A". This AGREEMENT also uses the term test operation as per the building permit. This term shall mean operation of the DELIVERY as required by the building permit, if necessary to implement the DELIVERY, and PAC shall not refer to the test operation as per the building permit. If the building permit is not required by the REGULATIONS, the term test operation as per the building permit shall be disregarded. It is understood that the TRIAL RUN and any test operation under the building permit may be conducted during the same time period. For the avoidance of doubt, the participation of the SUPPLIER in the test operation as per the building permit is not included in the scope of the DELIVERY according to the AGREEMENT and will be agreed as change of the DELIVERY according to Article 11 of the AGREEMENT in case of the SUPPLIER's request. |
|  | PPA For the purposes of this AGREEMENT, the term "PPA" shall always mean Act No. 134/2016 Coll., on Public Procurement, as amended. |

# PURPOSE OF AGREEMENT

|  | This AGREEMENT is entered into for the purpose of supplying turbines for the construction of new COMBINED CYCLE UNITS by CUSTOMER 1, CUSTOMER 2 and CUSTOMER 3 in accordance with the requirements set out in the AGREEMENT. |
| --- | --- |
|  | The Parties acknowledge that CUSTOMER 1, CUSTOMER 2 and CUSTOMER 3 shall not be obliged to perform jointly and severally under the AGREEMENT and the obligations relating to each DELIVERY shall always be performed by the CUSTOMER that is referred to in DETAILED TERMS OF DELIVERY pursuant to paragraph 6.1.1.2 of the AGREEMENT. |

# SUBJECT MATTER OF THE AGREEMENT

## SUBJECT MATTER OF THE AGREEMENT

|  | The subject matter of the AGREEMENT is the proper performance of the DELIVERY according to the requirements set out in the AGREEMENT. The SUPPLIER undertakes to deliver the GAS TURBINE to the SITE (as defined in Annex 7 to the AGREEMENT (location of the gas turbine) - Part B.2). Drawings, TP-G-0183 - Situation EOP/TP-G-0184 - Situation UE/TP-G-0185 - Situation PL) under the terms of the TDP without unloading on the SITE (INCOTERMS 2020), in a proper and timely manner, at its own cost and risk and to execute and handover the DELIVERY to the CUSTOMER to the extent and in the manner specified in the AGREEMENT. The CUSTOMER agrees to accept the duly executed DELIVERY and to pay the agreed PRICE in the amount and manner set forth in the AGREEMENT. |
| --- | --- |
|  | With respect to the provision of the DELIVERIES, the SUPPLIER undertakes to supply 7 GAS TURBINES according to the CUSTOMER's requirements. |
|  | The CUSTOMER undertakes to take over 7 GAS TURBINES from the SUPPLIER for the purpose of providing the DELIVERIES, in compliance with the following rules: - The CUSTOMER is obliged to deliver to the SUPPLIER no later than by the deadline specified in the following table DETAILED TERMS OF DELIVERY (but not earlier than 27 months before the required date of delivery of the GAS TURBINE to the construction site; earlier delivery is not taken into account, unless otherwise agreed by the contracting parties), which will, the determination of the date of delivery of the GAS TURBINE and the information on the application of the CUSTOMER‘s right not to take over a part of the DELIVERY pursuant to paragraph 9.1.6 of the AGREEMENT, if this is exercised by the CUSTOMER; within 15 days after delivery of the DETAILED TERMS OF DELIVERY, the SUPPLIER is obliged to hand over to the CUSTOMER four copies of the signed service contract according to Annex 1 to the AGREEMENT and within two months after this handover the CUSTOMER is obliged to hand over to the SUPPLIER two copies of the service contract signed by the CUSTOMER; - if the CUSTOMER fails to deliver the DETAILED TERMS OF DELIVERY to the SUPPLIER by the deadline specified in the following table, the SUPPLIER shall call upon the CUSTOMER to remedy the situation and provide him with a period of at least 15 days to remedy the situation (to deliver the DETAILED TERMS OF DELIVERY); - if the CUSTOMER fails to deliver the DETAILED TERMS OF DELIVERY to the SUPPLIER even within the deadline for remedy, the date of delivery of the GAS TURBINE to the construction site (meeting the MILESTONE No. 3) is the earliest possible date specified in the following table and the CUSTOMER’s right not to take over a part of the DELIVERY pursuant to paragraph 9.1.6 of the AGREEMENT is not applied; The SUPPLIER is obliged to notify the CUSTOMER of the missed delivery of the DETAILED TERMS OF DELIVERY and to hand over to the CUSTOMER four copies of the signed service contract according to Annex 1 to the AGREEMENT within 15 days after the expiry of the deadline for remedy and within two months after this handover the CUSTOMER is obliged to hand over to the SUPPLIER two copies of the service contract signed by the CUSTOMER. - The CUSTOMER undertakes to send DETAILED TERMS OF DELIVERY to the SUPPLIER on the same day for: - GAS TURBINE No. 2, 3, 4 (the same date of sending the DETAILED TERMS OF DELIVERY) and - GAS TURBINE No. 5 and 6 (the same date of sending the DETAILED TERMS OF DELIVERY) and Serial number of the GAS TURBINE/CUSTOMER/ place of DELIVERY; Latest date for delivery of the specification of the terms of delivery of the GAS TURBINE on the construction site (meeting the MILESTONE No. 3) – DETAILED TERMS OF DELIVERY; Delivery date for the GAS TURBINE on site (meeting MILESTONE No. 3). 1/ CUSTOMER 2 / CONSTRUCTION SITE OF CUSTOMER 2; 18 months prior the delivery date; 16.01.2026 - 16.07.2026. 2/ CUSTOMER 1 / CONSTRUCTION SITE OF CUSTOMER 1; 18 months prior the next delivery date at maximum; 12.07.2026 - 12.01.2027. 3/ CUSTOMER 1 / CONSTRUCTION SITE OF CUSTOMER 1; 18 months prior the delivery date; 11.10.2026 - 11.04.2027. 4/ CUSTOMER 1 / CONSTRUCTION SITE OF CUSTOMER 1; 18 months prior the delivery date; 11.01.2027 - 11.07.2027. 5/ CUSTOMER 3 / CONSTRUCTION SITE OF CUSTOMER 3; 18 months prior the delivery date; 07.07.2027 - 07.01.2028. 6/ CUSTOMER 3 / CONSTRUCTION SITE OF CUSTOMER 3; 18 months prior the delivery date; 06.10.2027 - 06.04.2028. 7/ CUSTOMER 2 / CONSTRUCTION SITE OF CUSTOMER 2; 18 months prior the delivery date; 03.04.2028 - 03.10.2028. The date of delivery of the GAS TURBINE to the construction site (meeting of MILESTONE No. 3) and the latest date for sending information on specifying the terms of delivery of the GAS TURBINE to the site of construction (meeting of MILESTONE No. 3) – DETAILED TERMS OF DELIVERY may be changed based on the agreement of the contracting parties. The SUPPLIER is obliged to launch the execution of the DELIVERY as per the AGREEMENT within 1 month of delivery of the DETAILED TERMS OF DELIVERY or within 15 days of the expiry of the remedial period pursuant to paragraph 6.1.1.2 of the AGREEMENT, if the DETAILED TERMS OF DELIVERY are not delivered by the CUSTOMER, at the latest. |
|  | The subject matter of the AGREEMENT is co-financed from the resources of the State Environmental Fund of the Czech Republic (SFŽP ČR) within the Modernization Fund. |
|  | The SUPPLIER undertakes that it and its SUB-SUPPLIERS shall allow representatives of the SFŽP ČR to obtain and use photographic material and film footage of the subject matter of the AGREEMENT at the SITE, and to provide these to third parties in accordance with the REGULATIONS. The CUSTOMER agrees to use its best efforts to ensure that representatives of SFŽP ČR are bound to the same confidentiality obligations as defined in the AGREEMENT. |
|  | The SUPPLIER is obliged to allow any persons authorised to carry out the control of the financing of the subject of the AGREEMENT to carry out the control in accordance with the REGULATIONS of all relevant documents, especially accounting documents, related to the implementation of the subject matter of the AGREEMENT, for the period of time specified by the legislation of the Czech Republic for their archiving (in particular Act No. 563/1991 Coll., on Accounting, as amended, and Act No. 235/2004 Coll., on Value Added Tax, as amended). |
|  | The SUPPLIER acknowledges that in accordance with Act No. 320/2001 Coll., on financial control in public administration and on amendments to certain acts (Act on financial control), as amended, it is obliged to cooperate in the performance of financial control carried out in connection with the payment of benefits from public expenditure and undertakes to provide maximum cooperation in this respect. |
|  | For the avoidance of doubt, the parties agree that any procedure, protocol, liquidated damages and other legal effect described in this AGREEMENT shall apply separately to each GAS TURBINE delivered under this AGREEMENT, and all contractual obligations of the parties shall be satisfied with respect to any one GAS TURBINE upon its FINAL ACCEPTANCE, except as provided in paragraph 37.1 of the AGREEMENT. |
|  | The SUPPLIER hereby declares that the specific type of GAS TURBINE [TO BE ADDED BY THE PARTICIPANT] that is subject matter of the DELIVERY, has reached a minimum of 8 000 hours in operation without serious defects. |
|  | Information on DETAILED TERMS OF DELIVERY as per paragraph 6.1.1.2 of the AGREEMENT shall be submitted by the CUSTOMER in the electronic form via SUPPLIER’s e-mail address [TO BE ADDED BY THE PARTICIPANT]. The SUPPLIER is entitled to change this e-mail address but shall inform the CUSTOMER thereof in writing. The change of the SUPPLIER’s e-mail address is effective vis-a-vis the CUSTOMER at the moment of delivery of the written notification of the change to the CUSTOMER. |

## SPECIFICATION OF DELIVERY

|  | The SUPPLIER shall perform all work, activities, CHIEF ASSEMBLY and deliveries of GOODS that are necessary for the proper functioning of the DELIVERY or part thereof executed by it under the AGREEMENT. The DELIVERY under the AGREEMENT shall be delivered in a workmanship and quality that meets all requirements specified in the AGREEMENT. |
| --- | --- |
|  | The SUPPLIER's performance includes in particular: |
|  | Execution of the DELIVERY to the extent and under the terms and conditions set forth in the AGREEMENT. |
|  | Processing and transmission of documentation and information related to to the SUPPLIER |
|  | Processing and delivery of spare parts lists including subsequent delivery of spare parts according to Article 13 of the AGREEMENT. |
|  | Preparation and submission of the QUALITY ASSURANCE PLAN according to paragraph 7.2 of the AGREEMENT. |
|  | Preparation, submission and regular updating of the TIME SCHEDULE for the implementation of the DELIVERY according to paragraph 8.2 of the AGREEMENT. |
|  | Preparation and delivery of instructions for operation, operation and routine maintenance (manuals) of the DELIVERY including all safety, fire and environmental regulations. The routine maintenance instructions (manual) shall cover the entire proposed lifetime of the DELIVERY (20 years of operation). |
|  | Management of the execution of the DELIVERY and coordination of the SUPPLIER's SUB-SUPPLIERS. |
|  | Quality management and control throughout the execution of the DELIVERY in accordance with ISO 9001:2000 series standards and Article 7 of the AGREEMENT. |
|  | Preparation of regular MONTHLY REPORTS on the development of the DELIVERY according to paragraph 14.5.2 of the AGREEMENT. |
|  | Participation in meetings with the participation of representatives of the SUPPLIER and the CUSTOMER according to paragraph 14.4 of the AGREEMENT. |
|  | At the time of presence at the SITE, participation in regular weekly and operational daily meetings as required by the CUSTOMER and/or as required for the implementation of the DELIVERY. |
|  | Participation in all meetings organized by the CUSTOMER and related to the DELIVERY within the framework of the COORDINATION. |
|  | The DELIVERY shall be delivered according to INCOTERMS 2020, DDP SITE of the specific CUSTOMER as defined in Annex 7 to the AGREEMENT (location of the gas turbine) - part B.2 Drawings, TP-G-0183 - Situation of EOP/TP-G-0184 - Situation of UE/TP-G-0185 - Situation of PL (without unloading at the SITE). Partial deliveries will be allowed subject to the following conditions: - SUPPLIER shall have the right to deliver a partial portion of the DELIVERY up to 30 calendar days prior to the date of delivery of the DELIVERY; - The SUPPLIER is obliged to inform the CUSTOMER no later than 30 calendar days prior to the delivery of a partial part of the DELIVERY what partial part of the DELIVERY and in what timeframe it will be delivered; - no storage conditions will be imposed by the SUPPLIER on the partial parts of the DELIVERY delivered by the SUPPLIER before the date of delivery of the DELIVERY (the partial part of the DELIVERY will be stored by the CUSTOMER in the outdoor premises of the SITE). |
|  | The EPC CONTRACTOR shall keep a construction diary in accordance with Decree No. 499/2006 Coll., on construction documentation, Annex 16, as amended, or the subsequent regulations. In accordance with Section 152(6) of Act No. 183/2006 Coll., on Spatial Planning and Building Code (Building Act), as amended, or the subsequent regulations, the SUPPLIER shall provide the EPC CONTRACTOR with the necessary cooperation. |
|  | Conduct all inspection and proof tests specified in the AGREEMENT, verifying proper performance of the DELIVERY and demonstrating safe operation and functionality of the equipment. |
|  | Maintaining a book of checks, inspections and tests, which will contain records of all checks and TAKEOVERS carried out during the implementation of the DELIVERY according to the requirements of the QUALITY ASSURANCE PLAN. |
|  | Repairs (restoration to original condition) of all tangible assets of the CUSTOMER damaged due to the causes attributable to the SUPPLIER during the execution of the DELIVERY. |
|  | The DELIVERY does not include the first refills of equipment as specified by the SUPPLIER to be supplied by the EPC CONTRACTOR. Further, the DELIVERY does not include fuel, water, steam, raw materials and consumables necessary for the normal operation of the DELIVERY. |
|  | Prior to commencing any activities on the SITE that may affect or restrict the activities of other contractors or the activities of the CUSTOMER, the SUPPLIER shall discuss such activities with the CUSTOMER's representative in advance and request APPROVAL to undertake such activities. |
|  | Ensuring all permits necessary for the implementation of the DELIVERY required by regulations and decisions of governmental authorities to be obtained on behalf of the SUPPLIER, except those secured by the CUSTOMER pursuant to the AGREEMENT and providing assistance in securing all permits necessary to implement the DELIVERY required by regulations and decisions of governmental authorities to be secured by the CUSTOMER. |
|  | Performing INDIVIDUAL TESTS of DELIVERY in pursuance of the CHIEF ASSEMBLY. |
|  | Performing COMPREHENSIVE TESTS of DELIVERY. |
|  | Training of the CUSTOMER's employees for operation and maintenance of the DELIVERY. The training will be conducted in the Czech language. |
|  | Performing FUNCTIONAL TESTS and TRIAL RUN. |
|  | Performing PERFORMANCE TEST – Part “A” and PERFORMANCE TEST – Part “B” in pursuance of the CHIEF ASSEMBLY. |
|  | Delivery of the DELIVERY to the CUSTOMER in the manner according to the AGREEMENT. |
|  | Elimination of all DEFECTS found during the execution of the DELIVERY, INDIVIDUAL TESTS, COMPREHENSIVE TESTS, TESTING OPERATION, PERFORMANCE TEST and WARRANTY PERIOD. |
|  | Provision of technical supervision during the TESTING OPERATION of the DELIVERY within the framework of the CHIEF ASSEMBLY. |
|  | Securing and transferring the RIGHTS OF USE to the SUPPLIER. |
|  | Ensuring compliance with all REGULATIONS. |

## PLACE OF PERFORMANCE

|  | The SUPPLIER acknowledges that the location of the installation of the GAS TURBINES is the premises of the heating plant of CUSTOMER 1, CUSTOMER 2 and CUSTOMER 3 according to the DETAILED TERMS OF DELIVERY, which is the key facility for the production and distribution of thermal energy carried out in the public interest and for the supply of electricity to the public distribution system according to Act No. 458/2000 Coll., on the conditions of business and the exercise of state administration in the energy sectors and on the amendment of certain acts (Energy Act), as amended. |
| --- | --- |
|  | The SUPPLIER undertakes to comply with all the CUSTOMER's internal regulations governing access to these premises listed in Annexes 9 and 10 to the AGREEMENT, where the relevant CUSTOMER's regulations listed in these annexes will be applied to the respective SITE (i.e. CUSTOMER 1's regulations shall be complied with at CUSTOMER 1's SITE, CUSTOMER 2's regulations shall be complied with at CUSTOMER 2's SITE, etc.), or as notified to the SUPPLIER in the course of performance of the AGREEMENT. All SUPPLIER's personnel, including SUB-SUPPLIERS' personnel, shall be instructed on the conditions of access to and movement in restricted or prohibited areas and on the SITE. They will be required to comply with these conditions, failure to do so may be grounds for barring individual workers from the site. |

## RESTRICTIVE MEASURES IN RELATION TO SANCTIONS DUE TO VIOLATIONS OF INTERNATIONAL RIGHTS AND THE CONFLICT IN UKRAINE

|  | The SUPPLIER declares that, as of the date of conclusion of the AGREEMENT, the information provided in the affidavit submitted in its request for participation in accordance with Article 10 of the TENDER DOCUMENTATION (for the first stage of the tendering procedure - qualification documentation) is true and veracious. |
| --- | --- |
|  | The SUPPLIER shall inform the CUSTOMER without undue delay, but no later than within 25 working days, that it has become aware of any of the following facts: - The SUPPLIER or its subcontractors are persons who are subject to international sanctions under the law regulating the implementation of international sanctions, on the basis of which the CUSTOMER may not award a public contract to a participant in the procurement procedure pursuant to Section 48a of the PPA; - The SUPPLIER or its subcontractors are persons who are subject to international sanctions under the law regulating the implementation of international sanctions, on the basis of which the CUSTOMER may not make available funds for the performance of the AGREEMENT (on the date of entry into force of the AGREEMENT pursuant to Section 5 of Act No. 69/2006 Coll., on the Implementation of International Sanctions, as amended). If the CUSTOMER transfers the DELIVERY (hardware and/or software and/or technology as well as corresponding documentation and/or works and services, regardless of the method of provision and/or including all types of technical support) provided by the SUPPLIER or parts thereof to a third party worldwide, the CUSTOMER shall comply with all applicable national and international export (re-)control regulations. In any case, the SUPPLIER shall comply with the (re-)export control regulations of the Federal Republic of Germany, Sweden, the European Union and the United States of America. If export controls are required, the CUSTOMER shall, upon the SUPPLIER's request and in accordance with applicable national and international regulations, promptly provide the SUPPLIER with all information regarding the specific end customer, destination and intended use of the DELIVERY provided by the SUPPLIER, as well as with respect to any existing export control restrictions. The CUSTOMER shall indemnify and hold the SUPPLIER harmless from and against any and all claims, proceedings, actions, fines, losses, costs and damages arising out of or relating to the failure of the CUSTOMER to comply with the export control regulations, and the CUSTOMER shall indemnify the SUPPLIER for all losses and expenses resulting therefrom, unless such failure was not caused by the fault of the CUSTOMER. This provision shall not constitute a change in the legal burden of proof. |

# QUALITY AND TECHNICAL CONDITIONS

## QUALITY

|  | The SUPPLIER shall perform the DELIVERY according to the AGREEMENT without DEFECTS so that it can be safely used as per the AGREEMENT. The SUPPLIER shall execute the DELIVERY for the CUSTOMER in such a way that it meets the GUARANTEED PARAMETERS of the DELIVERY as per the AGREEMENT at least within the ACCEPTABLE VALUES at the PRELIMINARY ACCEPTANCE, unless otherwise specified in the AGREEMENT. If the DELIVERY fails to meet the GUARANTEED PARAMETERS within the ACCEPTABLE VALUES specified in Annex 5 to the AGREEMENT, i.e. if the values exceed the unacceptable values specified in Annex 5 to the AGREEMENT, the DELIVERY shall not be deemed to have been performed in compliance with the AGREEMENT unless otherwise agreed by the parties to the AGREEMENT. |
| --- | --- |

## QUALITY ASSURANCE PLAN

|  | The SUPPLIER is obliged to prepare and have the CUSTOMER APPROVE the DETAILED TERMS OF DELIVERY within 180 days from the start of the implementation of the DELIVERY according to paragraph 6.1.1.2 of the AGREEMENT. The QUALITY ASSURANCE PLAN as per the SUPPLIER’s offer shall form a part of the DETAILED TERMS OF DELIVERY. The QUALITY ASSURANCE PLAN shall be binding on the SUPPLIER, the CUSTOMER and all SUB-SUPPLIERS throughout the entire period of performance of the DELIVERY. A document in the SUPPLIER's standard format, which corresponds in substance to the CUSTOMER's requirements for the QUALITY ASSURANCE PLAN (the CUSTOMER accepts in particular a change in the nomenclature or arrangement of the individual parts of the QUALITY ASSURANCE PLAN), shall also be considered a QUALITY ASSURANCE PLAN. In the event of a discrepancy between the similarity of the CUSTOMER's requirements for the QUALITY ASSURANCE PLAN and the documentation submitted by the SUPPLIER, the CUSTOMER's statement shall be decisive and binding on the SUPPLIER. |
| --- | --- |
|  | The QUALITY ASSURANCE PLAN shall include at least the following sections: - Administrative Manual, - Project Work Manual, - Procedure for changes in the DELIVERY, - Manual for Securing Supplies, - Documentation for preparation of the BSE manual including the Table for Assessment of the Risks in compliance with the form as per Annex 13 to the AGREEMENT, - Documentation for preparation of the Environmental Protection Plan, - Documentation for the preparation of the Construction Organisation Plan, - Control, Inspections and Tests plan, - Plan for the TAKEOVERS. Detailed requirements for the scope of the individual parts of the QUALITY ASSURANCE PLAN are given in Annex 7 to the AGREEMENT. |
|  | Essential content of the Administrative Manual: - specification of the AGREEMENT, - Brief description of DELIVERY, - List of documents of the AGREEMENT and their priority, - The names and contact details of the responsible representatives of the CUSTOMER and the SUPPLIER, - Organisational chart of the CUSTOMER and the SUPPLIER with indication and description of mutual relations and determination of responsibilities and authorisations, - Method of communication indicating the binding content, marking and numbering of written correspondence, electronic correspondence, handover protocols, records of telephone conversations and oral meetings, records of meetings, technical queries, etc., - Contact details of persons responsible for the implementation of the QUALITY ASSURANCE PLAN, - Method of distribution of information and documents, - Organisation, agenda and location of daily, weekly and monthly meetings, - List and content of reports, minutes and protocols, - Distribution list. |
|  | Essential content of the Project Work Manual: - Organisation of the design team, - Method of classification, issue, control and reconciliation of documentation, - System of identification, numbering and paper and electronic archiving, - Method of distribution, - Documentation formats and software used, - Distribution list. |
|  | Essential content of the Manual for Securing Supplies: - Delivery Assurance Plan, - List of SUB-SUPPLIERS, - List of items by operating files and construction items to be provided, indicating item number as per the AGREEMENT and documentation, SUB-SUPPLIER and required delivery date to the SITE, - The method of processing and content of documentation according to which the SUPPLIER's piece and other deliveries for the SUPPLIER will be provided, - Contents of supply assurance reports, - Divider. |
|  | Essential contents of the HSE Manual – see Annex 7 to the AGREEMENT. |
|  | Essential content of the Manual of the Environmental Protection - see Annex 7 to the AGREEMENT. |
|  | Essential content of the Construction Organisation Plan: - Organizational chart and implementation team, - Detailed definition of the SITE, - COORDINATION of activities on the SITE, - Method of processing and dates of updating the TIME SCHEDULE, - Schedule the deployment of workers and presence of SUB-SUPPLIERS on the SITE in accordance with the TIME SCHEDULE, - Description of the construction process and use of main assembly equipment (cranes, piling machines, etc.), - The manner and permitting of entry and movement of persons and GOODS to, upon and from the SITE, - Method of record keeping with respect to persons and GOODS, - A list of the CUSTOMER's internal directives and regulations that the SUPPLIER must comply with during activities on the SITE and on the CUSTOMER's premises, - Method of permitting work on the SITE, - Method of ensuring fire protection, - SITE cleaning, - SITE equipment and facilities, - Method of providing security and guarding, - Method of change management in the implementation of the DELIVERY, - Organisation of security on the SITE, - Distribution list. |
|  | Essential content of the Control, Inspection and Tests plan: - Organisational chart for ensuring controls and inspections, - Plan of internal controls and inspections of the SUPPLIER, - Plan of controls and inspections of SUB-SUPPLIERS, - Plan of controls and inspections at the SITE, - INDIVIDUAL TESTS Plan, - COMPREHENSIVE TESTS Plan, - TESTING OPERATION Plan which shall include: - FUNCTIONAL TESTS Plan, - TRIAL RUN Plan, - Materials for the drawing up PERFORMANCE TESTS Plan - Part „A“, - Materials for the drawing up PERFORMANCE TESTS Plan – Part B, - Plan of controls, inspections and tests during the TESTING OPERATION, - Plan of control, inspections and tests during the WARRANTY PERIOD. All plans shall contain at least a list of controls, inspections and tests, their methodology and method of execution, scope and description of activities, list of controlled parameters and required values, sample protocols with the APPROVAL clause, result and proposal for further steps, list of related REGULATIONS. |
|  | Essential content of the Plan for the TAKEOVERS: - Organisational chart for securing the TAKEOVERS, - Plan for TAKEOVERS of GOODS at the SUB-SUPPLIERS, - Schedule of partial TAKEOVERS of the covered-up works, - Schedule of partial TAKEOVERS on the SITE during construction, - Plan of the TAKEOVER before commencement of the TESTING OPERATION, - Plan for the TAKEOVER at PRELIMINARY ACCEPTANCE of the DELIVERY. All plans shall contain at least a list of inspections including the schedule, their method of execution, scope and description, a list of parameters to be inspected and the required values, sample protocols with the APPROVAL clause, the result and a proposal for further action, a list of related REGULATIONS. |

## TECHNICAL CONDITIONS

|  | The GOODS shall be tested (all tests according to the quality control plan) and equipped with all documents according to the AGREEMENT before delivery to the SITE. |
| --- | --- |
|  | The design of the DELIVERY shall allow for easy operation, maintenance and replacement of wear parts and consumables. |
|  | An integral part of the documentation supplied with the GOODS shall be a list of the technical regulations and standards to which the GOODS conform. |
|  | The SUPPLIER must deliver the GOODS with all documents issued by the authorities and testing laboratories for the type of GOODS according to the REGULATIONS and with the declaration of conformity. In particular, the following documents shall be provided: |
|  | Certificates approving the possibility to use the goods in explosive or fire hazardous environments. |
|  | Certificates and passports of pressure vessels. |
|  | Certificates of the goods for fire protection uses. |
|  | The SUPPLIER is obliged to provide and hand over to the CUSTOMER a declaration of conformity according to Act No. 22/1997 Coll., on technical requirements for products and on amendment and supplementation of certain acts, as amended, for the whole DELIVERY and its parts for which it is required by the REGULATIONS. |
|  | The expected life time of the DELIVERY shall be calculated for a period of 20 years from the date of issue of the protocol of PRELIMINARY ACCEPTANCE of the DELIVERY, with a service life within these 20 years of 160,000 hours, provided that the CUSTOMER ensures the operation, repair and maintenance of the DELIVERY in accordance with the instructions received from the SUPPLIER. This statement shall be declaratory only and shall not modify or replace SUPPLIER's warranty obligations under the AGREEMENT. |
|  | Prior to commencing work on any stage of the documentation, the SUPPLIER shall discuss with the CUSTOMER and the CUSTOMER'S ENGINEERING ORGANIZATION the binding settings and formats of the software to be used and shall comply with the settings once they are agreed by the parties. |
|  | The SUPPLIER shall prepare the following documentation in the Czech language (the CUSTOMER also accepts bilingual processing (Czech language/English language) with an officially certified translation into the Czech language): - Instructions for use (including operating and maintenance instructions for sub-machines), - Spare parts list, - HSE documentation (Risk assessment - documents for the HSE coordinator), - List of devices, - List of electrical appliances, - List of I/O signals, - Measurement list, - P&I diagrams, - CE declaration of conformity. The CUSTOMER shall be entitled to require the SUPPLIER to process other documentation in the Czech language if required by the effective LEGISLATION of the Czech Republic or the European Union. The SUPPLIER is entitled to prepare documentation beyond the above in English. The SUPPLIER shall provide all documentation (except for the AS-BUILT DOCUMENTATION) to the CUSTOMER in electronic form, namely: - 1x to check and APPROVE, - 1x in a APPROVED form after incorporation of relevant comments of the CUSTOMER. The SUPPLIER shall provide the CUSTOMER with AS-BUILT DOCUMENTATION in electronic and paper form, namely: - 1x in paper form and 1x in electronic form for checking and APPROVAL, - 1x in paper form and 1x in electronic form (on a data carrier) in an APPROVED form after incorporating the relevant comments of the CUSTOMER. The electronic form of the documentation will be processed in the following software applications and transmitted in the following formats (where not otherwise specified, the native format of the relevant software will be used): - Text documents will be submitted in MS Word 2007 or higher (*.doc,*.docx) formats, - Databases, tables, lists will be submitted in native MS Excel 2007 or higher formats (*.xls, *.xlsx), - Drawing documentation will be submitted in AutoCAD Rel. 2018 or previous formats (*.dwg, *.dxf), the drawing appearance and detailed settings will be agreed between the CUSTOMER and the SUPPLIER, - Scanned documents in *.pdf format, - Photos in *.jpg format with a resolution of at least 3000 x 2000 pixels, - Time schedules, Schedules will be submitted in MS Project 2007 format (*.mpp). They will also always be submitted in *.pdf format. A change of software or format is only permissible after approval by the CUSTOMER. The details of the execution of the INITIAL DOCUMENTATION OF THE DELIVERY and the AS-BUILT DOCUMENTATION will be described in the QUALITY ASSURANCE PLAN - Administrative Manual. |

# DELIVERY DEADLINES, TIME SCHEDULE

## DELIVERY DEADLINES

|  | The SUPPLIER is obliged to make the DELIVERY within the deadlines specified in Annex 2 to the AGREEMENT. |
| --- | --- |
|  | Failure to meet the above deadlines will be sanctioned in accordance with paragraph 22.2 of the AGREEMENT. |

## TIME SCHEDULE

|  | The SUPPLIER shall prepare and submit within 90 days of the date of commencement of the DELIVERY implementation pursuant to paragraph 6.1.1.2 of the AGREEMENT a detailed TIME SCHEDULE for the execution of the DELIVERY in accordance with Annex 2 to the AGREEMENT. The detailed TIME SCHEDULE and any updates thereto shall comply with the milestone dates set out in Annex 2 to the AGREEMENT as subsequently updated. The SUPPLIER shall prepare and submit the final part of the TIME SCHEDULE in relation to installation and commissioning no later than 4 months prior to delivery of the DELIVERY in accordance with paragraph 6.2.2.13 of the AGREEMENT. |
| --- | --- |
|  | The SUPPLIER shall update the TIME SCHEDULE once a month during the execution of the DELIVERY, provided that the milestone dates specified in Annex 2 to the AGREEMENT shall be maintained as subsequently updated. |
|  | The updated TIME SCHEDULE will be included in the MONTHLY REPORT and its implementation will be discussed at the monthly meetings. |
|  | TIME SCHEDULE shall be prepared for the period of implementation of the DELIVERY from the commencement of implementation of the DELIVERY pursuant to paragraph 6.1.1.2 of the AGREEMENT until successful completion of PERFORMANCE TESTS – Part „A“ in two levels: |
|  | The level 1 will be applied to the TIME SCHEDULE of the manufacturing of DELIVERY and arranged by operational sets and shall include the total periods of duration with marked MILESTONES. |
|  | The level 2 will include the detailed breakdown of all works and activities pm the SITE for 4 weeks’ time period (i.e., the previous, current and two upcoming weeks) and shall serve for the CUSTOMER as a base for the monitoring, controlling and measuring of the progress within the activities and for COORDINATION of the activities at SITE. This level of TIME SCHEDULE shall be submitted by the SUPPLIER regularly once a week in the course of the DELIVERY implementation and shall be discussed within the weekly coordination days. |
|  | In the event of delay in the implementation of the DELIVERY compared to the TIME SCHEDULE, the SUPPLIER is obliged to submit to the CUSTOMER a summary of the proposed remedial measures. |
|  | MILESTONES will also be marked in the TIME SCHEDULE. The MILESTONES can be changed only in compliance with the rules specified below. |
|  | The CUSTOMER, in accordance with § 100, paragraph 1 of the PPA, reserves the right to change the MILESTONES in the following cases: |
|  | For reasons of particularly adverse or unsuitable climatic conditions which, according to the contract with the EPC CONTRACTOR will demonstrably prevent the execution of the relevant part of the works and which will result in a change in the milestones specified in the contract with the EPC CONTRACTOR, which will demonstrably affect the DELIVERY. Restrictions on the progress of the works due to particularly adverse and/or unsuitable weather conditions shall be communicated by the CUSTOMER to the SUPPLIER without undue delay after this information has been communicated to the CUSTOMER by the EPC CONTRACTOR. The SUPPLIER shall be obliged to submit an updated TIME SCHEDULE at the CUSTOMER's request, reflecting the change in the dates of execution of the DELIVERY. A change in the DELIVERY execution dates shall always be possible so that it reflects the time necessary to overcome the consequences of such delay and its beginning and end shall be recorded in the EPC CONTRACTOR'S construction diary. |
|  | For reasons of the need to carry out additional works or changes to the DELIVERY, which will be carried out in accordance with Section 222 of the PPA, and which have a demonstrable impact on the implementation of the DELIVERY, always for the time necessary to carry them out. |
|  | Due to objective obstacles to the performance of the AGREEMENT arising as a result of a decision or intervention of state administration or self-government bodies in the process leading to the issuance of a decision or statement pursuant to Act No. 183/2006 Coll., on Spatial Planning and Building Code (Building Act), as amended, and other legal regulations, and exceeding the statutory deadlines for the issuance of such decisions, for no longer than the duration of these obstacles or for the time necessary to meet the requirements arising therefrom. |
|  | The MILESTONE may be changed only by written amendment to the AGREEMENT, unless the change of the MILESTONE is reserved in the AGREEMENT. If the change is reserved in the AGREEMENT, no amendment to the AGREEMENT is required and any impact of such change shall be addressed by the parties in the change request (document). |
|  | Unless the parties agree on a different time limit, the SUPPLIER shall mobilize its personnel to the SITE as soon as possible, but no later than (i) ninety calendar days after receiving the CUSTOMER's call for the first mobilization and (ii) sixty calendar days after receiving the CUSTOMER’s call for each other mobilization. The CUSTOMER agrees to use reasonable efforts to enable the SUPPLIER to provide the appropriate comprehensive CHIEF ASSEMBLY at the SITE on a continuous basis. In the event of any demobilization of SUPPLIER's personnel from the SITE, or any suspension required by the CUSTOMER or attributable to the CUSTOMER that is not due to the fault of the SUPPLIER, the mobilization period set forth above shall apply to any other mobilization, unless otherwise agreed by the parties. If the CHIEF ASSEMBLY is delayed or interrupted by circumstances for which the SUPPLIER is not responsible, the SUPPLIER shall be entitled to reasonable compensation. |

# PRICE

## PRICE

|  | The PRICE for DELIVERY in compliance with the AGREEMENT is set forth in Annex 4 of the AGREEMENT. |
| --- | --- |
|  | The PRICE is agreed upon by the CUSTOMER and the SUPPLIER and is valid for the entire term of the AGREEMENT, unless otherwise specified in the AGREEMENT. |
|  | The PRICE shall include all costs, risks, reserves and profits of the SUPPLIER with respect to the performance of the DELIVERY and all taxes, fees, duties, royalties and RIGHTS OF USE if any may arise under the AGREEMENT, and all financial costs associated with the performance of the DELIVERY, until the fulfilment of all SUPPLIER's obligations under this AGREEMENT. |
|  | The PRICE does not include value added tax (hereinafter referred to as "VAT"), which will be determined in the amount and manner according to the Czech legislation in force on the date of the taxable performance. In the event that the subject of the SUPPLIER's performance under the AGREEMENT will be construction and assembly works (regardless of whether it is services or delivery of goods with assembly), which fall under the CZ-CPA 41 to 43 code subject to the regime of reverse charge, VAT will not be charged to the price for such performance in accordance with Section 92a of Act No. 235/2004 Coll., on Value Added Tax, as amended. The SUPPLIER shall be responsible for determining whether the supply falls under CZ-CPA 41 to 43. |
|  | For the purposes of calculating the discounts on the PRICE, the contractual penalties and the amount of payments under paragraph 10.2 of the AGREEMENT, the PRICE shall be determined as follows: - PRICE = PRICE in CZK/USD/SEK/JPY x exchange rate below + price in EUR. The exchange rate for conversion of CZK/USD/SEK/JPY to EUR for the purposes of this clause of the AGREEMENT shall be determined as the average exchange rate of the Czech National Bank for the completed calendar month preceding the month in which the PRICE discount, contractual penalty or payment pursuant to paragraph 10.2 of the AGREEMENT is applied. |
|  | The CUSTOMER reserves the right not to order the following parts of the DELIVERY: - spare parts for the WARRANTY PERIOD; - reserved performance (reserved technical solution) as per Annex 7 to the AGREEMENT. When this right is exercised by the CUSTOMER, the PRICE of the DELIVERY under the AGREEMENT shall not include the price for the unsubscribed parts of the DELIVERY. The CUSTOMER's reservation of the possibility not to order the said part of the DELIVERY shall be stated in the DETAILED TERMS OF DELIVERY pursuant to paragraph 6.1.1.2 of the AGREEMENT. |

## PRICE CHANGES

|  | The PRICE can only be changed if the following conditions are met: |
| --- | --- |
|  | Changes to the DELIVERY pursuant to Article 11 of the AGREEMENT or |
|  | Application of the PRICE modification rules pursuant to paragraph 9.2.3 of the AGREEMENT. |
|  | Negotiation of a change in PRICE pursuant to Article 11 of the AGREEMENT shall be conducted in accordance with the procedures set forth in Article 11 of the AGREEMENT. All proposals for change in PRICE shall include detailed technical specifications, bills of quantities and unit prices. The highest market prices customary in the GAS TURBINE manufacturer's state will be used . If the market price customary in the GAS TURBINE manufacturer's state cannot be determined for a particular GOODS and/or CHIEF ASSEMBLY, such price will always be negotiated by and between the parties to the AGREEMENT and price agreed by the parties shall be applicable. |
|  | In applying the PRICE modification rules under this paragraph of the AGREEMENT, the PRICE shall be modified based on the input price expressed in the modification formula in effect on the date of the delivery of the DETAILED TERMS OF DELIVERY to the SUPPLIER or, in case of the CUSTOMER’s failure to deliver the DETAILED TERMS OF DELIVERY to the SUPPLIER, on the date following the date on which the remedial period pursuant to paragraph 6.1.1.2 of the AGREEMENT has expired. The SUPPLIER shall send to the CUSTOMER within 15 days from the date of the delivery of the DETAILED TERMS OF DELIVERY to the SUPPLIER or, in case of the CUSTOMER’s failure to deliver the DETAILED TERMS OF DELIVERY to the SUPPLIER, from the date following the date on which the remedial period pursuant to paragraph 6.1.1.2 of the AGREEMENT has expired, a notice stating all relevant facts and figures and calculating the increase in PRICE. The CUSTOMER shall be obliged to accept the price modification. The prerequisite for changing the PRICE is a change in the prices of the following inputs expressed in the modification formula: OPTION 1: Price of part of delivery in JPY NPJPY=(PJPY*(0,25*ILIn/ILIc + 0,75* CPIn/CPIc) Price of part of delivery in CZK NPCZK=PCZK*(0,25*ILIn/ILIc + 0,75* CPIn/CPIc) PRICE for DELIVERY of the GAS TURBINE n = NPJPY + NPCZK Where NPJPY; =; New PRICE for DELIVERY (JPY) recalculated for GAS TURBINE n (n = 1-7,) at the time of escalation.. PJPY; =; PRICE for DELIVERY (JPY) as per the AGREEMENT. PCZK; =; PRICE for DELIVERY (CZK) as per the AGREEMENT. NPCZK; =; New PRICE for DELIVERY (CZK) recalculated for GAS TURBINE n (n = 1-7,) at the time of escalation.. ILIn; =; Index of Labor Input (Industries Covered), (2020=100) of the calendar month preceding the calendar month of delivery of the DETAILED TERMS OF DELIVERY Reference: 0607CI2.xlsx (live.com) (Indexes of Business Conditions : Economic and Social Research Institute - Cabinet Office Home Page (cao.go.jp) – Individual Indicator – Coincident Index. ILIc; =; Index of Labor Input (Industries Covered), (2020=100) of the calendar month of signing the AGREEMENT. CPIn; =; Consumer Price Index 2020 - ALL JAPAN and All Items (2020=100) – index for the region/field of the calendar month preceding the calendar month of delivery of the DETAILED TERMS OF DELIVERY Reference: Consumer Price Index 2020-Base Consumer Price Index1 2020-Base Consumer Price Index ¦ View Statistical Table/Graph ¦ Portal Site of Official Statistics of Japan (e-stat.go.jp). CPIct; =; Consumer Price Index 2020 - ALL JAPAN and All Items, (2020=100) of the calendar month of signing the AGREEMENT. OPTION 2: Step 1 - Price indexation / change for establishment of price of parts of SUPPLY in respektive currencies EUR Delivery Price PnEUR= 0,5* PcEUR*INDn/INDc + 0,5* PcEUR SEK Delivery Price PnSEK= 0,5* PcSEK*INDn/INDc + 0,5* PcSEK CZK Delivery Price PnCZK= 0,5* PcCZK *INDn/INDc + 0,5* PcCZK Step 2 – Total DELIVERY PRICE for GAS TURBINE n = PnEUR + PnSEK +PnCZK Where PcEUR Total DELIVERY PRICE (EUR) of the CONTRACT PcSEK Total DELIVERY PRICE (SEK) of the CONTRACT PcCZK Total DELIVERY PRICE (CZK) of the CONTRACT PnCZK Total DELIVERY PRICE (CZK) recalculated for GAS TURBINE n (n= 1-7) PnSEK Total DELIVERY PRICE (SEK) recalculated for GAS TURBINE n (n= 1-7) PnEUR Total DELIVERY PRICE (EUR) recalculated for GAS TURBINE n (n= 1-7) INDn = Index PPI SPIN 2015 product group 25, (2020=100) – arithmetic average of index valu efor 6 months preceding calendar month of DETAIL CONDITIONS OF SUPPLY for GAS TURBINE n. Link: https://www.statistikdatabasen.scb.se/pxweb/en/ssd/START__PR__PR0301__PR0301G/PPI2020M/ INDc Index PPI SPIN 2015 product group 25, (2020=100) for the calendar month of CONTRACT signing OPTION 3: Step 1 - Price indexation / change for establishment of price of parts od DELIVERY in individual currencies EUR Delivery Price PnEUR= 0,5* PcEUR*INDn/INDc + 0,5* PcEUR *(1+K*Tn) SEK Delivery Price PnSEK= 0,5* PcSEK*INDn/INDc + 0,5* PcSEK *(1+K*Tn) CZK Delivery Price PnCZK= 0,5* PcCZK*INDn/INDc + 0,5* PcCZK *(1+K*Tn) Step 2 - DELIVERY PRICE for GAS TURBINE n = PnEUR + PnSEK +PnCZK Where: PcEUR = PRICE of the part of DELIVERY in (EUR) in the CONTRACT PcEUR = PRICE of the part of DELIVERY in (SEK) in the CONTRACT PcCZK = PRICE of the part of DELIVERY in (CZK) in the CONTRACT PnEUR = PRICE of the part of DELIVERY in (EUR) recalculated for GAS TURBINE n (n= 1-7) PnSEK = PRICE of the part of DELIVERY in (SEK) recalculated for GAS TURBINE n (n= 1-7) PnCZK = PRICE of the part of DELIVERY in (CZK) recalculated for GAS TURBINE n (n= 1-7) INDn = Index PPI SPIN 2015 product group 25, (2020=100) – arithmetic average of index valu efor 6 months preceding calendar month of DETAIL CONDITIONS OF SUPPLY for GAS TURBINE n. Link: https://www.statistikdatabasen.scb.se/pxweb/en/ssd/START__PR__PR0301__PR0301G/PPI2020M/ INDc Index PPI SPIN 2015 product group 25, (2020=100) for the calendar month of CONTRACT signing Tn Time in full months from date of CONTRACT signing till the date of DETAIL CONDITIONS OF SUPPLY for GAS TURBINE n. K constant – [its amount is determined by the PARTICIPANT in the interval <0.00375, 0.0075>] |

## discount on PRICE for delivery

|  | Discount on the PRICE for DELIVERY will be provided in the event that the DELIVERY: - fails to meet any of the GUARANTEED PARAMETERS of the PERFORMANCE TESTS – Part “A” in a way that the DELIVERY meets the ACCEPTABLE VALUES of the respective GUARANTEED PARAMETER as set forth in Annex 5 of the AGREEMENT and at the same time the SUPPLIER fails to seek corrective action and to repeat the PERFORMANCE TESTS - Part "A" under the terms and conditions set forth below in the AGREEMENT or fails to successfully repeat the PERFORMANCE TESTS - Part "A" within 4 months of the first performance of the PERFORMANCE TESTS - Part "A"; or - fails to meet any of the GUARANTEED PARAMETERS of the PERFORMANCE TESTS – Part “A” in a way that the DELIVERY does not meet the ACCEPTABLE VALUES of the respective GUARANTEED PARAMETER as set forth in Annex 5 of the AGREEMENT, however the CUSTOMER TAKEN OVER such a DELIVERY and SUPPLIER decides not to seek corrective actions. Discount will be provided pursuant to paragraphs 9.3.2.1 to 9.3.2.10 of the AGREEMENT. |
| --- | --- |
|  | In the event that the SUPPLIER delivers a DELIVERY that does not, even after SUPPLIER’s remedial attempts as per paragraph 21.5.6 of the AGREEMENT, meet the GUARANTEED PARAMETERS specified in paragraphs 9.3.2.3, 9.3.2.6, 9.3.2.7 and 9.3.2.8 of the AGREEMENT within the PERFORMANCE TESTS – Part "B" specified in Annex 5 to the AGREEMENT, whether within the ACCEPTABLE VALUES or outside the ACCEPTABLE VALUES, the CUSTOMER shall within the FINAL ACCEPTANCE OF THE DELIVERY approve, that the DELIVERY will be taken over by the CUSTOMER and a CERTIFICATE OF FINAL ACCEPTANCE will be issued and the SUPPLIER shall pay the CUSTOMER a discount on the PRICE for failure to comply with the GUARANTEED PARAMETERS. Discounts on the PRIZE will be provided according to the rates specified in paragraphs 9.3.2.3, 9.3.2.6, 9.3.2.7 and 9.3.2.8 of the AGREEMENT For the values of the GUARANTEED PARAMETERS determined by the PERFORMANCE TEST – Part "B", to which a discount from the PRICE of the relevant DELIVERY was applied after the PERFORMANCE TEST – Part "A", the values determined within the GUARANTEE TEST – Part "A" will be inserted into the formula for calculating the discount on the PRICE for failure to meet the GUARANTEED PARAMETERS in the PERFORMANCE TEST – Part "B" and these values will be reduced by degradation according to the degradation curve specified in Annex 5 to the AGREEMENT. For the values of the GUARANTEED PARAMETERS determined by the PERFORMANCE TEST – Part "B", on which the discount from the PRICE of the relevant DELIVERY was not applied after the PERFORMANCE TEST – Part "A", the values specified/guaranteed in Annex 5 to the AGREEMENT will be inserted into the formula for calculating the discount on the PRICE for failure to meet the GUARANTEED PARAMETERS in the PERFORMANCE TEST – Part "B" and these values will be reduced by degradation according to the degradation curve specified in Annex 5 to the AGREEMENT. In the event that within the PERFORMANCE TEST – Part “B” the DELIVERY demonstrates an improvement in the GUARANTEED PARAMETER to which the discount for the PERFORMANCE TEST – Part „A“ has been applied compared to the value determined in the PERFORMANCE TEST – Part "A" reduced by degradation according to the degradation curve specified in Annex 5 to the AGREEMENT, the CUSTOMER shall in such a case repay the SUPPLIER a part of the discount corresponding to such improvement of the GUARANTEED PARAMETER compared to the value determined in the PERFORMANCE TEST – Part "A" reduced by degradation according to degradation curves specified in Annex 5 to the AGREEMENT. |
|  | The following rules shall apply to the values of the parameters used to determine the discount for failure to achieve the values of the GUARANTEED PARAMETERS pursuant to paragraphs 9.3.2.2 to 9.3.2.8 to of the AGREEMENT: - The assessment of the parameters achieved during the performance of the PERFORMANCE TEST shall always be carried out in relation to the requirements set out for the GUARANTEED PARAMETERS of the DELIVERY in accordance with Annex 5 to the AGREEMENT. - For the purpose of measurements to prove the parameters used to determine the discount, the accuracy according to Annex 5 to the AGREEMENT is considered. |
|  | The discount for non-compliance with the GUARANTEED PARAMETER Own power consumption of the gas turbine VI shall amount to: Discount in the PRICE (EUR) = (SVl1 - Vl1) * D + (SVl2 - Vl2) * D [EUR] Where the following applies: Vl1; Own power consumption of the gas turbine in operational state 1 guaranteed by the SUPPLIER [kWh/h]. SVl1; Own power consumption of the gas turbine for operational state 1 as determined during the PERFORMANCE TESTS [kWh/h]. Vl2; Own power consumption of the gas turbine in operational state 2 guaranteed by the SUPPLIER [kWh/h]. SVl2; Own power consumption of the gas turbine for operational state 2 as determined during the PERFORMANCE TESTS [kWh/h]. D; is equal to 800 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 2000 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - If the result is more than "0", the discount will be provided at the calculated amount, or - If the result is less than or equal to "0", no discount will be provided. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning Pgm : Discount (EUR) = (Pgm - SP )gm * D [EUR] Where: Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [kWe]. SPgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning as determined during the PERFORMANCE TESTS [kWe]. D; is equal to 800 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 2000 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the discount will be provided in the calculated amount, or - If the result is less than or equal to "0", the discount shall not be provided. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Minimum achievable output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet Pmin : Discount (EUR) = (SPmin - Pmin ) * D [EUR] Where: Pmin; Minimum Achievable Performance while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet guaranteed by the SUPPLIER [kWe]. SPmin; The minimum achievable power output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet as determined during the PERFORMANCE TEST [kWe]. D; is equal to 800 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 2000 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the discount will be provided in the calculated amount, or - If the result is less than or equal to "0", the discount will not be provided. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Maximum achievable electrical output of the gas turbine at the generator terminals within 10 minutes of the start-up instruction P10 Discount (EUR) = (P10 - SP10 ) * D [EUR] Where: P10; Electric output of the gas turbine at the generator terminals, achievable within 10 minutes of the start-up instruction guaranteed by the SUPPLIER [kWe]. SP10; The electrical output of the gas turbine at the generator terminals achievable within 10 minutes of the start-up instruction as determined during the PERFORMANCE TEST [kWe]. D; is equal to 200 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 310 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the discount will be provided in the calculated amount, or - If the result is less than or equal to "0”, the discount shall not be provided. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Gross Power Generation Efficiency in operational state 1 Egm1 Discount (EUR) = 360000 SEgm1- 360000 Egm1 * D1 * Pgm Amount of discount for non-compliance with the GUARANTEED PARAMETER Gross Power Generation Efficiency in the operational state 2 X42 Discount (EUR) = 360000SX42 - 360000 X42* D2 * Pmin Where: Egm1; Gross Power Generation Efficiency in operational state 1 guaranteed by the SUPPLIER [%]. SE gm1; Gross Power Generation Efficiency in operational state 1 as determined during the PERFORMANCE TEST [%]. X4 2; Gross Power Generation Efficiency in operational state 2 guaranteed by the SUPPLIER [%]. SX4 2; Gross Power Generation Efficiency in operational state 2 as determined by the PERFORMANCE TEST [%]. Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [MWe]. Pmin; Minimum achievable output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet [kWe]. D1; is equal to 80 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 200 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. D2; is equal to 140 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 357,50 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the discount values: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the discount will be provided in the calculated amount, or - In the event that the result is less than "0", the bonus will be credited to the SUPPLIER, but only in case of non-compliance with the GUARANTEED PARAMETER "Flue gas temperature at the gas turbine outlet" in operational state 1. The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER “Flue gas temperature at the gas turbine outlet” in operational state 1. The bonus will be credited to the SUPPLIER if the flue gas temperature is > 540°C. - In the event that the result is less than "0", the bonus will be credited to the SUPPLIER, but only in case of non-compliance with the GUARANTEED PARAMETER " Flue gas temperature at the gas turbine outlet " in operational state 2. The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER “Flue gas temperature at the gas turbine outlet” in operational state 2. The bonus will be credited to the SUPPLIER if the flue gas temperature is > 540°C. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Flue gas temperature at the gas turbine outlet in the operational state 1 T1 Discount (EUR) = (T1 - ST1 ) * 800 * (Pgm / Egm1/100 - Pgm) [EUR] Where: Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [MWe]. Egm1; Gross Power Generation Efficiency in operational state 1 guaranteed by the SUPPLIER [%]. T1; Flue gas temperature at the gas turbine outlet in operational state 1 guaranteed by the SUPPLIER [°C]. ST1; Flue gas temperature at the gas turbine outlet in operational state 1 as determined during the PERFORMANCE TEST [°C]. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - If the result is more than "0", the discount will be granted at the calculated amount, or - In the event that the result is less than "0", a bonus will be credited to the SUPPLIER only in the event of non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency" in the operational state 1. The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency” in operational state 1. |
|  | Discount for non-compliance with the GUARANTEED PARAMETER Flue gas temperature at the gas turbine outlet in operating condition 2 T2 Discount (EUR) = (T2 - ST2) * 240 * (Pmin / (X42/100) – Pmin) [EUR] Where: Pmin; Minimum Achievable Performance while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet guaranteed by the SUPPLIER [MWe]. X42; Gross Power Generation Efficiency in operational state 2 guaranteed by the SUPPLIER [%]. T2; Flue gas temperature at the gas turbine outlet in operational state 2 guaranteed by the SUPPLIER [°C]. ST2; Flue gas temperature at the gas turbine outlet in operational state 2 as determined by the PERFORMANCE TEST [°C]. The following applies to the value of the discount: - The result will be rounded to whole numbers, and - If the result is more than "0", the discount will be granted at the calculated amount, or - In the event that the result is less than "0", a bonus will be credited to the SUPPLIER only in the event of non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency" in the operational state 2. - The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency” in operational state 2. |
|  | The maximum amount of the discount as per paragraph 9.3.2 of the AGREEMENT equals to 20 % of the PRICE. |
|  | In the event of the SUPPLIER’s breach of obligations that are subject to the provision of discount by the SUPPLIER, the CUSTOMER shall not claim any damages (whether liquidated or not) or contractual penalties for such a breach. In case the liquidated damages or contractual penalty has already been claimed by the CUSTOMER, the CUSTOMER shall reduce the discount as per paragraph 9.3.2 of the AGREEMENT by the amount corresponding to the claimed liquidated damages or contractual penalty (as applicable). |

# PAYMENT TERMS

## GENERAL TERMS AND CONDITIONS

|  | Payments for the DELIVERY under the AGREEMENT shall be made on the basis of tax documents (invoices) issued in accordance with the laws of the Czech Republic and the AGREEMENT. |
| --- | --- |
|  | Invoices are due 30 days from the date of delivery of the invoice to CUSTOMER 1, CUSTOMER 2 or CUSTOMER 3. |
|  | The invoice - tax document must contain all the requirements of a tax document according to Act No. 235/2004 Coll., on value added tax, as amended, in particular the following information: - The business name, registered office, registration number, VAT number, information on entry into the commercial register of the CUSTOMER (for DELIVERY as per the CALL FOR DELIVERY) and the SUPPLIER, - No. of the AGREEMENT attributed by the SUPPLIER - Designation of DELIVERY - "Supply of gas turbines from 40 to 60MWe", - Tax document registration number, - Date of invoice, date of taxable supply or date of receipt of payment, - Due date of the invoiced amount, - Name of the bank and bank account number of the SUPPLIER, - Scope and object of the taxable supply, - Value added tax rate, - The tax base or advance payment amount, VAT (by production code classification) and the total amount, - Signature of an authorized representative of the SUPPLIER, - The number of the CUSTOMER's application for subsidy (only if notified by the CUSTOMER to the SUPPLIER). |
|  | A copy of the TAKEOVER protocol with respect to the TAKEOVER of the respective MILESTONE pursuant to paragraph 21.3 of the AGREEMENT confirming that all conditions for payment of the invoice have been met shall be an integral part of each invoice, except for advance payment invoices. |
|  | Invoices that do not contain the above-mentioned data and information or contain incorrect data will be returned by the CUSTOMER to the SUPPLIER no later than on their due date. The CUSTOMER shall also be entitled to return the invoice if the invoice bears a different account number from that specified above in this AGREEMENT or as subsequently amended. The CUSTOMER shall not be entitled to return the invoice only if the invoice indicates a different bank account of the SUPPLIER published by the tax administrator in the VAT register and the invoice is accompanied by a declaration of the SUPPLIER's responsible person that he/she requests payment to the account indicated on the invoice. The SUPPLIER shall be obliged to issue a new invoice in such a case. Upon delivery of the new or corrected invoice to the CUSTOMER, the new due date shall begin. |
|  | Unless stated in the AGREEMENT otherwise, no party is entitled to set off its receivables against the other party receivables without the prior written consent of the other party. |
|  | The CUSTOMER reserves the right, in accordance with Section 106 of the PPA, to transfer to the SUB-SUPPLIER the part of the PRICE at the request of the SUB-SUPPLIER listed in Annex 6A to the AGREEMENT, provided that on the date of submission of the SUB-SUPPLIER'S request the SUPPLIER has been declared bankrupt, or that the SUPPLIER is in default of payment to the SUB-SUPPLIER for more than 30 days. The direct payment to the SUB-SUPPLIER shall be subject to a written request from the SUB-SUPPLIER, in which the SUB-SUPPLIER shall give evidence with respect to the following: - the title on the basis of which the direct payment is claimed (i.e. bankruptcy of the SUPPLIER or default of the SUPPLIER in payment to the SUB-SUPPLIER), - the legal title under which the SUB-SUPPLIER participates in the execution of the DELIVERY , - documents proving the entitlement to payment of the relevant payment from the SUPPLIER (in particular, proof of completion of the relevant performance, invoice), - the account number to which the direct payment is to be made. The CUSTOMER shall, upon receipt of the SUB-SUPPLIER's request, request the SUPPLIER's opinion. In the event that the SUPPLIER proves that the SUB-SUPPLIER is not entitled to a direct payment under this clause, the CUSTOMER shall not make such payment. The CUSTOMER shall be entitled to set-off the payments provided to the SUB-SUPPLIER in accordance with this paragraph of the AGREEMENT against its due obligation to pay the SUPPLIER relevant part of the PRICE. If the CUSTOMER does not exercise the right of set-off or if such set-off is no longer possible, the CUSTOMER shall be entitled to satisfy its claim for payment of the relevant amount by drawing from the PERFORMANCE BOND. |

## PAYMENT SCHEDULE

|  | Payments for SUPPLIES under the AGREEMENT will be made as follows: |
| --- | --- |
|  | Partial invoicing of the PRICE based on the fulfilment of the MILESTONES according to the payment schedule attached as Annex 3 to the AGREEMENT. Submission of the ADVANCE PAYMENT GUARANTEE pursuant to paragraph 27.3 of the AGREEMENT shall be a prerequisite for the payment of the first advance payment after the signing of the AGREEMENT and of the advance payment after fulfilment of the MILESTONE No. 2. Submission of the PARENT COMPANY GUARANTEE pursuant to paragraph 27.4 of the AGREEMENT shall be a prerequisite for the payment of any other advance payment that is not secured by the ADVANCE PAYMENT GUARANTEE |
|  | Advance payment after signing of the AGREEMENT in amount corresponding to 5 % of the PRICE for DELIVERY of each GAS TURBINE as per Annex 4 Advance payment invoice for each GAS TURBINE will be issued by the SUPPLIER after signing of the AGREEMENT and shall be settled in the first partial invoice for each GAS TURBINE as proportional subtraction from the invoiced amount in relation to the PRICE pursuant to Article 9. Advance payment after achievement of MILESTONE No. 2 amounting to the difference between 15 % of the PRICE of DELIVERY of each GAS TURBINE as per Annex 4 and the advance payment paid after signing of the AGREEMENT Advance payment invoice for each GAS TURBINE will be issued by the SUPPLIER after achievement of the MILESTONE No. 2 and shall be settled in the first partial invoice for each GAS TURBINE as proportional subtraction from the invoiced amount in relation to the PRICE pursuant to Article 9. Advance payment amounting to [TO BE ADDED BY THE PARTICIPANT] % of the PRICE of DELIVERY of each GAS TURBINE as per Annex 4 Advance payment invoice for each GAS TURBINE will be issued by the SUPPLIER no sooner than [TO BE ADDED BY THE PARTICIPANT] days after achievement of the MILESTONE No. 2 and shall be settled in the first partial invoice for each GAS TURBINE as proportional subtraction from the invoiced amount in relation to the PRICE pursuant to Article 9. INSTRUCTION FOR THE PARTICIPANT according to the PARTICIPANT’S needs, apart from the advance payment after signing the AGREEMENT and advance payment after fulfilment of the MILESTONE No. 2, the PARTICIPANT may state here more advance payments; all advance payments shall in their entirety not exceed 60 % of the PRICE for DELIVERY of each GAS TURBINE according to Annex 4 to the AGREEMENT. The PARTICIPANT is entitled not to request any advance payment. |
|  | A partial invoice amounting to 95 % of the PRICE for DELIVERY of each GAS TURBINE shall be issued after achievement of MILESTONE No. 3. |
|  | The partial invoice amounting to 5 % of the PRICE for DELIVERY of each GAS TURBINE shall be issued after achievement of MILESTONE No. 6. Within the said partial invoice all discounts pursuant to paragraph 9.3.2, liquidated damages/contractual penalties pursuant to Article 22 of the AGREEMENT and damages pursuant to Article 24 of the AGREEMENT shall be settled as well. The invoice for the last partial performance (final payment) shall also contain a breakdown of the PRICE for the purpose of incorporating the individual parts of the DELIVERY into the CUSTOMER's DHM, in accordance with Act No. 563/1991 Coll., on Accounting, as amended, including a separate breakdown of the price for training. |
|  | Any potential changes to the PRICE will be invoiced according to the terms set out in the relevant amendment to the AGREEMENT. |
|  | The division of the amounts of the partial invoices under paragraph 10.2.1 of the AGREEMENT between EUR and CZK/USD/SEK/JPY shall be made according to the division specified in the payment schedule attached as Annex 3 to the AGREEMENT. |
|  | In the event that, with regard to the course of execution of the DELIVERY, a situation arises that some or all of the MILESTONES for which individual partial invoices are intended according to paragraph 10.2.1 of the AGREEMENT are identical in terms, the SUPPLIER shall nevertheless issue individual partial invoices separately as if these MILESTONES were separate. |

# CHANGEs to the delivery

|  | SUPPLIER shall use its best efforts to agree to a corresponding change in the DELIVERY in which case it shall be entitled to a corresponding reasonable adjustment in the PRICE and TIME SCHEDULE, including MILESTONES, and technical parameters of DELIVERY, if the change in the DELIVERY results from latent obstacles, a change in the starting basis as specified below, the discovery of an unsuitable nature of things and sources that could not have been foreseen, or new requirements of the CUSTOMER as set forth in this Article 11 of the AGREEMENT below. |
| --- | --- |
|  | For the purposes of the AGREEMENT, a change to the DELIVERY shall be deemed to be a change to the scope or other contractual requirements relating to the DELIVERY to be performed under the AGREEMENT, and which does not constitute a material change to the AGREEMENT pursuant to Section 222 of the PPA. |
|  | The following are considered to be a change in the starting basis: - changes resulting from the opinions of the state administration authorities of the Czech Republic, - changes in regulations that come into force after the date of signing of the AGREEMENT, - changes to the DELIVERY requested by the CUSTOMER. |
|  | The following is not considered a change to the DELIVERY: - minor modifications to documentation for the implementation of the DELIVERY , - modifications that the SUPPLIER must make to ensure the operability, functionality, serviceability and safety of the DELIVERY under the AGREEMENT. |
|  | The SUPPLIER shall not and shall not be obliged to commence the implementation of changes to the DELIVERY before the change has been agreed by both parties and a written amendment to the AGREEMENT has been executed. In the event that it does so, it shall not be entitled to any increase in the PRICE and/or amendment to Annex 2 to the AGREEMENT. |
|  | Changes to the DELIVERY shall be made by way of an amendment to the AGREEMENT as follows: The SUPPLIER shall prepare documents for the preparation of a draft amendment to the AGREEMENT. The documents shall include: - a detailed description of the subject of the change, including relevant documentation, - justification for the change, - impact on the PRICE and TIME SCHEDULE, - technical parameters of DELIVERY - in the event of a change in the PRICE, a price calculation and a proposal to amend Annex 3 to the AGREEMENT. On the basis of the submitted documents, the CUSTOMER shall prepare a draft amendment to the AGREEMENT. |

# TAXES, DUTIES AND CHARGES

|  | The SUPPLIER declares that it is familiar with the tax, customs and administrative regulations of the Czech Republic and that it has included in the PRICE and will pay all taxes, duties and fees that are or may be required by the relevant state authorities in connection with the implementation of the DELIVERY. |
| --- | --- |
|  | The SUPPLIER declares that its bank account specified in this AGREEMENT is an account published by the tax administrator in the VAT register in accordance with Act No. 235/2004 Coll., on value added tax, as amended. |
|  | The SUPPLIER declares that as of the date of signing of this AGREEMENT, no decision on unreliable payer within the meaning of § 206a of Act No. 235/2004 Coll., on Value Added Tax, as amended, has been issued against him by the tax administrator, that no such proceedings have been initiated or conducted against him and that no conditions for initiating proceedings on unreliability of the payer with the relevant tax administrator are present. |
|  | The SUPPLIER undertakes that if the facts referred to in paragraphs 12.2 and 12.3 of the AGREEMENT cease to apply, it shall immediately, i.e., within five days from the date on which the facts occurred, notify the CUSTOMER of such fact and conclude an amendment to this AGREEMENT with the CUSTOMER. The content of such amendment shall be the setting of the procedures foreseen by Section 109a of Act No. 235/2004 Coll., on value added tax, as amended, or the negotiation of the CUSTOMER's right to withhold the amount corresponding to the VAT until the SUPPLIER fulfils its tax obligation. |
|  | The SUPPLIER agrees that if the CUSTOMER discovers that the declarations referred to in paragraphs 12.2 and 12.3 of the AGREEMENT are not valid, the CUSTOMER shall be entitled to withhold the amount corresponding to the VAT until the SUPPLIER has fulfilled its tax obligation, or the CUSTOMER shall pay the value added tax indicated on the issued tax documents directly to the account of the competent tax office of the SUPPLIER and the SUPPLIER shall be reimbursed the tax base. |
|  | In the event that the SUPPLIER fails to pay VAT or any other taxes, duties and charges which it is obliged to pay under the applicable REGULATIONS, and which are subsequently claimed by the governmental authorities against the CUSTOMER and the CUSTOMER pays them on behalf of the SUPPLIER, the CUSTOMER shall be entitled to claim payment of these payments and any other costs and damages against the SUPPLIER. |
|  | In the event that the SUPPLIER fails to reimburse the CUSTOMER for such payments, costs and damages within 30 days of submitting a request to and proving that the CUSTOMER has paid them on behalf of the SUPPLIER, the CUSTOMER may set off the amount due against any claim of the SUPPLIER or seek payment from the PERFORMANCE BOND |
|  | The SUPPLIER is obliged to comply with all tax, customs and administrative regulations of the Czech Republic and to act in such a way that their violation does not result in the liability of the CUSTOMER or any other obligation to secure or direct payment of taxes, fees or other mandatory payments to be paid by the SUPPLIER. |

# spare PARTS

|  | The SUPPLIER shall provide the CUSTOMER with an updated list of spare parts for the WARRANTY PERIOD no later than before the start of the TESTING OPERATION. This list shall contain at least the following information: technical specification of spare parts including catalogue number, number of pieces, unit price and total price, delivery date (deadlines or leading times). The price of spare parts for the WARRANTY PERIOD is also included in the price of the DELIVERY. Therefore, in the event that the list submitted by the SUPPLIER does not correspond to the list of spare parts for the WARRANTY PERIOD specified in Annex 8 to the AGREEMENT, or if the value of the proposed spare parts is lower than the value specified in Annex 8 to the AGREEMENT, the CUSTOMER shall be entitled to demand from the SUPPLIER an increase in the number of spare parts so that their value corresponds to the price specified in Annex 8 to the AGREEMENT or an adequate discount from the PRICE. SUPPLIER shall deliver the spare parts to CUSTOMER at its expense prior to the issuance of the PAC. If during the WARRANTY PERIOD the SUPPLIER uses spare parts from the CUSTOMER's inventory to eliminate DEFECTS, the SUPPLIER shall be obliged to replenish the used spare parts at its own expense within the time specified by the CUSTOMER. |
| --- | --- |
|  | If the CUSTOMER exercises the right not to order the spare parts for the WARRANTY PERIOD pursuant to paragraph 9.1.6 of the AGREEMENT, the SUPPLIER shall only provide the CUSTOMER with an updated list of spare parts for the WARRANTY PERIOD no later than before the commencement of the TESTING OPERATION, but such spare parts shall not be delivered by the SUPPLIER. |
|  | The SUPPLIER is obliged to provide assistance in securing the supply of spare parts for the planned lifetime of the DELIVERY according to paragraph 7.3.6 of the AGREEMENT and in the event that the production of some spare parts is discontinued during this period, it shall then provide the CUSTOMER with assistance in finding their replacement. |

# ORGANISATION OF WORKS

|  | All negotiations and contacts between the CUSTOMER and the SUPPLIER throughout the term of the AGREEMENT shall be conducted in the Czech language, except for normal daily communication, which shall be in English, unless otherwise agreed during the execution of the DELIVERY. |
| --- | --- |
|  | During the execution of the works on the SITE, the SUPPLIER shall not restrict the operability and operation of the CUSTOMER's heating plant, unless otherwise APPROVED by the CUSTOMER. |

## PROJECT MANAGERS

|  | The SUPPLIER shall designate a project manager who shall be responsible for the execution of the DELIVERY as per the AGREEMENT: - [TO BE ADDED BY PARTICIPANT] |
| --- | --- |
|  | The CUSTOMER designates the project manager: - [TO BE ADDED] |
|  | A detailed description of the rights, duties and responsibilities of the SUPPLIER's project manager shall be set forth by the SUPPLIER in the QUALITY ASSURANCE PLAN, Administrative Manual section. |
|  | A detailed description of the rights, duties and responsibilities of the CUSTOMER's project manager shall be determined by the CUSTOMER within 30 days after signing the AGREEMENT. |
|  | If a senior manager listed in a key position in the QUALITY ASSURANCE PLAN or a project manager listed by name above in the AGREEMENT becomes ineligible or unavailable to perform the relevant activity, the the relevant party shall replace him or her without delay and notify the the other Party. No amendment to the AGREEMENT shall be required to change the personnel in these positions. The CUSTOMER shall also have the right to request, for serious reasons (in particular repeated breaches of obligations), the replacement of the manager named in the QUALITY ASSURANCE PLAN or the project manager named above in the AGREEMENT |

## MEETINGS

|  | In the course of the SUPPLIER's execution of the DELIVERY, the SUPPLIER shall be obliged to participate in the following meetings: |
| --- | --- |
|  | Regular operational meetings according to the actual needs and progress of work during the execution of the DELIVERY. |
|  | Weekly briefings during the CHIEF ASSEMBLY, during the implementation of the DELIVERY and TESTING OPERATION. The following items will be the subject of the meeting: - evaluation of the progress of the DELIVERY, - occupational safety and hygiene (HSE), environmental protection, fire protection, - inspection and discussion of entries in construction and assembly logs, - work schedule for the week, - COORDINATION of works on the SITE, - the results of checks, inspections and TAKEOVERS carried out in the previous week, - plan of TAKEOVERS, controls and inspections, - discussion of DEFECTS, violations of the REGULATIONS and other deficiencies, - operational matters. |
|  | Monthly meetings throughout the period from commencement of the DELIVERY pursuant to Section 6.2.5 of the AGREEMENT until successful completion of the PERFORMANCE TEST - Part "A". The main item of the monthly meeting will be the discussion and approval of the MONTHLY REPORT, the work plan for the next 3 MONTHS and the COORDINATION of the contractors on the downstream (adjacent) works. |
|  | On behalf of the SUPPLIER, monthly meetings shall be attended by the Project Manager, Quality Control, Price Control and TIME SCHEDULE staff as required. |
|  | On behalf of the CUSTOMER, the monthly meetings shall be attended by the Project Manager or an authorized representative and other staff designated by the CUSTOMER as required. |

## MINUTES AND REPORTS

|  | The SUPPLIER is required to approve minutes of daily, weekly and monthly meetings. If the SUPPLIER does not agree with the draft minutes, it shall send its comments to the CUSTOMER, these shall be discussed at the latest at the next meeting. |
| --- | --- |
|  | The SUPPLIER is obliged to process and deliver to the CUSTOMER the MONTHLY REPORT always by the 5th working day of the following month in English language and by 10th working day of the following month in Czech language. The MONTHLY REPORT shall contain at least the following chapters: - a summary of the most important activities, - health and safety, environmental protection and fire protection during the works on the SITE, - accidents, incidents and the state of investigation in the course of work on the SITE, - problem areas requiring increased attention, - the course of the past month, - project and engineering activities, - purchase of GOODS and conclusion of contracts with SUB-SUPPLIERS, - implementation of the DELIVERY, - important entries to the construction and assembly logs, - plan of activities for the next 3 months, - project and engineering activities, - arranging deliveries and concluding contracts with SUB-SUPPLIERS, - implementation of the DELIVERY, - fulfilment of MILESTONES, - payments, payment schedule, - changes to the DELIVERY, - progress of the works, - construction workers, - problems and contradictions from the weekly and fortnightly meetings, - copies of minutes of weekly and fortnightly meetings, - photographic documentation from the implementation of the DELIVERY. |
|  | The content, form and distribution of the minutes of other meetings, the detailed content of the MONTHLY REPORT and the method of its distribution will be set out in the QUALITY ASSURANCE PLAN. |

## WORKERS

|  | The SUPPLIER is obliged to present to the CUSTOMER at the weekly meeting the actual number of persons who will be involved in the implementation of the DELIVERY within the framework of the CHIEF ASSEMBLY. |
| --- | --- |
|  | For each employee, the SUPPLIER shall: |
|  | Communicate the following information to the CUSTOMER: - the name and surname of the employee, - the type of work, the place of work and the duration of the posting, - the date of commencement and the date of termination of employment at the SITE. |
|  | Secure entry visas, residence permits and work permits in the Czech Republic, if required by the REGULATIONS. |
|  | All obligations set out in paragraph 14.6.2 of the AGREEMENT for the employment of foreign employees of the SUPPLIER shall also apply to foreign employees of any SUB-SUPPLIERS. |
|  | The SUPPLIER is obliged to employ for the execution of the subject of the AGREEMENT persons qualified to perform the work in a safe and quality manner, who have the qualifications, experience, knowledge, authorization, training and examination and health condition necessary according to the nature and complexity of the work. |
|  | The SUPPLIER shall ensure that the work carried out by its employees is carried out under the supervision of competent qualified supervisors. |
|  | The SUPPLIER shall ensure that during any activities on the SITE and on the CUSTOMER's premises, information is immediately communicated to all persons of the SUPPLIER involved in the execution of the DELIVERY in their native language or in Czech or English |
|  | The SUPPLIER shall pay social and health insurance premiums, pension insurance premiums and all other insurance premiums, taxes and fees required by the REGULATIONS and the AGREEMENT with respect to its employees. The same shall be provided for the SUB-SUPPLIER's employees. |
|  | The SUPPLIER shall provide normal work and protective clothing and footwear, safety protective equipment, etc. for persons involved in the execution of the DELIVERY. The SUPPLIER shall ensure that such persons do not unreasonably remain on the CUSTOMER's premises outside working hours and do not enter the premises, buildings and areas of the CUSTOMER's premises outside the scope necessitated by the performance of the DELIVERY. |
|  | The SUPPLIER is obliged to ensure that persons involved in the execution of the DELIVERY present on the SITE or on the CUSTOMER's premises have the SUPPLIER's marking visible on their work clothing or protective helmet. |
|  | The CUSTOMER may, at any time, on the basis of a breach of the rules set out in Annex 9 and Annex 10 to the AGREEMENT and in accordance with Annex 9 and Annex 10 to the AGREEMENT, force the SUPPLIER to replace the person involved in the execution of the DELIVERY and prohibit him from entering the SITE and the premises of the CUSTOMER. The SUPPLIER shall comply with this order and replace the relevant person with a new person who has the appropriate qualifications, skills and experience. |
|  | The CUSTOMER is entitled to check compliance with the provisions of paragraph 14.6 of the AGREEMENT at any time. The SUPPLIER shall cooperate and provide the CUSTOMER with all relevant documents and documentation necessary to carry out the inspection. |
|  | The maximum commuting and departure times of the SUPPLIER's personnel within the scope of the CHIEF ASSEMBLY for the purpose of quantifying the daily cost of the CHIEF ASSEMBLY shall not exceed 30 minutes (for each – arrival and departure – separately). |

# COOPERATION OF THE CUSTOMER

|  | The CUSTOMER shall secure the following permits required by the REGULATIONS: - Modification of the building before its completion (in Czech: změna stavby před jejím dokončením) according to Section 118 of Act No. 183/2006 Coll., on Planning and Building Code (Building Act), as amended, if necessary, - Permission to commence test operation according to the building permit pursuant to Section 124 of Act No. 183/2006 Coll., on Planning and Building Code (Building Act), as amended, - Completion consent (in Czech: kolaudační souhlas) pursuant to Section 122 of Act No. 183/2006 Coll., on spatial planning and building regulations (Building Act), as amended. - All other permits required by the relevant authorities, if the SUPPLIER is nor responsible for their obtaining as per the AGREEMENT. The building permit shall be handed over by the CUSTOMER to the SUPPLIER prior to the commencement of the CHIEF ASSEMBLY. If required by the SUPPLIER, the CUSTOMER shall also hand over certified copies of the other permits mentioned above. To allow the commencement of the test operation according to the building permit and to approve the building permit, the cooperation of the SUPPLIER is required, who is obliged to procure the relevant input documents, which can only be provided by the SUPPLIER, at the request of the CUSTOMER according to the conditions and within the scope defined in the AGREEMENT. |
| --- | --- |
|  | Prior to commencement of work on the SITE, the CUSTOMER shall inform the SUPPLIER of the area the SITE on which the SUPPLIER will perform the CHIEF ASSEMBLY. The CUSTOMER shall allow the SUPPLIER to work on the SITE on the dates specified in the TIME SCHEDULE. |
|  | The CUSTOMER shall allow the SUPPLIER to use the access road to the SITE to the extent specified in Annex 7 to the AGREEMENT. |
|  | The CUSTOMER is obliged to provide its personnel for the implementation and provision of COMPREHENSIVE TESTS, TESTING OPERATION and CONTINUOUS OPERATIONS. |
|  | The SUPPLIER is obliged to ensure the participation of its personnel in the controls, inspections and TAKEOVERS to be carried out with the participation of the SUPPLIER in accordance with the QUALITY ASSURANCE PLAN. |
|  | The CUSTOMER is obliged to ensure the participation of its employees in training courses on the operation, operation and maintenance provided by the SUPPLIER at the place and at the times agreed with the SUPPLIER. |
|  | The CUSTOMER shall permit entry of persons, transport of GOODS, materials, vehicles and machinery to and from the SITE through adjacent land owned by the CUSTOMER, but only to the extent necessary for the performance of the DELIVERY. |
|  | THE CUSTOMER shall provide THE SUPPLIER with the following: - arrange for basic occupational safety (HSE) training, - provide the basic permit to carry out works on the SITE, - ensure that a permit for working with open fires is obtained, - ensure the establishment of connection points for the energy and media necessary for the execution of the DELIVERY, - will provide energy and other media for the installation and execution of INDIVIDUAL TESTS on its own account. - will provide raw materials, consumables, energy and media to carry out COMPREHENSIVE and PERFORMANCE TESTS and TESTING OPERATION at its own expense. This provision shall also apply to the first repetition of the PERFORMANCE TEST - Part "A" if repeated for reasons attributable to the SUPPLIER. In case of further repetitions of the PERFORMANCE TEST – Part “A” for the reasons attributable to the SUPPLIER, the CUSTOMER shall provide the raw materials, consumables, energy and other media on the paid basis, the CUSTOMER and SUPPLIER shall entre into the separate contract with respect to the provision thereof. - construction site, storage and handling facilities according to Annex 7 to the AGREEMENT - other consideration according to Annex 7 to the AGREEMENT x - ensure deliveries that are part of the CUSTOMER's performance under the AGREEMENT - provide current construction documents and building permits for the construction of the new COMBINED CYCLE UNIT at the CUSTOMER's SITE prior to commencement of the CHIEF ASSEMBLY. |
|  | The CUSTOMER shall provide the CUSTOMER'S SAFETY COORDINATOR. |
|  | The CUSTOMER shall inform the SUPPLIER of all other works to be carried out on the SITE by other contractors, and ensure COORDINATION of the works and implementation of the DELIVERY with the activities of these contractors and with the operation of the plant. |
|  | The CUSTOMER shall provide to the SUPPLIER, to the extent reasonably available, all documentation of the current equipment and installations in the extend necessary to execute the DELIVERY |
|  | The CUSTOMER shall not refuse to issue to the SUPPLIER any consent, certificate and/or report in the performance of the DELIVERY under the AGREEMENT without a valid lawful reason and shall not unreasonably delay or withhold the foregoing. |
|  | The parties to the AGREEMENT exclude the application of the provisions of Section 2591 (Cooperation of the CUSTOMER) of the Civil Code to the legal relationship established by this AGREEMENT. |

# SUB-SUPPLIERS and suppliers of major components

## SUB-SUPPLIERS AND SUPPLIERS OF MAJOR COMPONENTS

|  | The SUB-SUPPLIER is a company, or a natural person engaged in business, which participates in the implementation of the DELIVERY under the AGREEMENT on the basis of a contractual relationship with the SUPPLIER and is listed in Annex 6A to the AGREEMENT. If a person not listed in Annex 6A to the AGREEMENT is to become the SUB-SUPPLIER after the AGREEMENT becomes effective, the SUPPLIER shall proceed in accordance with Clause 16.2.1 of the AGREEMENT. |
| --- | --- |
|  | The supplier of major components is the supplier listed in Annex 6B to the AGREEMENT. In the event of a change in the supplier of major components, the SUPPLIER shall seek the prior written consent of the CUSTOMER. |

## COMMON PROVISIONS

|  | In order to enter into a contract with SUB-SUPPLIER not listed in Annex 6A to the AGREEMENT, the SUPPLIER must request the prior written consent of the CUSTOMER. |
| --- | --- |
|  | The SUPPLIER shall enter into contracts with SUB-SUPPLIERS on its own behalf and shall bear all risks arising from such contracts. |
|  | SUPPLIER shall be liable for the obligations, work, GOODS, CHIEF ASSEMBLY performed by SUB-SUPPLIERS and all activities of SUB-SUPPLIERS when they perform work under the AGREEMENT as if performed by the SUPPLIER. |
|  | The SUPPLIER shall ensure that the contract between the SUB-SUPPLIER and the SUPPLIER implies a clear obligation to comply with the relevant provisions of this AGREEMENT relating to the SUB-SUPPLIER's performance. |
|  | The SUPPLIER is obliged to include in its contracts with SUB-SUPPLIERS provisions on: |
|  | The transfer of title to the DELIVERY or any part thereof to the SUPPLIER so that it may pass to the CUSTOMER in accordance with this AGREEMENT. |
|  | SUB-SUPPLIER's obligations to comply with the confidentiality obligations of similar to those in the AGREEMENT. |
|  | Obligation to submit to the CUSTOMER (upon its request), for information, orders (without prices) relating the delivery of the generator, gearbox and control system to be delivered by the respective SUB-SUPPLIER. |

# GOODS, CONSTRUCTION MACHINERY AND SURPLUS GOODS

|  | Deliveries of GOODS shall include a detailed delivery note (bill of delivery) listing all items and their quantities. All items shall be marked so as to be easily identifiable during transportation, handling and storage. |
| --- | --- |
|  | All GOODS and construction machinery must comply with the requirements of the REGULATIONS as required by the AGREEMENT. Construction machinery means all technical equipment, fixtures, machinery and tools intended by their nature to perform the DELIVERY but not to become part of it or to be consumed in whole or in part in its performance. |
|  | The SUPPLIER shall ensure that all GOODS necessary for the performance of the DELIVERY pursuant to the AGREEMENT are delivered to the SITE. |
|  | The SUPPLIER is responsible for the custom clearance of the GOODS including securing import permits. |
|  | The SUPPLIER shall identify the construction machinery required for the execution of the DELIVERY according to the AGREEMENT. |
|  | For the execution of the DELIVERY, the SUPPLIER shall use, to the extent provided by the REGULATIONS and/or necessary for the proper execution of the DELIVERY, only calibrated specified measuring instruments, which shall comply with Act No. 505/1990 Coll., on Metrology, as amended. |

# SITE

|  | The CUSTOMER shall provide to the SUPPLIER at its expense sources of electricity and other media according to Annex 7 to the AGREEMENT in the extend necessary for the SUPPLIER to fulfil its obligations on the SITE in accordance with this AGREEMENT. |
| --- | --- |
|  | The SUPPLIER declares that it has familiarized itself with the actual conditions at the SITE (as of the date of submission of the tender in the TENDER PROCEDURE) and has taken them into account in the PRICE. |

# CONTROLS, individual test and completion of assembly

|  | Checks, inspections and tests include the performance of technical supervision, all checks, tests and inspections during the execution of the DELIVERY. |
| --- | --- |

## TECHNICAL SUPERVISION

|  | During the execution of the DELIVERY, the CUSTOMER shall carry out technical supervision on the SITE to the extent necessary to check the compliance of the DELIVERY with the terms of the AGREEMENT. The technical supervision provided by the CUSTOMER does not relieve the SUPPLIER from the obligation to perform the DELIVERY properly in accordance with the AGREEMENT without DEFECTS. |
| --- | --- |
|  | The SUPPLIER shall provide the CUSTOMER's representatives carrying out the technical supervision with the necessary documents and information and allow them to carry out technical supervision on the SITE in an appropriate manner. |
|  | The SUPPLIER shall follow the instructions of the CUSTOMER's technical supervision in the execution of the DELIVERY in accordance with the AGREEMENT; this shall not relieve the SUPPLIER of its liability under the AGREEMENT. |

## CONTROLS, INSPECTIONS, TESTS

|  | SUPPLIER shall perform all controls, tests and inspections (hereinafter referred to as inspections) of the DELIVERY specified in the QUALITY ASSURANCE PLAN that are necessary to demonstrate compliance of the DELIVERY with the terms of the AGREEMENT. |
| --- | --- |
|  | The SUPPLIER shall perform all inspections of the DELIVERY prior to their delivery to the SITE to verify that their, quality of materials and workmanship are in accordance with the AGREEMENT. |
|  | The QUALITY ASSURANCE PLAN shall include at a minimum identification of the components of DELIVERY part to which the inspection relates, the specification of the relevant LEGISLATION, and a description of the parameter being assessed. |
|  | The CUSTOMER has the right to verify the quality of the DELIVERY at the agreed times and places. The SUPPLIER is obliged to allow the CUSTOMER to make such quality verification possible, for the purpose of its independent control. |
|  | The CUSTOMER shall have the right to refuse to accept the DELIVERY or any part of the DELIVERY if it finds that it is not in accordance with the AGREEMENT. If this occurs, the SUPPLIER shall, at its own expense, replace the defective part with a new, defect-free performance or make such modifications as will ensure that the defective part of the DELIVERY complies with all terms, conditions, requirements and specifications under the AGREEMENT. This shall be demonstrated by the SUPPLIER by repeated inspection. If the SUPPLIER proves that the defective part of the performance was caused by the CUSTOMER's fault, the SUPPLIER shall be entitled to the payment of the cost of modifying the performance or replacing the defective part. |
|  | The SUPPLIER is obliged to inform the CUSTOMER about the performance of all planned tests for which the participation of the CUSTOMER has been agreed, in writing at least 10 working days before their commencement. The SUPPLIER may carry out the tests in the event of the CUSTOMER's non-participation. |
|  | Inspections shall be carried out at the SITE, if possible; otherwise, they shall be carried out at the SUPPLIER'S or SUB-SUPPLIER'S premises. The SUPPLIER shall provide the CUSTOMER with access to the inspection site in the case of inspections for which the CUSTOMER's participation has been agreed. |
|  | The CUSTOMER may order the SUPPLIER to carry out other inspections not specified in the QUALITY ASSURANCE PLAN on the following terms and conditions: - the CUSTOMER shall provide the SUPPLIER with the justification of the alleged non-conformance of the DELIVERY with the AGREEMENT and propose what additional control, inspection or test shall be performed; - the SUPPLIER is entitled to refuse the CUSTOMER’s proposal in case that other control, inspection or test proving conformance of the DELIVERY with the AGREEMENT in respect raised by the CUSTOMER was performed in pursuance of the CHIEF ASSEMBLY; - the additional control, inspection or test may not be performed without the mutual agreement of both parties, if the agreement is not reached within 30 days, the rules of Article 34 of the AGREEMENT shall be applied. The CUSTOMER shall pay the costs of the additional only in case the result of the additional control, inspection or test proves conformance of the DELIVERY with the AGREEMENT. |
|  | The CUSTOMER shall have the right under the AGREEMENT to participate in tests for which the CUSTOMER's participation has been agreed in the AGREEMENT, as well in controls, inspections and tests for which the CUSTOMER’s participation will be agreed between the parties. The participation and/or non-participation of the CUSTOMER in the controls, inspections and/or tests shall in no way relieve the SUPPLIER of the obligation to deliver the DELIVERY according to the AGREEMENT. If the SUPPLIER fulfils and completes all the inspections and tests as per the QUALITY ASSURANCE PLAN, the SUPPLIER is entitled to dispatch the DELIVERY without the further consent of the CUSTOMER. If the SUPPLIER does not fulfil or complete any of the inspections and/or tests as per the QUALITY ASSURANCE PLAN, the SUPPLIER shall only be entitled to dispatch the DELIVERY if the CUSTOMER issues its APPROVAL thereto. The APPROVAL shall not be unreasonably withheld. |
|  | Work, supplies, GOODS, and CHIEF ASSEMBLY that the SUPPLIER must furnish or perform as a result of a nonconforming inspection caused by fault not attributable to the CUSTOMER shall not be considered a change in the DELIVERY. |
|  | The SUPPLIER is obliged to prepare a report of each inspection of the CUSTOMER and submit it for information or for the CUSTOMER'S APPROVAL according to the QUALITY ASSURANCE PLAN. |
|  | In the event that the result of the inspection does not meet the requirements of the AGREEMENT, the SUPPLIER is obliged to repeat the inspection after elimination of the DEFECTS and to invite the SUPPLIER to the re-inspection at least 3 working days in advance if it is an inspection for which the participation of the SUPPLIER has been agreed. |
|  | The SUPPLIER declares that it shall bear all costs associated with carrying out the controls, inspections and tests under the AGREEMENT are included in the PRICE. In the event of a repeated control, inspection or tests for reasons on the SUPPLIER's side, the SUPPLIER shall pay all its costs and the CUSTOMER's demonstrable costs. |

## INDIVIDUAL TESTS

|  | The detailed execution of the INDIVIDUAL TESTS shall be set out in the QUALITY ASSURANCE PLAN and the INDIVIDUAL TESTS plan prepared by the SUPPLIER and the APPROVED by the CUSTOMER. |
| --- | --- |
|  | INDIVIDUAL TESTS are carried out by the SUPPLIER in pursuance of the CHIEF ASSEMBLY in the presence of the CUSTOMER. |
|  | Upon successful completion of the INDIVIDUAL TESTS, the SUPPLIER shall prepare a report (protocol) detailing the progress and results of the INDIVIDUAL TESTS containing a declaration by the SUPPLIER's responsible representatives that the SUPPLIER is ready to commence the COMPREHENSIVE TESTS. |
|  | In the protocol, the SUPPLIER shall list, describe and date the removal of the DEFECTS that were detected during the INDIVIDUAL TESTS and that do not prevent the start of the COMPREHENSIVE TESTS and their safe execution. The SUPPLIER shall remedy such DEFECTS within the agreed deadlines. |
|  | The protocol for INDIVIDUAL TESTS is subject to CONSENT by the CUSTOMER. |
|  | In exceptional cases and upon APPROVAL by the CUSTOMER, it is possible to carry out an INDIVIDUAL TEST during the COMPREHENSIVE TEST or during the TESTING OPERATION. |

## COMPLETION OF ASSEMBLY

|  | COMPLETION OF ASSEMBLY shall be confirmed by mutual approval of the protocol of COMPLETION OF ASSEMBLY. At this moment the DELIVERY is ready to start the COMPREHENSIVE TESTS. |
| --- | --- |
|  | Upon COMPLETION OF ASSEMBLY, the SUPPLIER shall deliver to the CUSTOMER the updated and complete INITIAL DOCUMENTATION OF DELIVERY required by the AGREEMENT and the QUALITY ASSURANCE PLAN., which the SUPPLIER shall provide by the time of COMPLETION OF ASSEMBLY. |

# COMMISSIONING

## GENERALLY APPLICABLE PROVISIONS

|  | COMMISSIONING occurs after the completion of the INDIVIDUAL TESTS and the COMPLETION OF ASSEMBLY in accordance with paragraph 19.5 of the AGREEMENT and includes activities leading to the enabling of the CONTINUOUS OPERATION of the DELIVERY, i.e.: - COMPREHENSIVE TESTS, - TESTING OPERATION, - PRELIMINARY ACCEPTANCE of DELIVERY. |
| --- | --- |
|  | COMMISSIONING shall be carried out by the SUPPLIER, as specified in the AGREEMENT. The CUSTOMER shall coordinate the COMMISSIONING. The SUPPLIER shall ensure the proper function, operation and operability of the DELIVERY during the COMMISSIONING in accordance with the AGREEMENT. |
|  | The SUPPLIER shall carry out the COMMISSIONING, according to the TIME SCHEDULE agreed. The SUPPLIER shall appoint a responsible manager for the COMMISSIONING, who shall cooperate with the CUSTOMER. SUPPLIER shall ensure the presence of personnel to ensure the reliable and safe operation of the DELIVERY, the performance of DEFECT repairs and adjustments, including the provision of spare parts as specified in this AGREEMENT. The cost of such activities by the SUPPLIER shall be included in the PRICE. |
|  | The SUPPLIER agrees that the CUSTOMER shall use the DELIVERY from the date of commencement of the COMMISSIONING until the PRELIMINARY ACCEPTANCE of the DELIVERY in connection with the performance of the relevant tests, with the understanding that the outputs of the DELIVERY obtained during these tests may be used for further use, including commercially within the CUSTOMER's power plant operations, and in this context, this condition cannot be considered as a commercial use of the DELIVERY for the purposes of the AGREEMENT, and the issuance of a PRELIMINARY ACCEPTANCE CERTIFICATE by the CUSTOMER cannot be claimed on the basis of this. However, the act of such use of the SUPPLIER after commencement of the COMMISSIONING shall not affect the SUPPLIER's obligation to properly and timely perform the DELIVERY and the SUPPLIER's liability for the DELIVERY. With respect to paragraph 22.3.3.2 of the AGREEMENT the liability of the SUPPLIER for the SUPPLIER during the period of the repeat of the PERFORMANCE TEST "A" shall not be further affected, unless the damage is caused directly by the CUSTOMER's failure to comply with the SUPPLIER's instructions. |
|  | All inputs and outputs to and from the technological process of the DELIVERY are the property of the CUSTOMER during the performance of the AGREEMENT. |

## COMPREHENSIVE TESTS

|  | The detailed execution of the COMPREHENSIVE TESTS shall be set out in the COMPREHENSIVE TEST PLAN prepared by the SUPPLIER and APPROVED by the CUSTOMER. The COMPREHENSIVE TESTS PLAN shall be prepared by the SUPPLIER to the extent specified in the QUALITY ASSURANCE PLAN APPROVED by the CUSTOMER. |
| --- | --- |
|  | The SUPPLIER is obliged to procure and submit all materials, data and documents necessary for obtaining permits from Czech authorities and bodies, if required by the REGULATIONS, and permits for the CUSTOMER to start and carry out the COMPREHENSIVE TESTS and to comply with the conditions specified in these permits during the COMPREHENSIVE TESTS. SUPPLIER shall submit materials, data and documents in accordance with the terms of the AGREEMENT. All within the limits of clause 6.2.2.20 of the AGREEMENT. |
|  | Prior to or during the COMPREHENSIVE TESTS, the SUPPLIER shall train the CUSTOMER's employees in the operation and maintenance of the DELIVERY to the extent required by the AGREEMENT so that it may be properly and safely operated by the CUSTOMER. |
|  | If, for reasons attributable to the SUPPLIER, the requirements for initiation of follow-on testing as per the QUALITY ASSURANCE PLAN for operability, reliability, safety, and quality of the DELIVERY are not met during the COMPREHENSIVE TESTS, the SUPPLIER shall, at its own expense, make the necessary changes, modifications or additions to the DELIVERY to meet these parameters and requirements. The SUPPLIER shall notify the CUSTOMER of the necessary changes, modifications or additions and shall repeat the portion of the COMPREHENSIVE TESTS that has not been met, until all requirements have been met. During the COMPREHENSIVE TESTS, the SUPPLIER may make the necessary adjustments and settings. |
|  | Upon successful completion of the COMPREHENSIVE TESTS, the SUPPLIER shall prepare a COMPREHENSIVE TESTS report (protocol) detailing the progress and results of the COMPREHENSIVE TESTS and containing a declaration by the SUPPLIER's responsible representatives that the SUPPLIER is ready to commence TESTING OPERATIONS. |
|  | In the COMPREHENSIVE TESTS report, the SUPPLIER shall list, describe and set a date for the removal of the DEFECTS that were identified during the COMPREHENSIVE TESTS that do not prevent the commencement of the TESTING OPERATION. SUPPLIER shall remove such DEFECTS after the PRELIMINARY ACCEPTANCE of DELIVERY within the dates specified in the COMPREHENSIVE TESTS report APPROVED by the CUSTOMER. If the SUPPLIER does not remove the DEFECTS for reasons on his part within the agreed deadline, such DEFECTS may be removed by the CUSTOMER himself at the expense of the SUPPLIER; to cover the costs, the CUSTOMER is entitled to draw on the PERFORMANCE BOND according to paragraph 27.2 of the AGREEMENT, if the SUPPLIER fails to pay the costs within 30 days from the date of receipt of the request for their payment. |
|  | The COMPREHENSIVE TESTS are completed by the CUSTOMER'S APPROVAL to the COMPREHENSIVE TESTS protocol. |
|  | In exceptional cases and upon APPROVAL by the CUSTOMER, it is possible to carry out COMPREHENSIVE TESTS including its possible repetition even after the APPROVAL COMPREHENSIVE TESTS protocol during the TESTING OPERATION. |

## TESTING OPERATION

|  | TESTING OPERATION will commence once the following conditions have been met: - written statement by the SUPPLIER that it is possible to start the TESTING OPERATION, - the operator of the equipment has been demonstrably trained and became familiar with the operating and safety regulations. |
| --- | --- |
|  | The SUPPLIER shall comply with the conditions set out in the permit for the commencement and execution of the test operation under the building permit during the TESTING OPERATION. |
|  | During the TESTING OPERATION, the SUPPLIER shall demonstrate the faultless and safe operation of the DELIVERY and the fulfilment of the parameters and performance indicators according to the AGREEMENT. The compliance with the parameters and performance indicators shall be demonstrated by successful performance of: - FUNCTIONAL TESTS, - TRIAL RUN (72 hours continuously), - PERFORMANCE TESTS - Part "A". |
|  | The detailed execution of the individual parts of the TEST OPERATION shall be set out in the FUNCTIONAL TESTS Plan, the TRIAL RUN Plan (72 hours continuous) prepared by the SUPPLIER and APPROVED by the CUSTOMER and the PERFORMANCE TEST Plan prepared by the CUSTOMER and APPROVED by the SUPPLIER. |
|  | The TESTING OPERATION will be carried out under supervision of the SUPPLIER's representatives. The operation and maintenance of the SUPPLIER shall be ensured by the CUSTOMER's own employees, who shall be duly trained for this activity by the SUPPLIER. |
|  | The SUPPLIER is obliged to provide, upon the CUSTOMER's request, all the cooperation and additional information and supplements required by the competent authorities during the permitting and approval procedure. |
|  | The SUPPLIER shall, during the TESTING OPERATION, remedy all DEFECTS of the DELIVERY discovered up to the PRELIMINARY ACCEPTANCE of the DELIVERY, except for minor defects not impeding the proper and safe operation of the DELIVERY. SUPPLIER shall remedy such minor DEFECTS, within a deadlines APPROVED by the CUSTOMER, after the PRELIMINARY ACCEPTANCE OF DELIVERY. In the event that the SUPPLIER fails to remove the DEFECTS within the agreed deadlines for reasons on its part, the CUSTOMER may remove such DEFECTS itself at the expense and risk of the SUPPLIER; the CUSTOMER shall be entitled to draw on the PERFORMANCE BOND pursuant to paragraph 27.2 of the AGREEMENT to cover the costs should the SUPPLIER not pay the costs within 30 days of the request for payment being delivered. |
|  | The SUPPLIER shall carry out checks, inspections and tests during the TESTING OPERATION according to the plan of controls, inspections and tests during the TESTING OPERATION, which shall be part of the QUALITY ASSURANCE PLAN. Furthermore, the SUPPLIER shall be obliged to carry out additional checks, inspections and tests during the TESTING OPERATION on the following terms and conditions: - the CUSTOMER shall provide the SUPPLIER with the justification of the alleged non-conformance of the DELIVERY with the AGREEMENT and propose what additional control, inspection or test shall be performed; - the SUPPLIER is entitled to refuse the CUSTOMER’s proposal in case that other control, inspection or test proving conformance of the DELIVERY with the AGREEMENT in respect raised by the CUSTOMER was performed in pursuance of the CHIEF ASSEMBLY; - the additional control, inspection or test may not be performed without the mutual agreement of both parties, if the agreement is not reached within 30 days, the rules of Article 34 of the AGREEMENT shall be applied. If these performed additional checks, inspections and/or tests do not reveal any DEFECTS, the CUSTOMER shall bear the related costs. Otherwise, the SUPPLIER shall bear the costs. Likewise, the SUPPLIER shall be obliged to carry out any INDIVIDUAL and COMPREHENSIVE TESTS during the TESTING OPERATION, the performance of which was not necessary for the commencement of the TESTING OPERATION and which the CUSTOMER APPROVED to be carried out during the TESTING OPERATION. |
|  | TESTING OPERATION is completed by the PRELIMINARY ACCEPTANCE OF DELIVERY. Any trial operation according to the building permit shall be completed by the issuance of the completion consent (in Czech: kolaudační souhlas) procured by the CUSTOMER. |
|  | The minimum length of the TESTING OPERATION shall be determined in the TESTING OPERATION Plan and the minimum length of any test operation under the building permit shall be determined in the building permit procured by the CUSTOMER pursuant to paragraph 15.1 of the AGREEMENT. |

## TESTS DURING THE TESTING AND CONTINUOUS OPERATIONS

|  | TESTS during the TESTING OPERATION and during the CONTINUOUS OPERATION shall be coordinated by the CUSTOMER and according to his instructions they shall be arranged for by the SUPPLIER according to the terms of the AGREEMENT. PERFORMANCE TEST – Part “A” and PERFORMANCE TEST – Part “B” shall be performed by the SUPPLIER in pursuance of the CHIEF ASSEMBLY. |
| --- | --- |
|  | TESTS during the TESTING OPERATION will be carried out on dates according to the TIME SCHEDULE. |
|  | The FUNCTIONAL TESTS will be carried out according to the FUNCTIONAL TESTS Plan, which is part of the QUALITY ASSURANCE PLAN. |
|  | During the FUNCTIONAL TESTS, the SUPPLIER may make necessary adjustments and modifications. |
|  | The TRIAL RUN (72 hours) will be conducted according to the TRIAL RUN Plan, which is part of the QUALITY ASSURANCE PLAN. |
|  | The TRIAL RUN (72 hours) must demonstrate the reliability of the operation of the DELIVERY during 72 hours of continuous operation. The SUPPLIER shall not make any adjustments or modifications to the DELIVERY during the TRIAL RUN (72 hours). |
|  | Upon successful completion of the TRIAL RUN, the SUPPLIER shall prepare a report detailing the course and results of the TRIAL RUN. |
|  | In the report, the SUPPLIER shall list, describe and set deadlines for the removal of the DEFECTS that were detected during the TRIAL RUN. The SUPPLIER is obliged to remedy such DEFECTS within the agreed deadlines. |
|  | The protocol of the TRIAL RUN is subject to the CUSTOMER'S APPROVAL. |
|  | PERFORMANCE TESTS will be performed in accordance with the PERFORMANCE TESTS Plan, which is part of the QUALITY ASSURANCE PLAN. |
|  | PERFORMANCE TESTS will be divided into two parts: - PERFORMANCE TESTS - Part „A“ - PERFORMANCE TESTS – Part “B”. |
|  | During the PERFORMANCE TESTS, the SUPPLIER shall demonstrate that the DELIVERY and all its parts meet the parameters as specified in the AGREEMENT. A list of the GUARANTEED PARAMETERS and the required values are set out in Annex 5 to the AGREEMENT. |
|  | PERFORMANCE TEST - Part „A“ shall be performed by the CUSTOMER in cooperation with the SUPPLIER in pursuance of the CHIEF ASSEMBLY during the TESTING OPERATION after the operation of the DELIVERY has been stabilized prior to the PRELIMINARY ACCEPTANCE. |
|  | By performing the PERFORMANCE TESTS - Part „A“, the SUPPLIER shall demonstrate that the DELIVERY meets the GUARANTEED PARAMETERS required for the PERFORMANCE TESTS - Part „A“. Measurement and evaluation of all performance requirements and functions required for the PERFORMANCE TESTS - Part „A“ shall be performed by a duly authorized independent third party provided by the CUSTOMER. The PERFORMANCE TESTS - Part „A“ shall be completed by a protocol APPROVED by the CUSTOMER. |
|  | In the event of failure to meet the GUARANTEED PARAMETERS during the PERFORMANCE TESTS - Part „A“, for reasons solely attributable to the SUPPLIER, the SUPPLIER may repeat the PERFORMANCE TEST - Part „A“ once the SUPPLIER has made adjustments to the DELIVERY, unless otherwise agreed between the parties. Adjustments to the DELIVERY and the repetition of the PERFORMANCE TEST - Part „A“ shall be made at the times APPROVED by the CUSTOMER and in the event that the PERFORMANCE TESTS - Part „A“ are repeated for reasons solely attributable to the SUPPLIER, the SUPPLIER shall be obliged to pay all its extra costs and the CUSTOMER's costs incurred as a result of such repetition of the PERFORMANCE TESTS - Part „A“ (excluding the costs of gas consumption), as well as the applicable contractual penalties/liquidated damages pursuant to Article 22 of the AGREEMENT. |
|  | The PERFORMANCE TESTS – Part “B”, will be performed by the CUSTOMER in cooperation with the SUPPLIER in pursuance of the CHIEF ASSEMBLY during the WARRANTY PERIOD at the time stipulated by the CUSTOMER. Within the PERFORMANCE TESTS - Part “B” the DELIVERY shall prove to fulfil the GUARANTEED PARAMETERS required for the successful PERFORMANCE TESTS – Part “B”. The measurements and the assessment of all output requirements and functions as they are required for the GUARANTEE TESTS – Part B shall be performed by the properly authorized independent third party arranged for by the CUSTOMER. The GUARANTEE TESTS - Part “B”, will be finalised by the APPROVED protocol. - If the GUARANTEED PARAMETERS are not fulfilled during the PERFORMANCE TESTS - Part “B” due to the reasons solely attributable to the SUPPLIER, the SUPPLIER is entitled to repeat once the PERFORMANCE TESTS – Part “B” after performing adjustments to the DELIVERY, unless agreed otherwise by the parties. The adjustments and the repetition of the PERFORMANCE TESTS - Part “B”, will be performed at dates APPROVED by the CUSTOMER and in the case that the PERFORMANCE TESTS – Part “B” are repeated due to the reasons solely attributable to the SUPPLIER, the SUPPLIER shall be obliged to cover all his extra costs and the costs incurred by the CUSTOMER (except for the cost of the natural gas consumption), which occurred due to the repetition of the PERFORMANCE TESTS - Part “B”. |

# takeover of the DELIVERY

## GENERAL PROVISIONS

| 21.1.1. | TAKEOVER of the DELIVERY includes all takeovers during the execution of the DELIVERY as defined in the QUALITY ASSURANCE PLAN, MILESTONE'S acceptance, PRELIMINARY ACCEPTANCE and FINAL ACCEPTANCE. No TAKEOVER shall relieve the SUPPLIER of the obligation to deliver the DELIVERY in the manner, under the terms and conditions and within the time limits specified in the AGREEMENT. The SUPPLIER shall prepare a protocol with respect to each TAKEOVER, which shall include the date and place, subject, description of the course and result of the TAKEOVER. The SUPPLIER shall submit the protocol to the CUSTOMER for review and APPROVAL within 13 working days from the date of the TAKEOVER. If the CUSTOMER does not agree with the protocol and the results of the TAKEOVER due to DEFECTS in the DELIVERY, the SUPPLIER is obliged to repeat the TAKEOVER after the DEFECTS have been eliminated and to invite the CUSTOMER to the repeated TAKEOVER at least 3 working days in advance. The SUPPLIER declares that all costs associated with the implementation of the DELIVERY are included in the PRICE. In the event of repetition of the TAKEOVER for reasons on the SUPPLIER's side, the SUPPLIER shall pay all its costs and CUSTOMER's proven costs. |
| --- | --- |

## TAKEOVER OF THE DOCUMENTATION

|  | The SUPPLIER shall be obliged to duly hand over all documentation according to the AGREEMENT to the CUSTOMER together with the handover protocol. At the request of the CUSTOMER, the SUPPLIER is obliged to hand over the documentation beyond the scope specified in Annex 7 to the AGREEMENT within a reasonable period of time, if it is available (this is not new documentation that the SUPPLIER would have to yet elaborate), with the exception of documentation containing trade secrets and know-how of the SUPPLIER. |
| --- | --- |
|  | The place of delivery of the documentation is the CUSTOMER's headquarters according to paragraph 3.1.2 of the AGREEMENT for documentation delivered in printed form and the SUPPLIER's electronic repository for documentation delivered in electronic form. |
|  | The CUSTOMER shall check the completeness of the documentation after handing it over and shall further comment on the documentation within 20 working days from the date of handing over. The CUSTOMER's statement to the documentation does not relieve the SUPPLIER of responsibility for the documentation. The contents of the SUPPLIER's statement may be as following: No comments, the documentation can be used without restrictions, With comments not precluding its use. The documentation may be further used, provided that the comments of the CUSTOMER are incorporated for further use. With comments preventing its use. In this case, the documentation cannot be used and must be corrected by the SUPPLIER and resubmitted to the CUSTOMER for repeated inspection. |
|  | In the event that the CUSTOMER discovers errors in the documentation during the TAKEOVER, the SUPPLIER shall be obliged to correct them within 20 working days from the receipt of the comments, unless the parties agree otherwise. |

## MILESTONE'S TAKEOVER

|  | The SUPPLIER is obliged to invite the technical supervision of the SUPPLIER and the project manager of the SUPPLIER to the takeover of the MILESTONES no later than 10 working days before the date of their TAKEOVER for the acceptance before delivery of the GOODS and no later than 3 working days before the date of acceptance for the TAKEOVER at the SITE. |
| --- | --- |
|  | The TAKEOVER may only be carried out in the presence of the project managers of the CUSTOMER and the SUPPLIER. |
|  | The SUPPLIER shall perform all inspections as required by the AGREEMENT prior to TAKEOVER. |
|  | The SUPPLIER is obliged to prepare related documentation, reports and certificates of inspections carried out under the AGREEMENT prior to the TAKEOVER. |
|  | The protocol of the TAKEOVER APPROVED by the CUSTOMER shall be attached by the SUPPLIER to the invoice issued by the SUPPLIER upon completion of the MILESTONE to which payment is linked. The protocol shall include, at a minimum, an inventory of the work performed in accordance with the MILESTONE specifications in written or electronic form. |

## PRELIMINARY ACCEPTANCE

|  | The SUPPLIER shall manage and organise the PRELIMINARY ACCEPTANCE. |
| --- | --- |
|  | PRELIMINARY ACCEPTANCE shall be the TAKEOVER that will take place after successful completion of the TESTING OPERATION, including meeting at least the ACCEPTABLE VALUES of GUARANTEED PARAMETERS as set forth in Annex 5 of the AGREEMENT. The CUSTOMER shall be entitled to take over the DELIVERY even in the event that the GUARANTEED PARAMETERS are outside the ACCEPTABLE VALUES. In the event that any of the GUARANTEED PARAMETERS is not fulfilled in such a way that it is within the ACCEPTABLE VALUE of such GUARANTEED PARAMETER as set forth in Annex 5 to the AGREEMENT, the CUSTOMER shall take over the DELIVERY and the SUPPLIER shall be entitled, at its sole discretion, to take the necessary corrective action and repeat the PERFORMANCE TEST - Part "A" or pay the discount pursuant to paragraph 9.3 of the AGREEMENT. In the event that any of the GUARANTEED PARAMETERS is not fulfilled in such a way that it is not within the ACCEPTABLE VALUE of such GUARANTEED PARAMETER as set forth in Annex 5 to the AGREEMENT and at the same time the CUSTOMER decides to take over such DELIVERY, the SUPPLIER shall be entitled to decide whether it takes measures at its own expense and risk to meet the unfulfilled GUARANTEED PARAMETER and to repeat the PERFORMANCE TESTS - Part "A", all within 4 months of the PRELIMINARY ACCEPTANCE of the DELIVERY or to apply a discount pursuant to paragraph 9.3 of the AGREEMENT. |
|  | The SUPPLIER is obliged to invite the CUSTOMER to PRELIMINARY ACCEPTANCE of the DELIVERY on the dates according to the TIME SCHEDULE. |
|  | The SUPPLIER shall perform all inspections as required by the AGREEMENT prior to PRELIMINARY ACCEPTANCE. |
|  | The SUPPLIER shall prepare related documentation for the SUPPLIER, the FUNCTIONAL TESTS, TRIAL RUN and PERFORMANCE TESTS - Part „A“ reports and certificates of inspections and protocols of TAKEOVERS performed under the AGREEMENT. |
|  | The CUSTOMER shall check whether the SUPPLIER has fulfilled all its obligations which it was obliged to fulfil under the AGREEMENT by the time of completion of the TESTING OPERATION, in particular whether the SUPPLIER has successfully completed: - FUNCTIONAL TESTS, - TRIAL RUN, - PERFORMANCE TESTS "A", achieved at least in the ACCEPTABLE VALUES. If the aforementioned tests have been successfully completed and the DELIVERY has no DEFECTS, except for minor DEFECTS not limiting the proper and safe operation of the DELIVERY, for which a deadline for their removal has been agreed upon, PRELIMINARY ACCEPTANCE shall take place, of which the parties to the AGREEMENT shall execute a PRELIMINARY ACCEPTANCE CERTIFICATE. In the event that the SUPPLIER does not remove the identified minor DEFECTS for reasons on its side within the agreed time specified in PRELIMINARY ACCEPTANCE PROTOCOL, the CUSTOMER may remove such DEFECTS himself at the expense of the SUPPLIER; in case of the SUPPLIER’s delay in payment of such expense the CUSTOMER shall be entitled to draw on the PERFORMANCE BOND pursuant to paragraph 27.2 of the AGREEMENT to cover the costs. PRELIMINARY ACCEPTANCE shall occur even if the CUSTOMER has not issued a PAC by 12 months from the date of execution of MILESTONE No. 3 (GAS TURBINE with auxiliaries on SITE) as per Annex 2 to the AGREEMENT, provided that there is no delay in the PRELIMINARY ACCEPTANCE due to reasons attributable to the SUPPLIER. |
|  | Within 15 days after the PRELIMINARY ACCEPTANCE of the DELIVERY, the CUSTOMER shall issue the PAC and provide it to the SUPPLIER. |
|  | The WARRANTY PERIOD begins on the date of issue of the PRELIMINARY ACCEPTANCE CERTIFICATE. In case the CUSTOMER fails to issue a PRELIMINARY ACCEPTANCE CERTIFICATE in compliance with the AGREEMENT even though the conditions for the PRELIMINARY ACCEPTANCE are met, the WARRANTY PERIOD shall commence upon the PRELIMINARY ACCEPTANCE. |

## FINAL ACCEPTANCE OF DELIVERY

|  | The SUPPLIER shall be obliged to invite the CUSTOMER for the FINAL ACCEPTANCE of the DELIVERY within the date of expiry of the original WARRANTY PERIOD (the prolonged WARRANTY PERIOD as per paragraph 27.1.3 of the AGREEMENT shall be considered the original WARRANTY PERIOD). |
| --- | --- |
|  | FINAL ACCEPTANCE OF DELIVERY is the final TAKEOVER of DELIVERY after the end of the original WARRANTY PERIOD. |
|  | The SUPPLIER shall prepare and submit the AS-BUILT DOCUMENTATION and perform all the TESTS and measurements required by the AGREEMENT. |
|  | The CUSTOMER shall check whether the SUPPLIER has fulfilled all of its obligations that it was required to fulfill under the AGREEMENT, by the time the WARRANTY PERIOD expires. If no DEFECTS are found, the CUSTOMER shall issue to the SUPPLIER a FINAL ACCEPTANCE CERTIFICATE within 30 days after the expiration of the original WARRANTY PERIOD. The date of issuance of the FINAL ACCEPTANCE CERTIFICATE shall be the date of completion of the FINAL ACCEPTANCE. If the FINAL ACCEPTANCE CERTIFICATE is not issued by the CUSTOMER within this period, the FINAL ACCEPTANCE of the DELIVERY shall be deemed to have occurred on the last day of the original WARRANTY PERIOD. |
|  | The CUSTOMER shall confirm the FINAL ACCEPTANCE and issue the FINAL ACCEPTANCE CERTIFICATE even in the case that any of the GUARANTEED PARAMETERS within the PERFORMANCE TESTS – Part “B” is not fulfilled, whether within the range of the ACCEPTABLE VALUE of such GUARANTEED PARAMETER or not. In the case of any of the GUARANTEED PARAMETERS as set forth in Annex 5 to the AGREEMENT is not met, the SUPPLIER shall be entitled to decide whether it takes measures at its own expense and risk to meet the unfulfilled GUARANTEED PARAMETER and to repeat the PERFORMANCE TESTS - Part "B" within 60 days of the completion of unsuccessful PERFORMANCE TESTS - Part "B" or it pays the discount for non-achievement of the GUARANTEED PARAMETER set forth in paragraphs 9.3.2.1 to 9.3.2.9 of the AGREEMENT. In such a case the CUSTOMER signs the protocol on FINAL ACCEPTANCE and issues the FINAL ACCEPTANCE CERTIFICATE after the necessary remedial measurements were made and the PERFORMANCE TESTS – Part “B” were repeated, the GUARANTEED PARAMETERS as set forth in Annex 5 to the AGREEMENT are met or after the discount for non-achievement of the GUARANTEED PARAMETER has been provided. The discount will be provided in compliance with paragraphs 9.3.2.1 to 9.3.2.9 of the AGREEMENT. |
|  | The date of issuance of the FINAL ACCEPTANCE CERTIFICATE or the date of FINAL ACCEPTANCE of the DELIVERY in the event that the FINAL ACCEPTANCE CERTIFICATE has not been properly issued by the CUSTOMER pursuant to paragraph 21.5.4 of the AGREEMENT shall be the date of fulfilment of all of the SUPPLIER's obligations under the AGREEMENT, except for the obligation arising from the new WARRANTY PERIOD and liability for damages and contractual penalties/liquidated damages, if any. |
|  | On the date of issuance of the FINAL ACCEPTANCE CERTIFICATE, the CUSTOMER shall release the PERFORMANCE BOND in accordance with the terms of paragraph 27.2 of the AGREEMENT. If the FINAL ACCEPTANCE CERTIFICATE is not properly issued by the CUSTOMER pursuant to paragraph 21.5.4 of the AGREEMENT, the CUSTOMER shall release the PERFORMANCE BOND in accordance with the rules of the AGREEMENT in paragraph 27.2 of the AGREEMENT within 60 days of FINAL ACCEPTANCE of the DELIVERY. |

# contractual PENALTIES AND late payment INTEREST

## GENERAL PROVISIONS

|  | The following provisions apply to all contractual penalties and interest for late payment set forth in the AGREEMENT. |
| --- | --- |
|  | The CUSTOMER shall be entitled to claim a contractual penalty for breach of the following obligations under the AGREEMENT. |
|  | The due date of invoices calculating the contractual penalties and/or late payment interest, if any, is 30 days from the date of delivery of the relevant invoice to the other PARTY of the AGREEMENT. |
|  | The total amount of all contractual penalties in relation to the relevant DELIVERY is limited to 18 % of the PRICE of the relevant DELIVERY. |
|  | The value of contractual penalties shall be calculated to two decimal places. |
|  | The application and/or payment of any contractual penalty shall be without prejudice to the CUSTOMER's right to withdraw from the AGREEMENT and/or claim damages in the full amount and/or discount on the PRICE. Nevertheless, with respect to the breach of the obligations secured by the liquidated damages pursuant to paragraph 22.2.1, paragraph 22.2.2, paragraph 22.2.3 or paragraph 22.3 of the AGREEMENT and with respect to the breach of obligations that are subject to the discount as stipulated in paragraph 9.3 of the AGREEMENT, the CUSTOMER shall not be entitled to claim any additional damages, i.e. the contractual penalty/discount shall be considered sole and exclusive remedy for such a breach of the SUPPLIER’s obligations. |

## DELAY

|  | The CUSTOMER shall be entitled to demand a payment of the contractual penalty/liquidated damages for delay in the achievement of MILESTONE No. 3 only if the delay was caused by the breach of obligations under the AGREEMENT by the SUPPLIER at the rate of 0.1 % of the PRICE of the respective DELIVERY for each commenced day of delay. In this case, the contractual penalty shall be a lump-sum – no further damages can be claimed by the CUSTOMER. |
| --- | --- |
|  | The CUSTOMER shall be entitled to demand a payment of the contractual penalty/liquidated damages for delay in mobilizing the SUPPLIER's personnel to the SITE according to paragraph 8.2.9 of the AGREEMENT within the period of ASSEMBLY and INDIVIDUAL TESTS according to the SCHEDULE in the amount of CZK 10,000 for each case and commenced day of delay. The CUSTOMER is entitled to demand a payment of the contractual penalty/liquidated damages for delays in the aggregate duration of COMPREHENSIVE TESTS, FUNCTIONAL TESTS, TRIAL RUN and PERFORMANCE TESTS according to the TIME SCHEDULE due to the reasons solely attributable to the SUPPLIER in the amount of 0,05 % of the PRICE of the relevant DELIVERY for each commenced day of delay. For the avoidance of doubt, the time responsibility of the SUPPLIER under this paragraph of the AGREEMENT is fulfilled for each individual test by its successful completion as specified in the QUALITY ASSURANCE PLAN and not by APPROVAL of the test report by the CUSTOMER. APPROVAL of the test report is not a condition for starting the next test. This contractual penalty/liquidated damages shall not be applicable for the first fourteen (14) days of delay. The contractual penalty/liquidated damages for delays in COMMISSIONING (as defined in this paragraph of the AGREEMENT) shall only be applicable provided that the CUSTOMER fulfils the following conditions: - The CUSTOMER shall ensure all readiness specified in the TIME SCHEDULE, including the readiness of the downstream equipment, the readiness to output and power supply its own consumption, fuel supply and all necessary media for testing, cooperation of the CUSTOMER's staff and suppliers of related equipment, - if for a specific DELIVERY the CUSTOMER has decided according to paragraph 13.2 of the AGREEMENT not to require spare parts, the CUSTOMER is obliged to ensure that spare parts according to the list of spare parts recommended by the SUPPLIER for the WARRANTY PERIOD will be available on the premises of the CUSTOMER before the start of COMMISSIONING, and to allow the SUPPLIER to use these spare parts during the COMMISSIONING to remove DEFECTS under the same conditions as in paragraph 13.1 of the AGREEMENT. - if for a specific DELIVERY the CUSTOMER has decided according to paragraph 13.2 of the AGREEMENT to require spare parts, the CUSTOMER is obliged to ensure that spare parts according to the list of spare parts recommended by the SUPPLIER for the WARRANTY PERIOD will be available on the premises of the CUSTOMER before the start of COMMISSIONING, and to allow the SUPPLIER to use these spare parts during the COMMISSIONING to remove DEFECTS under the same conditions as in paragraph 13.1 of the AGREEMENT, all of the aforesaid subject to the prerequisite of the due delivery of the spare parts recommended by the SUPPLIER for the WARRANTY PERIOD by the SUPPLIER to the CUSTOMER prior the commencement of the COMMISSIONING. - The CUSTOMER shall provide the SUPPLIER with access to the SITE and to all equipment and premises of the CUSTOMER related to the COMMISSIONING during the COMMISSIONING to the extent necessary to ensure the SUPPLIER's obligations under the AGREEMENT. - The CUSTOMER shall provide the SUPPLIER with access to all relevant records on construction and installation and to operational data related to the DELIVERY to the extent necessary to ensure the SUPPLIER's obligations under the AGREEMENT. - The CUSTOMER shall inform the SUPPLIER without undue delay of any defects, errors, errors or obstacles that occurred during the tests specified in this article of the AGREEMENT. |
|  | The CUSTOMER shall be entitled to claim payment of the contractual penalty on a delay in commencement of the removal of DEFECTS limiting operations of the DELIVERY pursuant to paragraph 28.2.1.1 of the AGREEMENT during the WARRANTY PERIOD amounting to CZK 10,000.- for each even started day of the delay related to each DEFECT, subject to the conditions specified in paragraph 28.2.1 of the AGREEMENT. The CUSTOMER shall be entitled to claim payment of the contractual penalty on a delay in commencement of the removal of DEFECTS not limiting operations of the DELIVERY pursuant to paragraph 28.2.1.1 of the AGREEMENT during the WARRANTY PERIOD amounting to CZK 5,000.- for each even started day of the delay related to each DEFECT, subject to the conditions specified in paragraph 28.2.1 of the AGREEMENT. The CUSTOMER shall be entitled to claim payment of the contractual penalty on a delay in removal of DEFECTS that are not limiting operations of the DELIVERY pursuant to paragraph 28.2.1.2 of the AGREEMENT during the WARRANTY PERIOD amounting to CZK 5,000.- for each even started day of the delay related to each DEFECT, subject to the conditions specified in paragraph 28.2.1 of the AGREEMENT. The total amount of contractual penalties for delay in commencement of the removal of DEFECTS in DELIVERY and delay in removal of DEFECTS within the deadlines for their removal according to paragraph 22.2.3 of the AGREEMENT is limited to 2 % of the PRICE of the relevant DELIVERY. |
|  | The total amount of all contractual penalties for delay with respect to the relevant DELIVERY shall be limited to 15% of the PRICE of the relevant DELIVERY. |

## GUARANTEED PARAMETERS

|  | Contractual penalties in the event that SUPPLIER delivers DELIVERY that do not meet any of the GUARANTEED PARAMETERS are set forth below in this clause of the AGREEMENT. |
| --- | --- |
|  | Not acceptable values of the GUARANTEED PARAMETERS. In the case that the SUPPLIER delivers the DELIVERY not fulfilling any of the GUARANTEED PARAMETERS i so that they are unable to reach the ACCEPTABLE VALUES of the GUARANTEED PARAMETER, according to the AGREEMENT, and the CUSTOMER decides to TAKEOVER the DELIVERY despite of it and he decides as well on the obligation of the SUPPLIER to perform necessary corrective adjustments, the CUSTOMER will utilize the relevant contractual penalty, according to paragraph 22.3.3.2 of the AGREEMENT, until the time of the fulfilment of the GUARANTEED PARAMETER. If the CUSTOMER does not TAKE OVER the DELIVERY, he will have the right to utilize the relevant contractual penalty on the delay, according to paragraph 22.2 of the AGREEMENT, until the time of the achievement of the ACCEPTABLE VALUE of the GUARANTEED PARAMETER. The ACCEPTABLE VALUES of the GUARANTEED PARAMETERS are specified in Annex 5 to the AGREEMENT. |
|  | In the event that SUPPLIER delivers a DELIVERY that fails to meet any of the GUARANTEED PARAMETERS due to the fault of SUPPLIER in such a manner that it fails to meet the allowable ACCEPTABLE VALUES of such GUARANTEED PARAMETER under the AGREEMENT, the parties shall proceed as follows: |
|  | The CUSTOMER has APPROVED, within the PRELIMINARY ACCEPTANCE of the DELIVERY, that the DELIVERY will be taken over by the CUSTOMER and the SUPPLIER, for the non-observance of the GUARANTEED PARAMETER within the ACCEPTABLE RANGE: - Own power consumption of the gas turbine - Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning. - Maximum achievable electrical output of the gas turbine at the generator terminals within 10 minutes of the start-up instruction. - Minimum achievable output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet. - Gross Power Generation Efficiency. - Flue gas temperature at the gas turbine outlet will provide to the CUSTOMER the discount from the PRICE, according to rules stipulated in paragraph 9.3 of the AGREEMENT. |
|  | If the CUSTOMER TAKES OVER the DELIVERY within the PRELIMINARY ACCEPTANCE, the CUSTOMER shall provide the SUPPLIER, within the consequent CONTINUOUS OPERATIONS, the chance to repeat the PERFORMANCE TESTS – Part "A", including the chance to adjust the DELIVERY. The maximum time period for the repetition of the PERFORMANCE TESTS – Part "A" shall not exceed 120 days from the PRELIMINARY ACCEPTANCE of the DELIVERY. Within the period of first 60 days the SUPPLIER shall not be obliged to pay to the CUSTOMER any contractual penalties. In the next 60 days until the prove of the fulfilment of the GUARANTEED PARAMETER, within the repeated PERFORMANCE TEST – Part "A", the SUPPLIER shall pay to the CUSTOMER the contractual penalties according to the following arrangements: |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Own power consumption of the gas turbine VI shall amount to: Contractual penalty (EUR) = T * (SVl1 - Vl1) * D1 + (SVl2 - Vl2) * D2 [EUR] Where the following applies: T; Time of delay (in hours). Vl1; Own power consumption of the gas turbine in operational state 1 guaranteed by the SUPPLIER [kWh/h]. SVl1; Own power consumption of the gas turbine for operational state 1 as determined during the PERFORMANCE TESTS – Part “A” [kWh/h]. Vl2; Own power consumption of the gas turbine in operational state 2 guaranteed by the SUPPLIER [kWh/h]. SVl2; Own power consumption of the gas turbine for operational state 2 as determined during the PERFORMANCE TESTS – Part “A” [kWh/h]. D1; is equal to 0,0061 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0152 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. D2; is equal to 0,0061 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0152 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - If the result is more than „0“, the contractual penalty will be paid at the calculated amount, or - If the result is less than or equal to "0", no contractual penalty will be paid. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning Pgm shall amount to: Contractual penalty (EUR) = T * (Pgm - Pmin) * D [EUR] Where: T; Time of delay (in hours). Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [kWe]. SPgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning as determined during the PERFORMANCE TESTS – Part “A” [kWe]. D; is equal to 0,0061 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0152 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - If the result is more than „0“, the contractual penalty will be paid at the calculated amount, or - If the result is less than or equal to "0", no contractual penalty will be paid. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Minimum achievable output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet Pmin shall amout to: Contractual penalty (EUR) = T * (SPmin - Pmin) * D [EUR] Where: T; Time of delay (in hours). Pmin; Minimum Achievable Performance while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet guaranteed by the SUPPLIER [kWe]. SPmin; The minimum achievable power output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet as determined during the PERFORMANCE TEST – Part “A” [kWe]. D; is equal to 0,0061 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0152 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - If the result is more than „0“, the contractual penalty will be paid at the calculated amount, or - If the result is less than or equal to "0", no contractual penalty will be paid. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Maximum achievable electrical output of the gas turbine at the generator terminals within 10 minutes of the start-up instruction P10 shall amount to: Contractual penalty (EUR) = T * (P10 - SP10 ) * D [EUR] Where: T; Time of delay (in hours). P10; Electric output of the gas turbine at the generator terminals, achievable within 10 minutes of the start-up instruction guaranteed by the SUPPLIER [kWe]. SP10; The electrical output of the gas turbine at the generator terminals achievable within 10 minutes of the start-up instruction as determined during the PERFORMANCE TEST – Part “A” [kWe]. D; is equal to 0,0015 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0024 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the contractual penalty will be paid in the calculated amount, or - If the result is less than or equal to "0”, no contractual penalty shall be paid. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Gross Power Generation Efficiency in operational state 1 Egm1 shall amount to: Contractual penalty (EUR) = T * 360000 SEgm1- 360000 Egm1 * D1 * Pgm Contractual penalty for non-compliance with the GUARANTEED PARAMETER Gross Power Generation Efficiency in the operational state 2 X42 Contractual penalty (EUR) = T * 360000SX42 - 360000 X42* D2 * Pmin Where: Egm1; Gross Power Generation Efficiency in operational state 1 guaranteed by the SUPPLIER [%]. SE gm1; Gross Power Generation Efficiency in operational state 1 as determined during the PERFORMANCE TEST – Part “A” [%]. X4 2; Gross Power Generation Efficiency in operational state 2 guaranteed by the SUPPLIER [%]. SX4 2; Gross Power Generation Efficiency in operational state 2 as determined by the PERFORMANCE TEST – Part “A” [%]. Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [MWe]. Pmin; Minimum achievable output while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet [kWe]. D1; is equal to 0,0006 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0015 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. D2; is equal to 0,0011 [EUR] where the deviation from the GUARANTEED PARAMETER is up to 1 % is equal to 0,0027 [EUR] where the deviation from the GUARANTEED PARAMETER is 1 % or more. The following applies to the contractual penalty’s values: - The result will be rounded to whole numbers, and - In the event that the result is more than "0", the contractual penalty will be paid in the calculated amount, or - In the event that the result is less than "0", no contractual penalty shall be paid. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Flue gas temperature at the gas turbine outlet in the operational state 1 T1 shall amount to: For T1 ≥ 540°C: Contractual penalty (EUR) = T * (T1 - ST1 ) * 0,0061 * (Pgm / Egm1/100 - Pgm) [EUR] Where: T; Time of delay (in hours). Pgm; Maximum achievable electrical output of the gas turbine at the generator terminals after commissioning guaranteed by the SUPPLIER [MWe]. Egm1; Gross Power Generation Efficiency in operational state 1 guaranteed by the SUPPLIER [%]. T1; Flue gas temperature at the gas turbine outlet in operational state 1 guaranteed by the SUPPLIER [°C]. ST1; Flue gas temperature at the gas turbine outlet in operational state 1 as determined during the PERFORMANCE TEST – Part “A” [°C]. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - If the result is more than "0", the contractual penalty will be paid at the calculated amount, or - In the event that the result is less than "0", a bonus will be credited to the SUPPLIER only in the event of non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency" in the operational state 1. - The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency” in operational state 1. |
|  | Contractual penalty for non-compliance with the GUARANTEED PARAMETER Flue gas temperature at the gas turbine outlet in operating condition 2 T2 For T2 ≥ 540°C Contractual penalty (EUR) = T * (T2 - ST2) * 0,0018 * (Pmin / (X42/100) – Pmin) [EUR] Where: T; Time of delay (in hours). Pmin; Minimum Achievable Performance while complying with the required emission limits for pollutants in the flue gases at the gas turbine outlet guaranteed by the SUPPLIER [MWe]. X42; Gross Power Generation Efficiency in operational state 2 guaranteed by the SUPPLIER [%]. T2; Flue gas temperature at the gas turbine outlet in operational state 2 guaranteed by the SUPPLIER [°C]. ST2; Flue gas temperature at the gas turbine outlet in operational state 2 as determined by the PERFORMANCE TEST – Part “A” [°C]. The following applies to the value of the contractual penalty: - The result will be rounded to whole numbers, and - If the result is more than "0", the contractual penalty will be paid at the calculated amount, or - In the event that the result is less than "0", a bonus will be credited to the SUPPLIER only in the event of non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency" in the operational state 2. - The amount of the bonus is limited by the amount of the discount for non-compliance with the GUARANTEED PARAMETER "Gross Power Generation Efficiency” in operational state 2. |
|  | In order to carry out the repeated PERFORMANCE TEST – Part "A" and any adjustments to the DELIVERY, the CUSTOMER and the SUPPLIER shall reach an agreement on procedures, deadlines and possible restrictions related thereto within the PRELIMINARY ACCEPTANCE CERTIFICATE. |
|  | Repeated PERFORMANCE TEST - Part "A" shall be performed within 4 months from the date of PRELIMINARY ACCEPTANCE of the DELIVERY as per the AGREEMENT, unless otherwise agreed between the parties. |
|  | The total amount of liquidated damages for delivery of any portion of the DELIVERY that fails to meet any of the GUARANTEED PARAMETERS - Part "A" , shall be limited to 2 % of the PRICE of the respective DELIVERY. |
|  | Contractual penalty values will be calculated to two decimal places. |

## OTHER CONTRACTUAL PENALTIES

|  | Contractual penalties for breach of the SUPPLIER's obligations in the field of occupational safety and health, fire protection and environmental protection are described in Annex 9 to the AGREEMENT. |
| --- | --- |
|  | The contractual penalty for breach of SUPPLIER'S obligations specified in paragraph 6.4 of the AGREEMENT shall be CZK 100,000. - for each and every breach of the obligation. |
|  | The total amount of the contractual penalties under this paragraph 22.4 is limited to 1 % of the PRICE of the relevant DELIVERY. |

## LATE PAYMENT INTEREST

|  | In the event of default in payment of payments under the AGREEMENT, the debtor shall pay the lender interest on the default at the rate of 12 months EURIBOR + 6% per annum on the amount due for each day of delay. |
| --- | --- |

# damages

|  | For damages the rules as specified in Section 2894 et seq. of the CIVIL CODE shall apply. |
| --- | --- |
|  | The CUSTOMER and the SUPPLIER agree, in accordance with the provisions of Section 2898 of the CIVIL CODE, to limit the CUSTOMER´S right to damages in connection to the AGREEMENT, including the set-off of contractual penalties claimed under Article 22 of the AGREEMENT, to a maximum of 100 % of the PRICE of the respective DELIVERY, excluding VAT, with the exception of the limit stipulated in paragraph 23.4 of the AGREEMENT. In the event of a damage compensated by the CUSTOMER's insurance policy the CUSTOMER shall not claim damages against the SUPPLIER with respect to the part of the damage compensated by the provider of EAR/CAR all risk insurance |
|  | Damages shall be limited to compensation for actual damage, i.e. in particular damage resulting from damage to the CUSTOMER's equipment. At the same time, lost profits, financial losses, losses arising due to the interruption of DELIVERY operations, claims arising from the CUSTOMER's contracts with third parties, or subsequent, indirect and unforeseeable damages, including damage consisting in the costs of securing electricity supplies, are not considered real damages and/or thermal energy as a result of a breach of the CONTRACT on the part of the SUPPLIER, and only in the amount exceeding the contractual fine associated with the breach of the CONTRACT by the SUPPLIER. |
|  | The following claims shall not count towards the limit under paragraph 23.2 of the AGREEMENT: - Damage resulting from a breach of the AGREEMENT caused by a criminal act of the SUPPLIER, - Personal injury and compensation in the event of death due to causes attributable solely to the SUPPLIER, - Damage caused by the breach of the obligation to provide the CUSTOMER with the RIGHTS OF USE; - Damage resulting from infringement of industrial rights (in particular inventions, industrial designs, utility models and trademarks) by the SUPPLIER, - Damage resulting from a breach of the provisions of the AGREEMENT on the protection of CONFIDENTIAL INFORMATION by the SUPPLIER, - Damage resulting from breach of tax obligations of the SUPPLIER related to the institute of unreliable VAT payer, - SUPPLIER's costs for the removal of DEFECTS of the DELIVERY according to the AGREEMENT and CUSTOMER’s costs for the removal of DEFECTS claimed in compliance with paragraph 28.2.8 of the AGREEMENT - Damage caused by the gross negligence and/or wilful misconduct of the SUPPLIER, its SUB-SUPPLIER or an employee of any of them. |
|  | If, as a result of a breach of the AGREEMENT by the SUPPLIER, a third party makes a claim against the CUSTOMER, in particular concerning compensation for damage to third party property or death or personal injury, the CUSTOMER shall immediately notify the SUPPLIER of such claim and shall provide all information known to it concerning the claim. In such case, the SUPPLIER shall assume the defence against such third party claim, if possible. If, as a result of a third party claim described above, the CUSTOMER suffers damages, and provided that the CUSTOMER complies with the conditions set forth in this paragraph and fails to recognize such claim, the SUPPLIER shall indemnify the CUSTOMER for such damages to the extent agreed in this AGREEMENT. |
|  | Any limitations of liability set forth in this Agreement shall also apply to the benefit of the SUPPLIER's affiliates, subcontractors, sub-suppliers, employees, agents, or any other person acting on behalf of the SUPPLIER. |

# SUPPLIER'S LIABILITY

|  | The SUPPLIER shall bear the risk of damage to the DELIVERY until the time of delivery according to the agreed delivery terms. |
| --- | --- |
|  | The SUPPLIER shall be liable for all losses and damages to the DELIVERY or any part thereof, regardless of their cause or nature, which occur to the DELIVERY or any part thereof or to the GOODS which are transported to the SITE according to the agreed delivery terms. |
|  | Unless otherwise stated in the AGREEMENT, the SUPPLIER shall be liable under this AGREEMENT for losses and damages resulting from breach of duty on the part of the SUPPLIER, including defective CHIEF ASSEMBLY, which occur to the SUPPLIER or any part thereof or to the property of the CUSTOMER, until the expiration of the WARRANTY PERIOD. |
|  | The SUPPLIER shall be liable for losses and damages to third party property attributable to the SUPPLIER’s breach of the contractual obligations as per the AGREEMENT and for all injuries (including illness and death) to all persons caused by SUPPLIER’s breach of the contractual obligations as per the AGREEMENT up to the time of expiration of the WARRANTY PERIOD. |

# ownership

|  | Ownership to the SUPPLIER or any part thereof shall pass from the SUPPLIER to the CUSTOMER at the time of execution and/or delivery to the SITE or at the time of handover to the CUSTOMER or at the time of payment, whichever is earlier. |
| --- | --- |

# LAWS, SAFETY, ENVIRONMENT

|  | The SUPPLIER undertakes to comply with the currently applicable legal and other regulations to ensure occupational safety and health (HSE), fire protection and environmental protection, including the applicable ČSN, ČSN/EN and EN, during the implementation of the DELIVERY. |
| --- | --- |
|  | The SUPPLIER has carried out a risk assessment of its activities and will supplement its work procedures with measures to eliminate or reduce these risks. The SUPPLIER declares that it has familiarised itself with the working conditions of the environment in which it will carry out its activities, has assessed the possible risks and has incorporated safety measures into its technological procedures. The assessment of potential risks of the SUPPLIER and the CUSTOMER will be included in QUALITY PLAN in the form attached hereto as Annex 13. |
|  | The SUPPLIER shall equip its workers and cooperating persons with personal protective equipment (PPE) in accordance with the identified risks and safety markings of the CUSTOMER. The SUPPLIER undertakes that its workers and collaborators will use yellow reflective warning vests bearing the SUPPLIER's logo when carrying out their work. Exceptions to the use of reflective vests are works where other safety regulations prohibit it (e.g. welding, burning, etc.). |
|  | The SUPPLIER shall designate its responsible representatives and shall be obliged to invite the CUSTOMER to carry out initial training of these representatives in the internal regulations of the CUSTOMER's occupational health, safety and environmental protection, concerning both the CUSTOMER's own workplace and the facilities that the CUSTOMER's employees or collaborators may enter during the execution of the work. The work cannot be started without this initial training. The SUPPLIER's responsible representatives shall subsequently train the other workers and collaborators of the SUPPLIER at the workplace/SITE. The SUPPLIER shall record this training with the names and signatures of the trained workers and cooperating persons. The SUPPLIER shall be obliged to provide proof of the training of the workers at the CUSTOMER's request. |
|  | The SUPPLIER undertakes that its employees and collaborators shall comply with the obligations and regulations set out in Annex 9 and Annex 10 to the AGREEMENT in the performance of their activities under the AGREEMENT. The SUPPLIER declares that it has familiarised itself with the obligations set out in these documents and undertakes to comply with them and, in the event of a breach of the obligations set out, to pay to the CUSTOMER the contractual penalty to which the breach of the obligation (of the AGREEMENT) is related. |
|  | The SUPPLIER may commence work only when the equipment/work site/SITE on which he will work is secured and demonstrably handed over by the CUSTOMER. |
|  | The SUPPLIER shall appoint a safety coordinator at the SITE in accordance with Act No. 309/2006 Coll., regulating other requirements for occupational safety and health in labour relations and for ensuring safety and health in activities or services outside labour relations (Act on Ensuring Other Conditions of Occupational Safety and Health), as amended, if required by law. The HSE Coordinator shall submit an HSE plan to the SUPPLIER prior to the commencement of work. The SUPPLIER shall be obliged to familiarise itself with the HSE plan and to follow the rules set out therein. The SUPPLIER shall cooperate with the HSE Coordinator and participate in the HSE meetings organised by the HSE Coordinator. |
|  | The CUSTOMER is obligated to arrange for safety and security of the SITE in compliance with REGULATIONS. |

# WARRANTIES

## WARRANTY FOR DELIVERY

|  | The SUPPLIER warrants that the DELIVERY under the AGREEMENT shall be free from DEFECTS during the WARRANTY PERIOD. The WARRANTY PERIOD is set to: |
| --- | --- |
|  | - 24 months from the date of issue of the PRELIMINARY ACCEPTANCE CERTIFICATE; or - 36 months from the date of completion of MILESTONE No. 3 (GAS TURBINE with auxiliaries on SITE) in accordance with Annex 2 to the AGREEMENT; or - 19 120 equivalent operating hours of the GAS TURBINE, whichever of the above occurs earlier. |
|  | If the CUSTOMER discovers during the WARRANTY PERIOD that the SUPPLIER has DEFECTS, the CUSTOMER shall immediately notify the SUPPLIER in writing. SUPPLIER shall remedy the DEFECTS as stipulated in paragraph 28.2 of the AGREEMENT. |
|  | The WARRANTY PERIOD shall be extended by the period during which the CUSTOMER has been unable to use the DELIVERY due to the DEFECT (including the time period for which the equipment is out of operation due to the DEFECT removal attempt). Further, the WARRANTY PERIOD of DELIVERY shall be extended by the proportional period during which the SUPPLIER ordered the CUSTOMER to operate the DELIVERY on the reduced performance (the proportional time will be calculated according to the formula „ordered reduced performance/maximum guaranteed performance * number of days of restricted operation). |
|  | On the parts of the DELIVERY that the SUPPLIER had to replace with new ones, a new WARRANTY PERIOD starts from the moment the DEFECT is rectified. However, this new WARRANTY PERIOD shall be limited to a period of 12 months from the expiration of the WARRANTY PERIOD pursuant to Section 27.1.1.1 or after 24,000 equivalent hours of operation, whichever occurs first, and any liability for DEFECTS pursuant to this paragraph shall expire at the end of such period. The CUSTOMER shall be entitled to the FINAL ACCEPTANCE of the DELIVERY, even if the WARRANTY PERIOD on any part of the DELIVERY continues thereafter due to its repair or replacement. FINAL ACCEPTANCE shall not suspend a new WARRANTY PERIOD on the repaired or replaced parts of the DELIVERY. |
|  | The SUPPLIER shall be liable during the WARRANTY PERIOD for all apparent and latent DEFECTS of the DELIVERY and shall be obliged to remedy them, unless otherwise agreed by the parties. |

## performance bond

|  | The SUPPLIER is obliged to hand over the CUSTOMER the PERFORMANCE BOND at the moment of fulfilment of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE) in compliance with Annex 2 hereto. |
| --- | --- |
|  | The amount of PERFORMANCE BOND must correspond to ten per cent (10 %) of the PRICE of the relevant DELIVERY (excluding VAT). |
|  | The PERFORMANCE BOND shall not expire earlier than sixty (60) days after the FINAL ACCEPTANCE of the respective GAS TURBINE. In the event of delay in PRELIMINARY ACCEPTANCE for reasons attributable to the SUPPLIER, the SUPPLIER is obliged, at his own expense, to extend the validity of the PERFORMANCE BOND so that it expires not earlier than sixty (60) days after the FINAL ACCEPTANCE, otherwise the CUSTOMER is entitled, not earlier than 14 days before the expiration of the validity of the PERFORMANCE BOND, to draw the amount of the PERFORMANCE BOND as a collateral. The SUPPLIER is entitled to replace the PERFORMANCE BOND given to the CUSTOMER with a new or amended PERFORMANCE BOND, provided that the PERFORMANCE BOND will be valid in total for the entire period according to this article of the CONTRACT (every day according to this article of the CONTRACT covered by a PERFORMANCE BOND). |
|  | The PERFORMANCE BOND shall be issued by the SUPPLIER in the currency of the PRICE of the relevant DELIVERY. In the case of PRICE stated in several currencies (CZK, USD, SEK, JPY and EUR), the PERFORMANCE BOND shall be issued either in all the relevant currencies in the same proportion as the currencies are used for the PRICE of the relevant DELIVERY pursuant to the AGREEMENT or it will be issued only in the EURO currency using the exchange rate specified in paragraph 9.1.5 of the AGREEMENT. |
|  | The PERFORMANCE BOND will be reduced according as follows: - to five percent (5 %) of the total PRICE of the relevant DELIVERY excluding VAT (Annex 4 to the AGREEMENT) within sixty (60) days after meeting MILESTONE No. 6 according to Annex 2 to the AGREEMENT (PRELIMINARY ACCEPTANCE of the DELIVERY); - complete release upon fulfilment of the terms of the AGREEMENT – sixty (60) DAYS after the fulfilment of MILESTONE No. 7 (FINAL ACCEPTANCE of the DELIVERY) according to Annex 2 to the AGREEMENT |
|  | The PERFORMANCE BOND may be used by the CUSTOMER to settle a part of the claims of the CUSTOMER arising from the SUPPLIER’s breach of the contractual obligations as per the AGREEMENT. |
|  | The PERFORMANCE BOND shall not be used to secure an advance payment or the remaining part of the advance payment in the event that the SUPPLIER fails to meet its obligations regarding the delivery of the DELIVERY under the AGREEMENT. |
|  | The PERFORMANCE BOND must be issued by a first-class European bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), on which the SUPPLIER and the CUSTOMER agree. The PERFORMANCE BOND must be irrevocable, unconditional and redeemable on first request and without the bank examining the reasons for the requested drawdown and must not be in conflict with the terms of the AGREEMENT. The SUPPLIER shall inform the CUSTOMER if the credit rating of the entity providing the PERFORMANCE BOND falls below rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's). In such a case, the SUPPLIER shall provide the CUSTOMER with a substitute PERFORMANCE BOND, which shall be issued by a first-class European bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's). If the SUPPLIER is unable to fulfil its obligations under the above paragraph in a timely manner solely for macroeconomic reasons/downgrade of the banking sector, the SUPPLIER shall make reasonable efforts to find, within a reasonable period of time, an acceptable bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), if possible. Within these banks that meet these requirements, the SUPPLIER will endeavour to replace the relevant PERFORMANCE BOND with one or more bank guarantees issued by the best banks. The SUPPLIER shall always inform the CUSTOMER about its activities leading to the replacement of the relevant PERFORMANCE BOND. In the event that the SUPPLIER fails to provide a substitute PERFORMANCE BOND within 30 days of the time when the rating of the bank that issued the PERFORMANCE BOND has fallen below the level of BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), the CUSTOMER is entitled to draw on the existing PERFORMANCE BOND up to its full amount and keep it as a financial collateral until a substitute PERFORMANCE BOND is provided in accordance with this paragraph of the AGREEMENT. |
|  | In the event of delay in FINAL ACCEPTANCE for reasons attributable to the SUPPLIER, the SUPPLIER is obliged, at his own expense, to extend the validity of the PERFORMANCE BOND so that it expires not earlier than sixty (60) days after the FINAL ACCEPTANCE, otherwise the CUSTOMER is entitled, not earlier than 14 days before the expiration of the validity of the PERFORMANCE BOND, to draw the amount of the PERFORMANCE BOND as a collateral. |
|  | The obligation to arrange for the issuance of the PERFORMANCE BOND according to the AGREEMENT lies with the SUPPLIER. All costs associated with the PERFORMANCE BOND and its procurement shall be borne by the SUPPLIER and are included in the PRICE of DELIVERY. |

## advance payment guarantee

|  | The SUPPLIER is obliged to hand over the CUSTOMER the ADVANCE PAYMENT GUARANTEE prior the issuance of the invoice for the first advance payment and for the advance payment for the achievement of MILESTONE No. 2 as stipulated in paragraph 10.1.2 of the AGREEMENT. The amount of ADVANCE PAYMENT GUARANTEE for each advance payment must correspond to the amount of the advance payment requested by the SUPPLIER in compliance with paragraph 10.1.2 of the AGREEMENT. |
| --- | --- |
|  | The ADVANCE PAYMENT GUARANTEES shall not expire earlier than sixty (60) days after the achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE) pursuant to Annex 2 to the AGREEMENT. In the event of delay in achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE) for reasons attributable to the SUPPLIER, the SUPPLIER is obliged, at his own expense, to extend the validity of the ADVANCE PAYMENT GUARANTEES so that it expires not earlier than sixty (60) days after the achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE), otherwise the CUSTOMER is entitled, not earlier than 14 days before the expiration of the validity of the ADVANCE PAYMENT GUARANTEE, to draw the amount of the ADVANCE PAYMENT GUARANTEE as a collateral. The SUPPLIER shall be entitled to replace the ADVANCE PAYMENT GUARANTEE with a new or modified ADVANCE PAYMENT GUARANTEE provided that the ADVANCE PAYMENT GUARANTEE shall be valid in the aggregate for the entire period under this paragraph of the AGREEMENT (each day under this paragraph of the AGREEMENT shall be covered by the ADVANCE PAYMENT GUARANTEE). |
|  | The ADVANCE PAYMENT GUARANTEE shall be issued by the SUPPLIER in the currency of the PRICE of the relevant DELIVERY. In the case of PRICE stated in several currencies (CZK, USD, SEK, JPY and EUR), the ADVANCE PAYMENT GUARANTEE shall be issued either in all the relevant currencies in the same proportion as the currencies are used for the PRICE of the relevant DELIVERY pursuant to the AGREEMENT or it will be issued only in the EURO currency using the exchange rate specified in paragraph 9.1.5 of the AGREEMENT. |
|  | The ADVANCE PAYMENT GUARANTEE shall be used to secure an advance payment or the remaining part of the advance payment in the event that the SUPPLIER fails to meet its obligations regarding the delivery of the DELIVERY under the AGREEMENT. |
|  | The ADVANCE PAYMENT GUARANTEE must be issued by a first-class European bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), on which the SUPPLIER and the CUSTOMER agree. The ADVANCE PAYMENT GUARANTEE must be irrevocable, unconditional and redeemable on first request and without the bank examining the reasons for the requested drawdown and must not be in conflict with the terms of the AGREEMENT. The SUPPLIER shall inform the CUSTOMER if the credit rating of the entity providing the ADVANCE PAYMENT GUARANTEE falls below the rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's). In such a case, the SUPPLIER shall provide the CUSTOMER with a substitute ADVANCE PAYMENT GUARANTEE, which shall be issued by a first-class European bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's). If the SUPPLIER is unable to fulfil its obligations under the above paragraph in a timely manner solely for macroeconomic reasons/downgrade of the banking sector, the SUPPLIER shall make reasonable efforts to find, within a reasonable period of time, an acceptable bank with a rating of at least BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), if possible. Within these banks that meet these requirements, the SUPPLIER will endeavour to replace the relevant ADVANCE PAYMENT GUARANTEE with one or more bank guarantees issued by the best banks. The SUPPLIER shall always inform the CUSTOMER about its activities leading to the replacement of the relevant ADVANCE PAYMENT GUARANTEE. In the event that the SUPPLIER fails to provide a substitute ADVANCE PAYMENT GUARANTEE within 30 days of the time when the rating of the bank that issued the ADVANCE PAYMENT GUARANTEE has fallen below the level of BBB- (Standard & Poors or Fitch Ratings) or Baa3 (Moody's), the CUSTOMER is entitled to draw on the existing ADVANCE PAYMENT GUARANTEE up to its full amount and keep it as a financial collateral until a substitute ADVANCE PAYMENT GUARANTEE is provided in accordance with this paragraph of the AGREEMENT. |
|  | The obligation to arrange for the issuance of the ADVANCE PAYMENT GUARANTEE according to the AGREEMENT lies with the SUPPLIER. All costs associated with the ADVANCE PAYMENT GUARANTEE and its procurement shall be borne by the SUPPLIER and are included in the PRICE of DELIVERY. |

## parent company guarantee

|  | The SUPPLIER is obliged to provide the CUSTOMER prior to the issuance of the invoice for the advance payments after the achievement of MILESTONE No. 2 as per paragraph 10.2.1.2 of the AGREEMENT the PARENT COMPANY GUARANTEE in the form corresponding to the draft contained in Annex 12 hereto . In respect of any parent company of the SUPPLIER that is a company or other corporate entity and is registered outside of the Czech Republic, a legal opinion addressed to the CUSTOMER verifying the due execution, authorisation and enforceability of the relevant PARENT COMPANY GUARANTEE, in a form acceptable to the CUSTOMER (acting reasonably), shall be provided by the SUPPLIER together with provision of the PARENT COMPANY GUARANTEE itself. |
| --- | --- |
|  | The PARENT COMPANY GUARANTEE shall not expire earlier than sixty (60) days after the achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE) pursuant to Annex 2 to the AGREEMENT. In the event of delay in achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE) for reasons attributable to the SUPPLIER, the SUPPLIER is obliged, at his own expense, 14 days prior to the expiration of the PARENT COMPANY GUARANTEE at the latest, to extend the validity of the PARENT COMPANY GUARANTEE so that it expires not earlier than sixty (60) days after the achievement of MILESTONE No. 3 (GAS TURBINE with auxiliaries at SITE), otherwise the SUPPLIER shall not be entitled, until the date of submission of the prolonged PARENT COMPANY GUARANTEE, to any due payment under the AGREEMENT. |
|  | The SUPPLIER shall give notice to the CUSTOMER of the change of control in relation to the SUPPLIER to take effect during the validity of the PARENT COMPANY GUARANTEE without undue delay, but within 30 business days of the change of control at the latest. The SUPPLIER shall, within the reasonable time period, deliver to the CUSTOMER a new PARENT COMPANY GUARANTEE in the form corresponding to the draft contained in Annex 12 hereto from the SUPPLIER’s new parent company that has a proven financial capability (anti-money laundering (AML) including KYC procedure and counter terrorism financing (CTF) regulations to be taken into account as well) and shall ensure that such PARENT COMPANY GUARANTEE shall remain valid and enforceable until the expiry of the PARENT COMPANY GUARANTEE. |
|  | The obligation to arrange for the issuance of the PARENT COMPANY GUARANTEE according to the AGREEMENT lies with the SUPPLIER. All costs associated with the PARENT COMPANY GUARANTEE and its procurement shall be borne by the SUPPLIER and are included in the PRICE of DELIVERY. |

# DEFECTS AND THEIR REMOVAL

## EXCLUSION OF LIABILITY FOR DEFECTS

|  | The liability of the SUPPLIER for DEFECTS excludes DEFECTS resulting from: - Improper or inadequate maintenance, unless the maintenance is in accordance with instructions prepared by the SUPPLIER, - Normal wear and tear, - Defects in parts that have been modified in the meantime by a third party or the CUSTOMER, - Improper operation and use of the DELIVERY in violation of the SUPPLIER's instructions for operation, use and maintenance provided by the SUPPLIER. - Installation, assembly, commissioning not performed by the SUPPLIER, unless the installation, assembly or commissioning was based on defective instructions from the SUPPLIER. |
| --- | --- |

## defects removal

|  | The SUPPLIER shall commence the removal of the DEFECT and remove the DEFECT within the following deadlines. |
| --- | --- |
|  | Commencement of the removal of DEFECTS either limiting or not limiting the operation of the DELIVERY within 48 hours from the time of written notification of DEFECT by the CUSTOMER. |
|  | Removal of DEFECTS not limiting the operation of the SUPPLIER shall be carried out by the SUPPLIER within the terms mutually agreed by the parties. If the CUSTOMER and the SUPPLIER do not agree on the date of removal, the SUPPLIER shall be obliged to remove the DEFECT within a reasonable time corresponding to the nature and extent of the DEFECT. |
|  | Removal of DEFECTS limiting the operation of the SUPPLIER shall be provided by the SUPPLIER without undue delay after the commencement of the removal of DEFECT, if possible with respect to the technique and technology, otherwise within the terms mutually agreed by the parties. If the CUSTOMER and the SUPPLIER do not agree on the date of removal, the SUPPLIER shall be obliged to remove the DEFECT within a reasonable time corresponding to the nature and extent of the DEFECT. |
|  | The commencement of the removal of the DEFECT means the identification of the DEFECT by the SUPPLIER or a due professional and competent person authorized by him, whereas the time of DEFECT removal shall be agreed with the CUSTOMER. |
|  | The rectification/removal of the DEFECT means putting the DELIVERY to the compliance with the AGREEMENT and demonstration of such a fact, where appropriate to the nature of the DEFECT, by appropriate checks, inspections, revisions and tests and TAKEOVER of the rectified DELIVERY. |
|  | The SUPPLIER is obliged to follow the AGREEMENT when removing DEFECTS, to secure itself all permits and authorizations necessary to remove the DEFECTS and to comply with all safety measures and regulations. |
|  | The removal of DEFECT must be dule handed over to the CUSTOMER. Of each removal/rectification of the DEFECT the protocol shall be prepared. The DEFECT shall be considered rectified after the TAKE OVER at the moment of signing the protocol on the DEFECT removal, without undue delay of the completion of rectification works with respect to the DEFECT. |
|  | The protocol shall contain the following data: - Date and time of notification of a DEFECT, start and completion of works on DEFECT rectification, date and time of successful TAKEOVER and with DEFECTS limiting the operation of the DELIVERY also date and time of return to normal operation or possibility to use the DELIVERY, - Copy of notification of the DEFECT, - Record from handover of defective part of the DELIVERY by CUSTOMER to SUPPLIER for DEFECT remedy, - Names and family names of SUPPLIER 's and CUSTOMER's employees participating on DEFECT remedy, - Description of the DEFECT, method of its removal, results of examinations and TAKEOVER, - Classification of DEFECT into DEFECTS hindering operation of WORK or of PROJECT or DEFECTS not hindering operation of WORK, - Record of acceptance of defective part of the DELIVERY by SUPPLIER to CUSTOMER after remedy of the DEFECT, - Declaration of SUPPLIER'S authorized representative that the DEFECT was properly remedied and signatures of authorized representatives of CUSTOMER and SUPPLIER. |
|  | The CUSTOMER shall report in writing to the SUPPLIER any DEFECTS found. The written form shall be maintained if the defect report is notified to the SUPPLIER by e-mail to [TO BE ADDED BY PARTICIPANT] (add name, address). The SUPPLIER is obliged to acknowledge receipt by e-mail, to the hands of [TO BE ADDED] (fill in name, address). The decisive date for determining the date and time of notification of the DEFECT are the data from the e-mail of the CUSTOMER. |
|  | In the event that the SUPPLIER fails to commence the removal of the DEFECTS within the terms specified in the AGREEMENT, the CUSTOMER shall be entitled to have the DEFECTS removed by another supplier if the SUPPLIER does not remedy the DEFECT even after the written reminder sent by the CUSTOMER. All costs associated with the removal of the DEFECT in such case shall be borne by the SUPPLIER. The SUPPLIER’s liability for such DEFECT as set forth in paragraph 27.1 of the AGREEMENT shall remain intact despite engagement of the third party |
|  | The SUPPLIER declares that it has included all costs related to the DEFECTS and their removal according to the AGREEMENT in the PRICE. |
|  | At the SUPPLIER's request, the CUSTOMER shall ensure that the ownership of the replaced parts/items is transferred to the SUPPLIER. |

# confidentiality

## BUSINESS AFFAIRS

|  | Neither party shall disclose the CONFIDENTIAL INFORMATION to any third party without the prior written consent of the other party, or use the CONFIDENTIAL INFORMATION for any purpose other than the performance of the AGREEMENT or for the purposes contemplated by this AGREEMENT (both of which are collectively referred to in this Article as the "PURPOSE"), and the CONFIDENTIAL INFORMATION shall be held in confidence by the receiving party with the same degree of care, as is exercised with respect to the receiving party's own equally important CONFIDENTIAL INFORMATION, so as to prevent disclosure to any third party, but at least with reasonable care. The prohibition of disclosure of CONFIDENTIAL INFORMATION does not apply to communications with: Technical, legal, tax and accounting advisors, provided that they are bound by confidentiality obligations at least equivalent to those contained in this Article and limited to such advisors who have a reasonable need to know CONFIDENTIAL INFORMATION for the PURPOSE; CONFIDENTIAL INFORMATION provided by the SUPPLIER to SUB-SUPPLIERS to the extent necessary for the performance of the AGREEMENT by the SUB-SUPPLIERS, provided that they are bound by confidentiality obligations at least equivalent to those contained in this Article; To Affiliates, provided that they are bound by confidentiality obligations at least equivalent to those contained in this Article and limited to such Affiliates who have a reasonable need to know the CONFIDENTIAL INFORMATION for the PURPOSE; in judicial, administrative or arbitration proceedings, to the extent necessary to enforce or defend against claims arising out of or in connection with this AGREEMENT; If required by law or regulation, any governmental or regulatory decision, court order or binding law applicable to the applicable party, provided that, unless prohibited by law, such decision or order will be communicated in writing without undue delay to the disclosing party to afford the disclosing party an opportunity to intervene, and provided further that the receiving party will use reasonable efforts to obtain assurances that the CONFIDENTIAL INFORMATION will be treated as confidential. CONFIDENTIAL INFORMATION disclosed pursuant to such mandatory law, ruling or court order should be marked "Confidential", "Restricted" or similar. The obligations of the first paragraph shall not apply to information which: (i) have been or become public knowledge other than as a result of a breach of this AGREEMENT; or (ii) the relevant Party has been demonstrably informed of this without an obligation of confidentiality at the time of entering into this AGREEMENT; or (iii) has been disclosed to it by a third party without an obligation of confidentiality, provided that such third party is not aware to the receiving parties without breach of any legal or contractual obligation to protect the information; or (iv) independently developed by the receiving party without the use of any CONFIDENTIAL INFORMATION. |
| --- | --- |
|  | The consultants, affiliates, prime contractors and subcontractors referred to in (a), (b) and (c) above are referred to herein as "Permitted Recipients". If a Receiving Party discloses or distributes Confidential Information to Permitted Recipients or has consented to the related disclosure or distribution of Confidential Information, such Receiving Party shall be liable for the acts or omissions of its Permitted Recipients or their employees (even if such Permitted Recipients have ceased to be Permitted Recipients) as if such acts or omissions were the Receiving Party's own acts or omissions where such acts or omissions result in the unauthorized dissemination, use and/or disclosure of such Confidential Information. |
|  | SUPPLIER represents that it has included all costs associated with the protection of CONFIDENTIAL INFORMATION under the AGREEMENT in the PRICE. |

# WITHDRAWAL FROM THE AGREEMENT

## WITHDRAWAL FOR BREACH

|  | Withdrawal from the AGREEMENT for breach of the AGREEMENT is generally governed by Section 2001 et seq. of CODE. In the case of the breach of the AGREEMENT each party shall be entitled to withdraw from the AGREEMENT only if it has provided to the party reasonable remedial period, not shorter than sixty (60) days and the other party did not remedy the breach in time. |
| --- | --- |
|  | In addition to the reasons specified in the Code, the CUSTOMER may withdraw from the AGREEMENT if the following facts occur during the performance of the AGREEMENT: |
|  | - The SUPPLIER enters the liquidation; - the bankruptcy of the SUPPLIER was declared in accordance with the provisions of Act No. 182/2006 Coll., the Insolvency Act, as amended; - The SUPPLIER has become unable to make his payments for any other reason; - the SUPPLIER ceases to meet the conditions for doing business within the European Union, or - the event foreseen in paragraph 6.4.2 of the AGREEMENT occurs, of which the SUPPLIER is obliged to inform the CUSTOMER. |
|  | The SUPPLIER materially or repeatedly violates the principles of work safety according to the AGREEMENT, the REGULATIONS or the APPROVED HSE Manual and does not take reasonable measures. |
|  | The total amount of contractual penalties will exceed the value set forth in paragraph 22.1.1.3 of the AGREEMENT and/or the total amount of contractual penalties damages for delay exceeds the value set forth in paragraph 22.2.4 of the AGREEMENT or the total amount of discounts from the PRICE exceeds the value stipulated in paragraph 9.3.2.9 of the AGREEMENT. |
|  | If the CUSTOMER withdraws from the AGREEMENT for the reason specified in paragraph 30.1.2.3 of the AGREEMENT, the CUSTOMER shall be entitled to demand from the SUPPLIER the removal of the DELIVERY, or parts thereof, and the refund of the PRICE or its part corresponding to the price of the removed part of the DELIVERY paid by the CUSTOMER up to the time of withdrawal. The CUSTOMER shall be entitled to use the PERFORMANCE BOND for refund. In the event of withdrawal due to the fact that the total amount of discounts from the PRICE exceeds the value specified in paragraph 9.3.2.9 of the AGREEMENT, the SUPPLIER may decide within a reasonable period of time to remedy the situation according to paragraph 30.1.1 of the AGREEMENT to pay the CUSTOMER discounts on the PRICE in excess of the value specified in paragraph 9.3.2.9 of the AGREEMENT, in the amount corresponding to the calculation of the discount for the relevant breach of contractual obligations. If the SUPPLIER does so, the CUSTOMER is not entitled to withdraw from the AGREEMENT under this article of the AGREEMENT. |
|  | For the reasons set out in paragraph 30.1.2.1 and 30.1.2.2 of the AGREEMENT, the CUSTOMER shall be entitled to withdraw only with respect to the unfulfilled balance of the DELIVERY. The CUSTOMER shall retain the parts of the DELIVERY already provided by the SUPPLIER. The value of the parts of the DELIVERY to be retained by the CUSTOMER shall be determined according to the PRICE for the fulfilled part of the DELIVERY and, if this cannot be determined according to the AGREEMENT, then based on the agreement of the parties or on the basis of a third party expert opinion. |
|  | For the reasons set out in paragraph 30.1.2.3, the CUSTOMER is furthermore entitled to decide on withdrawal only in respect of the unfulfilled balance of the DELIVERY. In such case, the CUSTOMER shall be entitled to decide to retain the completed parts of the DELIVERY. The value of the parts of the DELIVERY to be retained by the CUSTOMER shall be determined according to the PRICE for the fulfilled part of the DELIVERABLES, and if this cannot be determined according to the AGREEMENT, then based on the agreement of the parties or on the basis of a third party expert opinion. |
|  | In addition to the reasons set forth in the Code, the SUPPLIER may withdraw from the AGREEMENT if the following occurs: |
|  | - the CUSTOMER has entered the liquidation; - the bankruptcy of the CUSTOMER has been declared under the provisions of Act No. 182/2006 Coll., the Insolvency Act, as amended; - the CUSTOMER has become unable to make his payments for any other reason; - the CUSTOMER comes under the direct or indirect control of any competitor of the SUPPLIER in the supply and manufacture of gas turbines; |
|  | The CUSTOMER is in default in payment of the relevant part of the PRICE for more than 60 days from the due date. The SUPPLIER shall notify the CUSTOMER in writing within 20 days after the due date of such amount. In the event that the SUPPLIER notifies the CUSTOMER of the default later, the SUPPLIER shall be entitled to withdraw from the AGREEMENT if the CUSTOMER is in default of payment of the relevant part of the PRICE for more than 40 days from the date of notification. |
|  | A suspension of the performance of the DELIVERY pursuant to paragraph 31.5 of the AGREEMENT occurs. |
|  | If the SUPPLIER or the CUSTOMER withdraws from the AGREEMENT, the following shall apply (if the rules of paragraph 30.1.3 of the AGREEMENT are not applicable): |
|  | The SUPPLIER shall, on the date of receipt of the notice of withdrawal, stop work on the implementation of the DELIVERY, within 10 days at the SUPPLIER's expense preserve the DELIVERY so that no damage can occur, hand over to the CUSTOMER the parts of the DELIVERY or GOODS completed and/or ready for delivery of the part of DELIVERY in pursuance of the TAKEOVER including the CHIEF ASSEMBLY provided up to the date of withdrawal. |
|  | CUSTOMER shall pay to SUPPLIER within 60 days of the completed TAKEOVER the portion of the PRICE corresponding to the parts of DELIVERY handed over pursuant to paragraph 30.1.7.1 of the AGREEMENT, that shall be calculated based on the taken over portions of the DELIVERY, the completion of the MILESTONES and payment schedule, and any demonstrable costs of the party withdrawing from the AGREEMENT arising in relation to the withdrawal. The CUSTOMER shall release the PERFORMANCE BOND on the same date. In the event of withdrawal by the CUSTOMER, the demonstrable costs of the CUSTOMER are limited to the demonstrable costs of the CUSTOMER for completing the delivery beyond the PRICE and the demonstrable costs of the CUSTOMER caused by withdrawal from the AGREEMENT. The demonstrable costs of the CUSTOMER paid pursuant to this clause shall be considered the exclusive compensation of the CUSTOMER's claims arising from the withdrawal from the AGREEMENT. In the event of withdrawal by the SUPPLIER the demonstrable costs of the SUPPLIER shall cover the costs of the preservation of the DELIVERY and her protection against damage, the costs of demobilisation and costs of termination of the contracts concluded with the SUBCONTRACTORS and suppliers of the major components. |
|  | The risk of damage to the DELIVERY passes from the SUPPLIER to the CUSTOMER at the moment of signing the TAKEOVER protocol, if not stated otherwise in the AGREEMENT. |

## WITHDRAWAL FOR OTHER REASON

|  | If the CUSTOMER does not obtain support for electricity from high-efficiency combined heat and power generation from the Ministry of Industry and Trade, and this fact is communicated to the SUPPLIER in writing no later than 4 months before the delivery of the GAS TURBINE to the construction site (MILESTONE No. 3), the CUSTOMER is entitled to withdraw from the DELIVERY (GAS TURBINES) part, for which the CUSTOMER did not receive support for electricity from high-efficiency combined heat and power generation, no later than 4 months before the delivery of the GAS TURBINE to the construction site (MILESTONE No. 3). |
| --- | --- |
|  | If the CUSTOMER withdraws from the DELIVERY for the reason stated in paragraph 30.2.1 of the AGREEMENT, the CUSTOMER has the right to a refund of the PRICE or its part corresponding to the PRICE of the transferred part of the DELIVERY paid by the CUSTOMER until the withdrawal period and at the same time not yet drawn by the CUSTOMER from the ADVANCE PAYMENT GUARANTEE or PARENT COMPANY GUARANTEE. If the PRICE or its part is not returned within 21 days according to the first sentence of this paragraph, the CUSTOMER is entitled to use the ADVANCE PAYMENT GUARANTEE or the PARENT COMPANY GUARANTEE, unless the contracting parties agree otherwise. The CUSTOMER is obliged to release the ADVANCE PAYMENT GUARANTEE and the PARENT COMPANY GUARANTEE or their unused parts, if any, to the SUPPLIER within 7 days after the date of the return of the PRICE or its part according to the first sentence of this paragraph to the CUSTOMER. |
|  | With the exception of the obligations and rights specified in paragraph 30.2 of the AGREEMENT, neither the SUPPLIER nor the CUSTOMER have any right or obligation towards the other party in relation to the withdrawal from the DELIVERY part of the AGREEMENT or the withdrawal from the AGREEMENT, on the basis of or in connection with them, unless expressly stated otherwise in the AGREEMENT. |

# suspension OF DELIVERY

|  | The SUPPLIER is obliged, on the basis of a written request from the CUSTOMER made no later than 30 days before the date of delivery of the GAS TURBINE to the SITE (achievement of MILESTONE No. 3), unless the contracting parties agree otherwise, to suspend the delivery of the DELIVERY or its part and to ensure the storage of the DELIVERY. |
| --- | --- |
|  | The CUSTOMER shall reimburse the SUPPLIER demonstrably and reasonably incurred costs incurred by the SUPPLIER as a result of the suspension of the delivery of the DELIVERY or its part to the CUSTOMER and the provision of storage of the DELIVERY. The SUPPLIER is entitled to demand payment of such costs after the restart of the performance of the DELIVERY or its part (end of suspension) or after the withdrawal of the SUPPLIER from the AGREEMENT pursuant to paragraph 31.5 of the AGREEMENT. The CUSTOMER is obliged to pay the costs in question under this paragraph hereof. The SUPPLIER undertakes not to require the CUSTOMER to pay the costs specified in the first sentence of this paragraph of the AGREEMENT for the first 14 days of suspension of the delivery of the DELIVERY (or part thereof). |
|  | The CUSTOMER shall inform the SUPPLIER of the restart of the performance (end of the suspension) of the DELIVERY by a written notice sent to the SUPPLIER at least 30 days in advance. The delivery date of the GAS TURBINE shall be extended by the time necessary to overcome the consequences of suspension of the delivery of the DELIVERY or its part. |
|  | Upon restart of the performance of the AGREEMENT (end of the suspension), the SUPPLIER shall prepare and submit for the CUSTOMER's approval an amendment to the AGREEMENT that shall settle the consequences of the suspension of the delivery of DELIVERY or its part. |
|  | In the event that the total duration of all suspension exceeds 180 days, the SUPPLIER shall be entitled to withdraw from the AGREEMENT or any part thereof. |
|  | The SUPPLIER is entitled to interrupt (suspend) the delivery of the DELIVERY or its part if the CUSTOMER is in delay with the payment of the relevant part of the PRICE for a period exceeding 30 days from the notice by the SUPPLIER thereof or if the CUSTOMER has not ensured HSE conditions on the construction site in accordance with the REGULATIONS. The SUPPLIER is obliged to notify the CUSTOMER of the delay in writing within 20 days after the due date of the relevant amount. In the event of a justified interruption (suspension) of the delivery of the DELIVERY by the SUPPLIER, the CUSTOMER is obliged to reimburse the SUPPLIER demonstrably and efficiently incurred costs incurred by the SUPPLIER as a result of the interruption of the delivery of the DELIVERY or its part and ensuring the storage of the DELIVERY. The delivery date of the GAS TURBINE shall be extended by the time necessary to overcome the consequences of interruption of the delivery of the DELIVERY or its part. |

# UNPREDICTABLE AND INSURMOUNTABLE OBSTACLES

|  | If unforeseeable and insurmountable obstacles as per Section 2913 of CODE occur, the party affected by such obstacles shall within a reasonable time notify the other party of their commencement and termination and take all reasonable steps necessary to minimize the effect of such obstacles on the performance of this AGREEMENT. |
| --- | --- |
|  | The SUPPLIER and/or the CUSTOMER shall not be liable for failure to perform any obligation of the AGREEMENT if performance is delayed, prevented or affected by unforeseen and insurmountable obstacles pursuant to Section 2913 of the CODE for the time and to the extent necessary to overcome the effects of the event and any schedules and deadlines shall be extended accordingly. |
|  | If the impediments last longer than 180 days in total (even intermittently), the CUSTOMER or the SUPPLIER shall have the right to withdraw from the AGREEMENT. In such case, the CUSTOMER and the SUPPLIER shall proceed in accordance with paragraph 30.1.7 of the AGREEMENT and each party shall bear its own costs related to this fact. |

# ASSIGNMENT OF RIGHTS AND OBLIGATIONS

|  | Neither party to the AGREEMENT shall assign any of its rights or obligations under the AGREEMENT, or any part thereof, to any third party without the prior written consent of the other party. |
| --- | --- |
|  | The RIGHTS OF USE shall be transferred to the CUSTOMER upon signing the protocol of PRELIMINARY ACCEPTANCE of DELIVERY. If any process or use under the AGREEMENT of any part of the DELIVERY delivered by SUPPLIER under this AGREEMENT is restricted or prohibited by court order due to a violation of the RIGHTS OF USE by such practice or use, then the SUPPLIER shall, at its expense, defend, indemnify and hold harmless the SUPPLIER against any third party claim and, if necessary, provide - necessary licenses for the use of the equipment, material or process causing the above violation, or with the prior written consent of the CUSTOMER - replace the equipment, material or process with substantially the same equipment, material or process but which does not cause the infringement referred to above; or - modify the same so as not to cause the foregoing breach; provided, however, that any such substituted or modified portions of the DELIVERY shall comply with the requirements of and be subject to the provisions of this AGREEMENT, and provided further, however, that such substitutions or modifications shall not alter the specification of the DELIVERY pursuant to paragraph 6.2 of the AGREEMENT. SUPPLIER's obligations in this paragraph of the AGREEMENT are subject to the following conditions: - CUSTOMER shall promptly notify SUPPLIER in writing of the third party claim and provide SUPPLIER with a copy of the relevant communication, notice or other action regarding the alleged infringement; - CUSTOMER shall not admit infringement if in compliance with the REGULATIONS, and shall provide SUPPLIER with such authority, information and assistance as SUPPLIER reasonably requires to defend or settle such claim; and If the CUSTOMER ceases to use the DELIVERY or any relevant part thereof, the CUSTOMER shall notify the third party in writing that such cessation of use is not an admission of infringement of intellectual property rights. Any claims by the CUSTOMER shall be barred if the SUPPLIER proves that CUSTOMER is at fault for violating the RIGHTS OF USE. |

# DISPUTE RESOLUTION

|  | All disputes arising out of or in connection with the AGREEMENT, including any issues relating to the termination or any subsequent modification of the AGREEMENT, shall be finally settled in accordance with the Rules of Arbitration of the International Chamber of Commerce ("ICC"). If the value of the entire matter in dispute, including the value of any counterclaims, is EUR 1 million or more, the provisions of the Expedited Procedure Rules shall not apply and the arbitration tribunal shall consist of three arbitrators. If the tribunal consists of three arbitrators, each party shall nominate one arbitrator for confirmation by the ICC. The two arbitrators shall agree on the third arbitrator within 30 days of their nomination. If the two arbitrators fail to agree on a third arbitrator within the 30-day period, the ICC shall select and appoint a third arbitrator. The seat of arbitration shall be Prague, Czech Republic. The language to be used in the proceedings and arbitration shall be Czech. Any order to produce or disclose documents shall be limited to the documents specifically relied upon by each party in its submission(s). Consolidation of arbitrations pending under the ICC Arbitration Rules into a single arbitration will only be possible if all parties have agreed to the consolidation. |
| --- | --- |

# CONFLICT OF INTEREST

|  | The SUPPLIER shall not employ any employee of the CUSTOMER during the execution of the AGREEMENT. The SUPPLIER shall not pay any employee of the CUSTOMER a salary or commission or give a discount on goods or other financial consideration nor shall the SUPPLIER offer and/or give any gift, discount on goods or other financial or non-financial consideration to any such employee. The CUSTOMER shall not employ any employee of the SUPPLIER during the execution of the AGREEMENT. The CUSTOMER shall not pay any salaries, commissions, fees or make any payments or rebates to any employee of the SUPPLIER, nor shall the CUSTOMER offer or give any gift or other financial or non-financial consideration to any such employee. |
| --- | --- |

# CONTACTS AND CORRESPONDENCE

|  | All contractual correspondence between the CUSTOMER and the SUPPLIER must be sent to the following addresses: |
| --- | --- |
|  | ORDERED BY: - Name: [TO BE ADDED] - E-mail: [TO BE ADDED] |
|  | SUPPLIER: - Name: [ADD PARTICIPANT] - E-mail: [ADD PARTICIPANT] |
|  | All instructions, notices, consents, authorizations, approvals, acknowledgments and other documents transmitted pursuant to the AGREEMENT shall be in writing and signed in accordance with the AGREEMENT and shall be deemed to have been delivered: |
|  | In case of sending by e-mail, the moment of delivery, |
|  | In the case of personal handover, the moment of handover (written confirmation of handover required), |
|  | If sent by registered mail within the Czech Republic within 10 working days from the date of dispatch, |
|  | If sent by registered mail between different countries within 21 calendar days from the date of dispatch. |

# miscellaneous

|  | Provisions of the AGREEMENT which, by their nature and meaning, survive the termination of the AGREEMENT, including provisions relating to limitation or exclusion of liability, shall survive and be enforceable by the CUSTOMER and the SUPPLIER notwithstanding the termination of the AGREEMENT. In any event, the following provisions shall apply: paragraph 29.1, paragraph 6.4.2, Article 23 and Article 24. |
| --- | --- |
|  | The SUPPLIER shall be fully liable for its SUB-SUPPLIERS, their employees and entities acting for them, to the same extent as for its own acts or omissions when they provide performance under the AGREEMENT. |
|  | The SUPPLIER is obliged to inform the CUSTOMER within a reasonable period of time of any change of registration in the commercial or trade register affecting the AGREEMENT. |
|  | The language of the AGREEMENT is Czech. All negotiations shall be conducted in Czech unless agreed otherwise by PARTIES. |
|  | If, by mistake or omission of the parties to the AGREEMENT, any part of the AGREEMENT violates a mandatory provision of law, only that part of the AGREEMENT shall be void pursuant to Section 576 of CODE. Compensation for any damage caused by the invalidity of such part of the AGREEMENT shall be governed by Section 579 of CODE. If there is such a change in the law as to render any previously mandatory provisions of the law dispositive or extinguish them altogether, the parties to this AGREEMENT shall proceed in such a manner as to give the best possible effect to the intention of the parties to this AGREEMENT as expressed by its execution under the terms of the law in force and binding at the time of its execution. |
|  | If the CUSTOMER or the SUPPLIER submits a proposal for an amendment to this AGREEMENT, the other party undertakes to comment on the proposal within 14 days of its receipt. During this period, the party who prepared the proposal shall be bound by it. The absence of a statement shall in no way be construed as an acceptance of any proposal. |
|  | Where any contact details are specified in this AGREEMENT, the relevant party may change them at any time by written notice delivered to the other party in accordance with this AGREEMENT; this shall be without prejudice to the SUPPLIER's obligation, if any, to obtain the CUSTOMER's consent to substitute a person in a particular position. |
|  | The AGREEMENT shall be concluded only after full agreement on all the details of the AGREEMENT. Pursuant to Section 1740(3) of CODE, the parties to the AGREEMENT hereby exclude acceptance of an offer with an amendment or deviation from the wording of this AGREEMENT. |
|  | This AGREEMENT may be amended or cancelled only by agreement of the CUSTOMER and the SUPPLIER in writing by an addendum signed by representatives of the CUSTOMER and the SUPPLIER authorized to sign the AGREEMENT, unless otherwise specified in the AGREEMENT (reserved amendments to the AGREEMENT). |
|  | The CUSTOMER and the SUPPLIER agree that they have read the AGREEMENT, understand its entire wording, that the AGREEMENT is not prepared on conspicuously unfavourable terms and that they agree to the entire content of the AGREEMENT. |
|  | The AGREEMENT shall come into force and effect on the date the AGREEMENT is signed by both parties to the AGREEMENT. The signing of the AGREEMENT by both parties to the AGREEMENT may be done physically or electronically. In the case of electronic signature, the AGREEMENT is signed by the date of attachment of the electronic signature pursuant to Act No. 297/2016 Coll., on trust services for electronic transactions, as amended, by both parties to the AGREEMENT. |
|  | Upon the signing of the AGREEMENT, all prior written and oral understandings, promises, assurances, warranties, representations and understandings between the CUSTOMER and the SUPPLIER concerning the subject matter of the AGREEMENT, whether written or oral, shall cease to be valid and all other relationships shall be governed solely by the provisions of this AGREEMENT, including its attachments and any approved amendments. |
|  | The SUPPLIER acknowledges that the CUSTOMER, by virtue of the performance of this AGREEMENT, must process, to the extent necessary, the personal data of the SUPPLIER's employees, including its SUB-SUPPLIERS, who participate in the performance of this AGREEMENT. The rights of these employees arising from the processing of their personal data by the SUPPLIER are contained in the "Information Memorandum" set out in Annex 11 to this AGREEMENT. The SUPPLIER undertakes to make its employees, including its SUB-SUPPLIERS, aware of this document. |
|  | The following annexes form an integral part of the AGREEMENT: - Annex 1 – Binding LTSA draft - Annex 2 – List of MILESTONES - Annex 3 – Payment Schedule - Annex 4 – Price tables - Annex 5 – GUARANTEED PARAMETERS of DELIVERY - Annex 6A – List of SUB-SUPPLIERS - Annex 6B – List of suppliers of major components - Annex 7 – BOOK "B", TENDER DOCUMENTATION - Annex 8 – Part of the SUPPLIER's offer - Annex 9 – Rules for SUPPLIERS - Annex 10 – Welding inspection management rules and other CUSTOMER's by-laws - Annex 11 – GDPR Information - Annex 12 – Form of PARENT COMPANY GUARANTEE - Annex 13 – Table of the Assessment of the Risks |
|  | The SUPPLIER shall not be obliged to perform this AGREEMENT if such performance is prevented by any impediments resulting from national or international foreign trade affecting the CUSTOMER or customs requirements or any embargoes or other sanctions imposed on the CUSTOMER, in particular embargoes or other sanctions imposed by the United Nations, the EU or the USA |
|  | Any consent, approval, acceptance, etc. shall not be unreasonably withheld or delayed. |
|  | The SUPPLIER declares that it is not prevented from providing performance under this AGREEMENT as of the date of its signing by any measures taken by the Government of the Czech Republic or other competent authorities of the Czech Republic or the European Union in connection with the COVID-19 disease, the occurrence of the SARS CoV-2 coronavirus or the war conflict in Ukraine related to the territory of the Czech Republic or the SUPPLIER's activities (hereinafter referred to as "Measures"). The SUPPLIER expressly declares, as of the date of signing of the AGREEMENT, that it has read all the Measures in detail and that it does not consider any of the provisions set forth therein to be ones that it could not reasonably have foreseen. However, given the long-term nature of performance under this AGREEMENT, the SUPPLIER is unable to anticipate the development of measures to be taken in the Czech Republic or the European Union in connection with the COVID-19 disease, the occurrence of the SARS CoV-2 coronavirus or the war conflict in Ukraine, or the occurrence of other obstacles in connection with the foregoing that will affect the SUPPLIER's ability to properly perform its obligations under this AGREEMENT. |

# insurance

|  | The CUSTOMER shall take and maintain the Construction All Risk/Erection All Risk (CAR/EAR) insurance policy as per conditions agreed below up to the extent of coverage availability at reasonable terms on the market for the time of each specific project. Due to contract length, supplied technology change and insurance market volatility should the coverage be unobtainable at reasonable terms, conditions might be re-negotiated and set according to mutual agreement between CUSTOMER and SUPPLIER. The sums set hereon could be adjusted based on inflation/deflation as of “zero point”. Zero point – signing date of this AGREEMENT. |
| --- | --- |
|  | The CUSTOMER shall provide an C/EAR insurance in accordance as a minimum with the requirements set out in this Article 38 covering the covering the overall project and shall send a copy of this EAR insurance to the Supplier within thirty (30) days after the commencement of the site works. The Supplier and its subcontractors shall be named as co-insureds and the insurers’ waiver of their subrogation rights shall be provided. |
|  | Beyond the CUSTOMER and other parties, the CUSTOMER wants or is obliged to include into the coverage, the following parties shall be named insureds: |
|  | The SUPPLIER and all its affiliated companies being involved in the execution of the project (whether manufacturing, delivering or erecting/testing) |
|  | All subcontractors/sub-suppliers of the SUPPLIER. |
|  | Insurers waive their subrogation rights all such named insured persons to the extent that the insurers provide insurance cover under this policy. |
|  | Other provisions to be provided by the Erection All Risks Policy: |
|  | The liability of insurers shall commence latest with when the first risks of construction/ erection activities are starting on Site and shall not expire before Provisional Acceptance date (PAC) given to CUSTOMER by the End user. |
|  | The Erection All Risks Policy shall be endorsed to provide an Extended-Maintenance Cover after this PAC Date during the SUPPLIER’s DEFECTS Liability Period (WARRANTY PERIOD) under the AGREEMENT. |
|  | The Erection All Risks Policy shall be endorsed to provide separate Surrounding/Existing Property cover with a limit in no case less than EUR 1,000,000 per occurrence. |
|  | The sum insured has to be automatically reinstated after payment of a claim without additional premium, or, if the policy does not contain such a provision, the CUSTOMER has the obligation to reinstate immediately the full covered values immediately after the occurrence of a damage at its own expense. |
|  | The Erection All Risks Policy shall be non-cancellable, unless otherwise provided by law |
|  | The Erection All Risks Policy shall be endorsed to provide cover loss or damage arising out of Strike, Riot and Civil Commotion (with either, where reasonably available, no sublimit, or, if a sublimit for this cover has to be applied due to market restrictions, the applicable sublimit shall be mutually agreed between CUSTOMER and SUPPLIER). |
|  | All claims are payable in that currency in which the costs of loss or damage will arise. |
|  | The Comprehensive Third Party Liability policy insurance shall cover CUSTOMER’S and SUPPLIER´S legal liability with a limit of indemnity of not less than 5 million EUR (or equivalent in other currency) per occurrence and 10 million EUR (or equivalent in other currency) in the aggregate. |
|  | The terms and conditions of the policy shall be in accordance with good industrial standards which are applied for Projects of comparable size, with not broader exclusions and restraints as are typically required by the international insurance market for this type of policies, and the policy shall contain all typical extension as are commonly provided under such type of policies, like for example: |
|  | Costs for removal of debris, salvage, fire extinguishing and demolition costs |
|  | Extra costs for overtime, Sundays, holidays, and night work as well as for express freight with an adequate first loss sum insured |
|  | Additional costs for air freight on a first loss basis |
|  | Professional Fees Clause |
|  | Off-site Storage Clause |
|  | Automatic Increase Clause |
|  | 72 Hours Clause |
|  | Plans, Documents and Computer Records Clause |
|  | Interim Payments Clause |
|  | Free Issue Materials Clause |
|  | The deductibles to be applied under the Erection All Risks policy shall not exceed those that are obtainable on the market at the reasonable terms. |
|  | Insurances to be maintained by the SUPPLIER as insuring party |
|  | Without prejudice to the SUPPLIER's other obligations under this Agreement, the SUPPLIER shall take out insurance in accordance with the following stipulations and shall procure that such insurance remains valid for the entire duration of the Term and until the expiry of all of the SUPPLIER's obligations, warranties and liabilities under or in connection with this Agreement. The insurance may be on annual basis with respective renewals each year. |
|  | The SUPPLIER shall deliver to the CUSTOMER upon the CUSTOMER's written request certificates of the SUPPLIER’s insurance, evidencing that the SUPPLIER is in accordance with the insurance requirements under this Agreement. |
|  | In particular, the SUPPLIER hereby undertakes to sign and to keep the following insurance coverage. The SUPPLIER shall indemnify and hold the CUSTOMER harmless from any losses, damages, legal proceedings, or claims arising out of the SUPPLIER's failure to comply with its obligations under this paragraph 38.7.3 of the AGREEMENT. |
|  | Third Party Liability: general third party liability policy for damage and injury caused to third parties covering, SUPPLIER’s legal liability arising out of the performance of the Agreement, or which are the consequence of the latter, for any and all damage caused by the SUPPLIER and by any possible subcontractors falling within the SUPPLIER's vicarious liability for its subcontractors. Such insurance policy shall have a limit of EUR 20 000 000 per occurrence and in aggregate and must cover property damage, death/bodily injuries caused to third parties (including the CUSTOMER and its own employees), and product liability. CUSTOMER shall be an additionally insured person with insurers’ waiver of their subrogation rights, but only to the extent that death/bodily injury and/or property damage is caused by the SUPPLIER’s negligence. |
|  | Professional Indemnity insurance to cover SUPPLIER’s legal liability for third party damages (death/bodily injury and/or property damage, including damage to CUSTOMER’s existing property, however excluding loss or damage to the Works itself) arising out from SUPPLIER’s professional activities, with a limit of liability of EUR 10 000 000 per occurrence and in the aggregate per project (corresponding to each DELIVERY). |
|  | Mandatory insurances: all mandatory insurances required to be maintained by the SUPPLIER in accordance with applicable Law (for example, motor third party liability). Such insurance policies will have limits in compliance with the applicable Law and/or appropriate to cover the SUPPLIER in case of requests for damages arising out of the performance of the Agreement. The SUPPLIER will, subject to the limitations and exclusions set forth in this Agreement, in any event be liable for any event not covered by insurance due to insurance policy thresholds or exclusions. |
|  | In any event, in no way will the taking out of the above-mentioned insurance policies limit the SUPPLIER's liability arising out of the Agreement, the applicable Law or otherwise. In particular, the SUPPLIER will remain liable (subject to the limitations and exclusions set forth in this Agreement) for the damage caused by the SUPPLIER and which are not covered for any reason whatsoever by these insurance policies as a result of fixed excess, percentage excess, maximum coverage, exclusions and/or limitations of coverage or any other reason related to the effectiveness or to the scope or to the limitations of the insurance policies. The cost of the insurance coverage to be maintained by the SUPPLIER in accordance with this paragraph 38.7 of the AGREEMENT has been included in the PRICE. In no way may anything provided for under this article be interpreted to the extent of reducing, amending, or excluding the SUPPLIER's liability. |

# SIGNATURES

| On behalf of the CUSTOMER: |  | On behalf of the SUPPLIER: |
| --- | --- | --- |
| In ....................................... on ..................... |  | In ....................................... on ..................... |
| ..................................................................... |  | ..................................................................... |
| ..................................................................... |  | ..................................................................... |

Annex 1

Binding LTSA draft

Annex 2

List of MILESTONES

Annex 3

Payment Schedule

Annex 4

Price 	tables

Annex 5

GUARANTEED 	PARAMETERS of DELIVERY

Annex 6A

List of	 SUB-SUPPLIERS

Annex 6B

List of suppliers of major components

Annex 7

BOOK "B", TENDER DOCUMENTATION

Annex 8

Part of the 	SUPPLIER's offer

Annex 9

Rules for suppliers

Annex 10

Welding inspection management rules 	and other CUSTOMER's by-laws

Annex 11

GDPR Information

Annex 12

Form of PARENT COMPANY GUARANTEE

Annex 13

Table of the Assessment of the Risks